## Activity Plan 2020
Activity Plan - 2021
State Ministry of Urban Development, Coast Conservation, Waste Disposal and Community Cleanliness
Implementing Agency |  | State Ministry of Urban Development, Coast Conservation, Waste Disposal and Community Cleanliness
Name of the Project |  | Transport Development Project
Area of Responsibility |  | Improving Urban Public Transport
SN | Name of the Project/ Sub Component/ Sub activity | Date of Commencement | Date of Completion | TEC (Rs.Mn) | Allocation - 2021 (Rs.Mn) | Cumulative Financial & Physical Progress up to 31.12.2020 | T/P | January | February | March | April | May | June | July | August | September | October | November | December | Output | Outcome | Responsible officer (Name/ Designation/ Telephone no)
1 | Implementation of Colombo Metro Network -PPP Basis (Red, Green, Blue & Purple line)
1.1 | Consultancy Service for refining of Pre-feasibility and feasibility study for purple line | 2021-02-01 | 2021-10-01 | 60 | 26.5 | - | PT | - | 2% | 10% | 15% | 25% | 35% | 52% | 60% | 80% | 100% | - | - | Completion for the FS for the Purple line in PPP basis | To implement a Colombo Metro Network to minimize the traffic congestion and to save the annual economic loss due to traffic crisis | Project Director : Eng. P.P. Wijesekara , Deputy Project Director : Eng. P. Dissanayake ,Senior Engineers: Eng.N.B.A.P. Nissanka , Eng. Shanika Hemachandra Tel: 011 2870 751
PP
[6 empty] | - | FT | - | - | 6 | - | 23 | - | - | - | 26.5 | - | - | -
FP
1.2 | Consultancy Service for Individual consultancy for PPP basis evaluation and procurement process | 2020-04-22 | 2021-12-31 | 5.95 | 2 | 21.3% | PT | 21.3% | 25% | 26% | 26% | 26% | 50% | 50% | 52% | 53% | 60% | 75% | 100% | Preparation of RFP Completion of Evaluation and Negation of proposals in PPP basis
PP
[6 empty] | 1.15 | FT | - | 1.35 | 1.55 | 1.75 | - | 1.95 | 2.15 | 2.35 | 2.55 | .2.75 | 2.95 | 3.15 |  |  |  | 7
FP
1.3 | Consultancy Service for Owner Consultancy for proposal evaluation | 2019-03-06 | 2020-01-31 | 76.98 | - | Terminated | PT
PP
[6 empty] | 38.49 | FT
FP
1.4 | Consultancy Service for Independent Engineer | 2021-10-15 | 2024-12-30 | 1686.61 | - | - | PT | - | - | - | - | - | - | - | - |  | 2% | 3% | 5% | To review of designs, drawings, specific captions and Construction Supervision for the Implementation of Colombo Metro System
PP
[6 empty] | - | FT | - | - | - | - | - | - | - | - | - | - | - | -
FP
1.5 | Consultancy Service for Environmental Impact Assessment | 2018-12-17 | 2019-07-17 | 12.6 | 4.13 | 100% | PT | - | - | - | - | - | - | - | - | - | - | - | - | To obtain the Environmental clearance for the Metro Network
PP
[6 empty] | 8.47 | FT | - | 3.5 | - | - | - | 4.13 | - | - | - | - | - | -
FP
1.6 | Social Impact Assessment (SIA) and Resettlement Action Plan (RAP) for balance part of the Purple line | 2021-06-15 | 2022-03-31 | 5 | 1 | - | PT | - | - | - | - | - | 5% | 10% | 15% | 20% | 25% | 30% | 35% | Completion of SIA and RAP
PP
[6 empty] | - | FT | - | - | - | - | - | - | - | 0.3 | - | - | - | 1
FP
2 | Implementation of Kadawatha Multimodal Center
2.1 | Consultancy Service for Multimodal Center | 2018-02-19 | 2021-05-10 | 16 | 0.5 | 78% | PT | 80% | 82% | 90% | 95% | 100% | - | - | - | - | - | - | - | To complete the construction of Multi Model Center at Kadawatha | Development of an integrated transit system that provides satisfactory service coverage for people and freight transport by enhancing the connectivity will be achieved through construction of multimodal transport centres | Project Director : Eng. P.P.Wijesekara , Deputy Project Director : Eng. P. Dissanayake ,Senior Engineers: Eng.Padmini Wanigasekara Tel: 011 2870 751
PP
[6 empty] | 11.84 | FT | - | - | - | - | - | 0.5 | - | - | - | - | - | -
FP
2.2 | Construction of Kadawatha Multimodal Center - Stage 1 | 2018-10-10 | 2019-12-23 | 182.73 | - | 100% | PT
PP
[6 empty] | 173.68 | FT
FP
2.3 | Construction of Kadawatha Multimodal Center - Stage II | 2019-11-14 | 2021-05-10 | 203 | 10.87 | 78% | PT | 80% | 82% | 90% | 95% | 100% | - | - | - | - | - | - | -
PP
[6 empty] | 76.73 | FT | - | 5 | - | 10 | - | 10.87 | - | - | - | - | - | -
FP
3 | Construction of Polduwa By Pass Road (Stage 03)
3.1 | Construction of Polduwa By Pass Road (Stage iii) | 2018-06-25 | 2020-11-01 | 497.38 | 5 | 82% | PT |  | Proposed to Terminate | [10 empty] | To completes the assigned section of the construction of Polduwa Bypass road | To reduce the traffic congestion in the main road of Battaramulla | Project Director : Eng. P.P.Wijesekara , Deputy Project Director : Eng. P. Dissanayake ,Senior Engineers: Eng.Padmini Wanigasekara Tel: 011 2870 751
PP
[6 empty] | 286.25 | FT | - | - | - | 5 | - | - | - | - | - | - | - | -
FP
4 | Project Operational Works
4.1 | Operational Expenditure | 2021-01-01 | 2021-12-31 | 50 | 50 | - | PT | 8.33% | 16.67% | 25% | 33.33% | 41.67% | 50% | 58.33% | 66.67% | 75% | 83.33% | 91.67% | 100% | Competion of assigned tasks by the Ministry in scheduled time |  | Project Director : Eng. P.P.Wijesekara , Deputy Project Director : Eng. P. Dissanayake , Project Secretary: Ms. Jayamini Ranasingha
PP
[6 empty] | - | FT | 4.24 | 8.4 | 12.56 | 16.72 | 20.88 | 25.04 | 29.2 | 33.36 | 37.52 | 41.68 | 45.84 | 50
FP
Grand Total |  |  |  | 1109.64 | 100