## Cover
Activity Plan – 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Project |  | : | Town Development Projects in Nine Provinces
Implementing Agency |  | : | Urban Development Authority
Project Summary:
1. Construction of Market at Nuwara Eliya (Stage I)
2. Design and Construction of Infrastructure Facilities at Railway Station at Hatton (Stage IV)
3. Construction of Bus Stand at Ginigathhena
4. Relocation of Filling Station of SLTB at Yatinuwara Depot
5. Proposed New Conference Hall for Sri Vidhyasagara Maha Pirivena at Hirikaduwa, Menikhinna
6. Proposed Monk Residence for Mihindu Dharmapeeta Vihara at Digana, Rajawella
7. Proposed Dharma Shalawa Building at Sri Lokananda Buddhist Centre, Kandy
8. Proposed Extension at Sri Dharmawardhanaramaya Viharaya at Medamahanuwara
9. Proposed Construction of Hostels for Monks for Sri Sandagiri Thapowana Pirivena at Medamahanuwara
10. Proposed Multipupose Religious Building for Kuruambe Dhaham Sevana Meditation Centre at Narampanawa
11. Design and Construction Infrastructure Facilities for Sri Dalada Maligawa (Stage IV)
12. Development of Bus Stand at Halloluwa (Stage II)
13. Development Bus Stand at Hasalaka
14. Infrastructure Development of Bus Stand at Mullativu (Stage III)
15. Construction of Two Storied Library Building for Kandawali School at Puthukudiyiruppu
16. Construction of Two Storied Classroom Building for Bharathi School at Puthukudiyiruppu
17. Bus Stand Development at Jaffna (Stage II)
18. Bus Stand Development at Mannar
19. Construction of Danashalawa of Mirisawetiya at Anuradhapura (Stage I)
20. Balance Work of Shrine Room of Lankaramaya Temple at Anuradhapura
21. Proposed Renovation of Vihara Mandiraya at Isurumuniya Temple at Anuradhapura
22. Proposed Facility Building at Srimahabodhi Premises
23. Construction of Sangavasaya of Tuparamaya at Anuradhapura
24. Kumbichchiyankulama Wewa Recreational Area Development (Phase V) - Bridge No. 3
25. Town Improvement Project at Welikanda
26. Improvement to Eluwankulama - Aruwakkalu Road
27. Development of Beach Park at Chilaw
28. Construction of Weekly Fair at Maho
29. Development of Private Bus Stand at Batticaloa
30. Development of Walasmulla Pola
31. Wedasiti Kanda Entrance Development
32. Baddegama Town development (Bus Stand Development)
33. Construction of Proposed Public Market and Playground at Ahungalla
34. Development at Wellawaya Pola
35. Construction of Piliyandala By-pass Road (Stage I)
36. Construction of Piliyandala By-pass Road (Stage II)
37. Construction of Kottawa Thalagala Road (Stage I)
38. Construction of Kottawa Thalagala Road (Stage II)
39. Construction of Kirimandala Mawatha Road (CMC Road)
40. Moratuwa Town Development (Weerapuran Appu Park)
41. Construction of Internal Roads at Techno City at Homagama
42. Construction of Multi Purpose Building at Boralesgamuwa
43. Children's Orphanage at Aththidiya (Stage I)
44. Children's Orphanage at Aththidiya (Stage II)
45. Construction of New Market at Katubedda
46. Pola Development at Wellampitiya
47. Construction of Real Time Flood Mitigation Center at Kirimandala Mawatha
48. Belek Kade Pola Development at Ratmalana
49. Development of Bus Stand (Link Existing Railway Station) at Aluthgama
50. Development of Pola Area at Horana (Phase II)
51. Construction of Kithudana Pubuduwa National Center at Walpola, Ragama (Stage II)
52. Public Market at Minuwangoda
53. Drainage Design and Improvements at Wetland Park, Gampaha (Stage II)

## 1
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Central Province - 13 Projects
Nuwara Eliya District
Sub Project - 01. Construction of Market at Nuwara Eliya (Stage I)
i | Construction of basement | 185 | 60.65 | 98.82 | 2019-08-30 | 30-July-20 | 35% | PT | - | 80% | 100% | - | Construction of market area and facilitating the venders and traders
[8 empty] | PP | - | - | - | -
|  | 175 |  |  |  |  | 34.66% | FT | - | 80% | 100% | -
[8 empty] | FP | - | - | - | -
ii | Construction of ground floor | 80 | - | - | 2020-08-01 | 31-Dec-20 | - | PT | - | - | 50% | 100%
[8 empty] | PP | - | - | - | -
|  | 68.48 |  |  |  |  | - | FT | - | - | 50% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 265 | 60.65 | 98.82
243.48
Sub Project - 02. Design and Construction of Infrastructure Facilities at Railway Station at Hatton (Stage IV)
i | Construction of grid 8-11 up to 1st floor slab, electrical and finishing work (painting and lighting) | 60 | 15.76 | 5 | 2019-11-13 | 2020-07-31 | 75% | PT | - | - | 100% | - | Completion of railway station building and improving transport infrastructure facilities
[8 empty] | PP | - | - | - | -
|  | 48.85 |  |  |  |  | 32.26% | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 60 | 15.76 | 5
48.85
Sub Project - 03. Construction of Bus Stand at Ginigathhena
i | Completion of balance work (glass curtains, drains etc.) | 100 | 50.9 | 10 | 2018-07-30 | 2020-07-31 | 95% | PT | - | - | 100% | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 80.49 |  |  |  |  | 63.24% | FT | - | 80% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 100 | 50.9 | 10
80.49
Kandy District
Sub Project - 04. Relocation of Filling Station of SLTB at Yatinuwara Depot
i | Installation of fuel tank and finishing work (painting and electrical work) | 26.26 | 10.83 | 8 | 2019-07-23 | 2020-06-30 | 75% | PT | - | 100% | - | - | Relocation of the fuel station at Kandy Good Shed for paving the way for Multi Model Transport Hub
[8 empty] | PP | - | - | - | -
|  | 23.33 |  |  |  |  | 46.42% | FT | - | 80% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 26.26 | 10.83 | 8
23.33
Sub Project - 05. Proposed New Conference Hall for Sri Vidhyasagara Maha Pirivena at Hirikaduwa, Menikhinna
i | Completion of super structure | 5.87 | 3.6 | 3 | 2019-10-22 | 2020-06-30 | 60% | PT | - | 100% | - | - | Completion of the conference hall and improving facilities at the pirivena
[8 empty] | PP | - | - | - | -
|  | 7.08 |  |  |  |  | 50.85% | FT | - | 90% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 5.87 | 3.6 | 3
7.08
Sub Project - 06. Proposed Monk Residence for Mihindu Dharmapeeta Vihara at Digana, Rajawella
i | Wall construction and finishing work (painting and plastering) | 6.81 | 3.82 | 1.99 | 2019-10-22 | 2020-07-31 | 50% | PT | - | 75% | 100% | - | Providing better accommodation facilities for the monks in the viharaya
[8 empty] | PP | - | - | - | -
|  | 7.81 |  |  |  |  | 48.91% | FT | - | 60% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 6.81 | 3.82 | 1.99
7.81
Sub Project - 07. Proposed Dharma Shalawa Building at Sri Lokananda Buddhist Centre, Kandy
i | Finishing work (painting, electrical work and plastering) | 5.19 | 4 | 2.47 | 2019-10-17 | 2020-02-28 | 100% | PT | - | - | - | - | Completion of the Dharma Shalawa and improving facilities in the historical temple and handed over
[8 empty] | PP | - | - | - | -
|  | 6.47 |  |  |  |  | 61.82% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 5.19 | 4 | 2.47
6.47
Sub Project - 08. Proposed Extension at Sri Dharmawardhanaramaya Viharaya at Medamahanuwara
i | Completion of super structure and finishing work (plastering and painting) | 6.6 | 1.84 | 4 | 2019-07-16 | 2020-06-30 | 50% | PT | - | 100% | - | - | Construction of the shrine room and improving facilities in the historical temple
[8 empty] | PP | - | - | - | -
|  | 7.63 |  |  |  |  | 24.12% | FT | - | 77% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 6.6 | 1.84 | 4
7.63
Sub Project - 09. Proposed Construction of Hostels for Monks of Sri Sandagiri Thapowana Pirivena at Medamahanuwara
i | Completion of super structure and finishing work (plastering and painting) | 9.05 | - | 3 | 2019-07-16 | 2020-07-31 | 25% | PT | - | 75% | 100% | - | Construction of hostels and improving accommodation facilities in the historical temple
[8 empty] | PP | - | - | - | -
|  | 5.74 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 9.05 | - | 3
5.74
Sub Project - 10. Proposed Multipurpose Religious Building for Kuruambe Dhaham Sevana Meditation Centre at Narampanawa
i | Completion of super structure and finishing work (plastering and painting) | 8.32 | 4.42 | 4.98 | 2019-07-16 | 2020-02-28 | 100% | PT | - | - | - | - | Construction of the religious building and improving facilities in the historical temple and handed over
[8 empty] | PP | - | - | - | -
|  | 9.4 |  |  |  |  | 47.02% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 8.32 | 4.42 | 4.98
9.4
Sub Project - 11. Design and Construction of Infrastructure Facilities for Sri Dalada Maligawa (Stage IV)
i | Finishing work (painting and lighting) | 31.42 | 16.2 | 5 | 2019-06-20 | 2020-02-28 | 100% | PT | - | - | - | - | Improving facilities for pilgrims at Sri Dalada Maligawa and handed over
[8 empty] | PP | - | - | - | -
|  | 31.42 |  |  |  |  | 51.56% | FT | - | 75% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 31.42 | 16.2 | 5
31.42
Sub Project - 12. Development of Bus Stand at Halloluwa (Stage II)
i | Completion of parking area | 12.14 | - | 6 | 2019-12-20 | 2020-07-31 | 50% | PT | - | 75% | 100% | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 12.14 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 12.14 | - | 6
12.14
Sub Project - 13. Development Bus Stand at Hasalaka
i | Finishing work (asphalting, plastering etc.) | 31.73 | 22 | 6.73 | 2018-12-24 | 2020-06-30 | 80% | PT | - | 100% | - | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 31.73 |  |  |  |  | 69.34% | FT | - | 70% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 31.73 | 22 | 6.73
31.73
Northern Province - 5 Projects
Mullativu District
Sub Project - 14. Infrastructure Development of Bus Stand at Mullativu (Stage III)
i | Electrical installation | 15 | 14.03 | - | 2019-07-23 | 2020-03-01 | 100% | PT | - | - | - | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 14.03 |  |  |  |  | 100% | FT | - | - | - | -
[8 empty] | FP | - | - | - | -
ii | Asphalting and road development | 12 | 0.97 | 6 | 28-Jan-20 | 2020-03-01 | 100% | PT | - | - | - | -
[8 empty] | PP | - | - | - | -
|  | 10 |  |  |  |  | 9.7% | FT | - | 40% | 75% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 27 | 15 | 6
24.03
Sub Project - 15. Construction of Two Storied Library Building for Kandawali School at Puthukudiyiruppu
i | Construction of super structure | 21.48 | - | 8 | 2019-10-14 | 2020-08-31 | 50% | PT | - | 90% | 100% | - | Construction of the library and providing facilities for school children
[8 empty] | PP | - | - | - | -
|  | 24.03 |  |  |  |  | - | FT | - | 90% | 100% | -
[8 empty] | FP | - |  | - | -
Total |  | 21.48 | - | 8
24.03
Sub Project - 16. Construction of Two Storied Classroom Building for Bharathi School at Puthukudiyiruppu
i | Construction of super structure | 22.95 | - | 5 | 2019-10-14 | 2020-07-31 | 40% | PT | - | 70% | 100% | - | Completion of the best quality classroom and providing facilities for school children
[8 empty] | PP | - | - | - | -
|  | 24.48 |  |  |  |  | - | FT | - | 20% | 50% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 22.95 | - | 5
24.48
Jaffna District
Sub Project - 17. Bus Stand Development at Jaffna (Stage II)
i | Asphalting and external lighting, gabion wall etc. | 95 | - | 10 | 2019-11-29 | 2020-07-31 | 40% | PT | - | 90% | 100% | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 87.87 |  |  |  |  | - | FT | - | 90% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 95 | - | 10
87.87
Mannar District
Sub Project - 18. Bus Stand Development at Mannar
i | Finishing work (plastering and asphalting) | 150 | 51.88 | 11 | 2020-07-07 | 2020-06-30 | 90% | PT | - | 100% | - | - | Construction of bus stand and providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 135.28 |  |  |  |  | 38.35% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 150 | 51.88 | 11
135.28

## 2
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
North Central Province - 7 Projects
Anuradhapura District
Sub Project - 19. Construction of Dana Shalawa of Mirisawetiya at Anuradhapura (Stage 1)
i | Finishing work (painting and floor finishing) | 4 | - | 1 | 2020-01-20 | 2020-06-30 | 75% | PT | - | 100% | - | - | Construction of the dana shalawa and improving facilities in the Miriswatiya Temple
[8 empty] | PP | - | - | - | -
|  | 4 |  |  |  |  | - | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
ii | Finishing of doors and windows | 2.6353 | 1.6 | 1 | 2020-01-20 | 2020-06-30 | 95% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 2.8 |  |  |  |  | 57.14% | FT | - | 92% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 6.6353 | 1.6 | 2
6.8
Sub Project - 20. Balance Work of Shrine Room of Lankaramaya Temple at Anuradhapura
i | Finishing of doors and windows | 1.6 | - | 1.7 | 2020-01-22 | 2020-05-30 | 75% | PT | - | 100% | - | - | Construction of shrine room and improving facilities in the Lankaramaya Temple
[8 empty] | PP | - | - | - | -
|  | 1.7 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Outdoor landfill work and landscaping | 3.24 | - | 3.2 | 22-Jan-20 | 2020-05-30 | 70% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 3.2 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 4.84 | - | 4.9
4.9
Sub Project - 21. Proposed Renovation of Vihara Mandiraya of Isurumuniya Temple at Anuradhapura
i | Finishing roof work | 3.2941 | - | 3.5 | 2020-01-20 | 2020-05-30 | 75% | PT | - | 100% | - | - | Renovation Vihara Mandiraya in the Isurumuniya Temple
[8 empty] | PP | - | - | - | -
|  | 3.5 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Finishing of columns | 3.3882 | - | 3.6 | 2020-01-20 | 2020-05-30 | 70% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 3.6 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 6.6824 | - | 7.1
7.1
Sub Project - 22. Proposed Facility Building at Srimaha Bodhi Premises
i | Plumbing | 0.94118 | 0.5 | 0.5 | 2020-01-18 | 2020-05-30 | 75% | PT | - | 100% | - | - | Improving facilities for pilgrims at the Srimaha Bodhiya
[8 empty] | PP | - | - | - | -
|  | 1 |  |  |  |  | 50% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Painting | 0.47059 | 0.4 | 0.1 | 2020-01-18 | 2020-05-30 | 70% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.5 |  |  |  |  | 80% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
iii | Interlocking | 0.47059 | - | 0.5 | 2020-01-18 | 2020-05-30 | 50% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.5 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 1.8824 | 0.9 | 1.1
2
Sub Project - 23. Construction of Sangavasaya of Tuparamaya at Anuradhapura
i | Final bill to be settled | 15.4165 | 11.96 | 4.42 | 2019-08-15 | 2020-02-15 | 100% | PT | - | - | - | - | Providing accommodation facilities for monks and handed over
[8 empty] | PP | - | - | - | -
|  | 16.38 |  |  |  |  | 73.02% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 15.4165 | 11.96 | 4.42
16.38
Sub Project - 24. Kumbichchankulama Wewa Recreational Area Development (Phase V) - Bridge No. 3
i | Concrete work of foundation, columns and beams) | 3.2 | 1 | 2.4 | 2019-10-12 | 2020-02-28 | 100% | PT | - |  | - | - | Providing good quality and safety recreational facilities for public
[8 empty] | PP | - | - | - | -
|  | 3.4 |  |  |  |  | 29.41% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Miscellaneous, curb and hand rails | 0.75294 | - | 0.8 | 2019-10-12 | 2020-05-30 | 50% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.8 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
iii | Steel work | 1.4118 | - | 1.5 | 2019-10-12 | 2020-05-30 | 95% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 1.5 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 5.3647 | 1 | 4.7
5.7
Polonnaruwa District
Sub Project - 25. Town Improvement Project at Welikanda
i | Structural work | 15.0588 | 1.73 | 7 | 2019-10-22 | 2020-06-30 | 50% | PT | - | 100% | - | - | Improving commercial building for public
[8 empty] | PP | - | - | - | -
|  | 16 |  |  |  |  | 10.81% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Electrical and plumbing work | 12.3294 | 8.1 | 3.2 | 2020-01-20 | 2020-06-30 | 50% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 13.1 |  |  |  |  | 61.83% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
iii | Finishing work (painting and tiling) | 0.94118 | - | - | 2020-02-20 | 2020-06-30 | 25% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 1 |  |  |  |  | - | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 28.3294 | 9.83 | 10.2
30.1
North Western Province - 3 Projects
Puttlam District
Sub Project - 26. Improvement of Eluwankulama - Aruwakkalu Road
i | Laying carpet on Eluwakkulama – Aruwakkaru Road up to “Y” Junction | 92.06 | 30.7 | 5 | 2019-11-09 | 2020-06-30 | 50% | PT | - | 100% | - | - | Providing a new road for Aruwakkaru Solid Waste Management Project and Aruakkaru village
[8 empty] | PP | - | - | - | -
|  | 92.06 |  |  |  |  | 33.35% | FT | - | 40% | 75% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 92.06 | 30.7 | 5
92.06

## 3
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
North Western Province - 3 Projects
Puttlam District
Sub Project - 27. Development of Beach Park at Chilaw
i | Preliminaries | 1.035 | 0.948 | - | 2019-10-21 | 2020-06-30 | 92% | PT | - | 100% | - | - | Improving recreational facilities for the public
[8 empty] | PP | - | - | - | -
|  | 1.035 |  |  |  |  | 91.59% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
ii | Demolition and site clearance | 0.594 | 0.345 | - | 2019-10-21 | 2020-06-30 | 96% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.594 |  |  |  |  | 58.08% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
iii | Earthwork | 1.032 | 0.04 | - | 2019-10-21 | 2020-06-30 | 40% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 1.032 |  |  |  |  | 3.876% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
iv | Filling work | 1.935 | - | - | 2019-10-21 | 2020-06-30 | 45% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 1.935 |  |  |  |  | - | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
v | Seating for edge of parking area | 2.923 | 0.691 | - | 2019-10-21 | 2020-06-30 | 40% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 2.923 |  |  |  |  | 23.64% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
vi | Construction of football goal | 0.4 | - | - | 2019-10-21 | 2020-06-30 | - | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.4 |  |  |  |  | - | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 7.919 | 2.024 | -
7.919

## 4
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
North Western Province
Kurunegala District
Sub Project - 28. Construction of Weekly Fair at Maho
i | Asphalt work surrounding the market | 16.9412 | 17.5 | - | 2018-10-02 | 2020-06-30 | 95% | PT | - | 100% | - | - | Construction of best quality market place for vendors and public
[8 empty] | PP | - | - | - | -
|  | 18 |  |  |  |  | 97.22% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
ii | Finishing sub structure and super structure | 89.4118 | 78.02 | 10 | 2018-10-03 | 2020-06-30 | 95% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 95 |  |  |  |  | 82.13% | FT | - | 92% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 106.3529 | 95.52 | 10
113

## 5
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Eastern Province - 1 Project
Batticaloa District
Sub Project - 29. Development of Private Bus Stand at Batticaloa
i | Final bill to be settled | 73.67 | 47.5 | 11.9 | 2018-Nov-17 | 2019-09-12 | 100% | PT | - | - | - | - | Providing parking facilities for busses and handed over to the Municipal Council
[8 empty] | PP | - | - | - | -
|  | 73.67 |  |  |  |  | 64.48% | FT | - | 80% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 73.67 | 47.5 | 11.9
73.67
Southern Province - 5 Projects
Hambanthota District
Sub Project - 30. Development of Walasmulla Pola
i | Construction of internal roads and drainage and balanced work of toilet blocks | 128 | 80.5 | 20 | 2018-01-01 | 2020-06-30 | 85% | PT | - | 100% | - | - | Development of pola, providing access and sanitary facilities for vendors and public
[8 empty] | PP | - | - | - | -
|  | 128 |  |  |  |  | 62.89% | FT | - | 93% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 128 | 80.5 | 20
128
Sub Project - 31. Wedasiti Kanda Entrance Development
i | Preliminaries | 0.1 | - | 0.1 | 2019-11-19 | 2020-03-01 | 100% | PT | - | - | - | - | Providing parking spaces to the pilgrims and improving appearance
[8 empty] | PP | - | - | - | -
|  | 0.1 |  |  |  |  | - | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Construction of car park, paving work and planting trees | 8.71 | 1.7 | 1 | 2019-11-19 | 2020-03-01 | 100% | PT | - |  | - | -
[8 empty] | PP | - | - | - | -
|  | 8.71 |  |  |  |  | 19.52% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 8.81 | 1.7 | 1.1
8.81
Galle District
Sub Project - 32. Baddegama Town Development (Bus Stand Development)
i | Preliminaries | 3.02 | 2.3 | - | 2018-04-19 | 2020-06-30 | 89% | PT | - | 100% | - | - | Providing parking facilities for busses
[8 empty] | PP | - | - | - | -
|  | 3.02 |  |  |  |  | 76.16% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
ii | Construction of toilet blocks | 4.31 | - | 1 | 2020-01-01 | 2020-06-30 | 10% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 4.31 |  |  |  |  | - | FT | - | 23% | 100% | -
[8 empty] | FP | - | - | - | -
iii | Construction of police post and driver's rest room | 2.34 | - | 1 | 2020-01-01 | 2020-06-30 | 10% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 2.34 |  |  |  |  | - | FT | - | 43% | 100% | -
[8 empty] | FP | - | - | - | -
iv | Construction of bus stand | 17.8 | 5 | 6 | 19-Apr-18 | 2020-06-30 | 32% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 17.8 |  |  |  |  | 28.09% | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
v | Landscaping | 15.6 | - | 1.06 | 29-Feb-20 | 2020-06-30 | 10% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 15.6 |  |  |  |  | - | FT | - | 30% | 100% | -
[8 empty] | FP | - | - | - | -
vi | Demolishing of existing toilet | 0.12 | 0.06 | - | 2018-04-19 | 2020-06-30 | 60% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 0.12 |  |  |  |  | 50% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
vii | Provincial sum for plumbing and drainage work | 2 | - | 1 | 2020-01-03 | 2020-06-30 | 10% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 2 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
viii | Approved variation for bus stand | 9.6 | 2 | 1 | 2018-12-01 | 2020-06-30 | 34% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 9.6 |  |  |  |  | 20.83% | FT | - | 31% | 100% | -
[8 empty] | FP |  | - | - | -
Total |  | 54.79 | 9.36 | 11.06
54.79
Sub Project - 33. Construction of Proposed Public Market and Playground at Ahungalla
i | Paving work, improvement of playground and installation of gate | 59 | 45 | 14 | 2018-05-28 | 2020-05-30 | 97% | PT | - | 100% | - | - | Facilitating vendors and public and providing recreational facilities for public
[8 empty] | PP | - | - | - | -
|  | 59 |  |  |  |  | 76.27% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 59 | 45 | 14
59
Monaragala District
Sub Project - 34. Development of Wellawaya Pola
i | Balance work of preliminaries | 1.76 | 1.5 | 1 | 2019-03-11 | 2020-06-30 | 90% | PT | - | 100% | - | - | Construction of pola building and facilitating the vendors and public
[8 empty] | PP | - | - | - | -
|  | 1.76 |  |  |  |  | 85.23% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Construction of sub structure | 23.43 | 19.14 | 2 | 2019-04-01 | 2020-05-30 | 80% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 23.43 |  |  |  |  | 81.69% | FT | - | 70% | 100% | -
[8 empty] | FP | - | - | - | -
iii | Construction of super structure | 34.87 | 25.72 | 4 | 2019-06-04 | 2020-06-30 | 50% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 34.87 |  |  |  |  | 73.76% | FT | - | 45% | 100% | -
[8 empty] | FP | - | - | - | -
iv | Electrical work | 2.09 | - | 1.45 | 2020-03-01 | 2020-06-30 | 40% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 2.09 |  |  |  |  | - | FT | - | 60% | 100% | -
[8 empty] | FP | - | - | - | -
v | Removing garbage pit and construction of zinc and aluminum sheet fence | 7.36 | 6.3 | - | 2019-05-07 | 2020-06-30 | 90% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 7.36 |  |  |  |  | 85.6% | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
vi | Lighting and painting | 7.36 | - | 1.06 | 2020-03-01 | 2020-09-30 | - | PT | - | 50% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 7.36 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 76.87 | 52.66 | 9.51
76.87

## 6
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Colombo District
Sub Project - 35. Construction of Piliyandala By-pass Road (Stage 1)
i | Finishing work (ABC overlaying, asphalt overlaying, retaining wall) of road (60m-1,000m) | 143.66 | 65.41 | 20 | 2017-08-30 | 2020-02-29 | 100% | PT | - | - | - | - | Easing traffic congestion through Piliyandala town and not yet hand over
[8 empty] | PP | - | - | - | -
|  | 143.66 |  |  |  |  | 45.53% | FT | - | 60% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 143.66 | 65.41 | 20
143.66
Sub Project - 36. Piliyandala By-pass Road (Stage II)
i | Finishing work (ABC overlaying and asphalt overlaying) of road (0-60m) | 55.814 | 19.56 | 10 | 2018-08-03 | 2020-02-29 | 100% | PT | - | - | - | - | Easing traffic congestion through Piliyandala town and not yet hand over
[8 empty] | PP | - | - | - | -
|  | 55.814 |  |  |  |  | 35.04% | FT | - | 53% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 55.81 | 19.56 | 10
55.814
Sub Project - 37. Construction of Kottawa Thalagala Road (Stage I)
i | Finishing work (ABC overlaying and asphalt overlaying) of road | 224 | 165.45 | 15 | 2017-07-10 | 2020-06-29 | 90% | PT | - | 100% | - | - | Easing traffic congestion
[8 empty] | PP | - | - |  | -
|  | 224 |  |  |  |  | 73.86% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 224 | 165.45 | 15
224
Sub Project - 38. Construction of Kottawa Thalagala Road (Stage II)
1 | Finishers work of road construction (ABC overlaying, asphalt overlaying) | 198.99 | 48.24 | 50 | 2018-11-22 | 2020-06-29 | 80% | PT | - | 100% | - | - | Easing traffic congestion
[8 empty] | PP | - | - | - | -
|  | 198.99 |  |  |  |  | 24.24% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 198.99 | 48.24 | 50
198.99
Sub Project - 39. Construction of Kirimandala Mawatha (CMC Road)
i | Construction of road | 400 | 25 | 30 | 2019-01-25 | 2020-12-31 | 35% | PT | - | 70% | 80% | 100% | Easing traffic congestion
[8 empty] | PP | - | - | - | -
|  | 200 |  |  |  |  | 12.5% | FT | - | 70% | 80% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 400 | 25 | 30
200
Sub Project - 40. Moratuwa Town Development (Weerapuran Appu Park)
i | Landscaping (paving and tree planting) | 29 | 34 | 0 | 2019-12-20 | 2020-03-01 | 100% | PT | - | - | - | - | Providing the recreational facilities for public and not yet hand over
[8 empty] | PP | - | - | - | -
|  | 34 |  |  |  |  | 100% | FT | - | - | - | -
[8 empty] | FP | - | - | - | -
ii | Finishing work (painting and tiling) | 40 | 41 | 0.5 | 2019-12-05 | 2020-03-01 | 100% | PT | - | - | - | -
[8 empty] | PP | - | - | - | -
|  | 41.5 |  |  |  |  | 98.8% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 69 | 75 | 0.5
75.5
Sub Project - 41. Construction of Internal Roads at Techno City at Homagama
i | Finishing work (turfing and retaining wall) of road | 242 | 135.7 | 10 | 2017-08-03 | 2020-06-30 | 95% | PT | - | 100% | - | - | Easing traffic congestion
[8 empty] | PP | - | - | - | -
|  | 242 |  |  |  |  | 56.07% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 242 | 135.7 | 10
242
Sub Project - 42. Construction of Multi Purpose Building at Boralesgamuwa
i | Construction of pilling | 67 | 15 | 4.81 | 2019-12-27 | 2020-08-27 | 18% | PT |  | 70% | 100% | - | Providing commercial facilities for public
[8 empty] | PP | - | - | - | -
|  | 67 |  |  |  |  | 22.39% | FT |  | 70% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 67 | 15 | 4.81
67

## 7.
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Colombo District
Sub Project - 43. Children's Orphanage at Aththidiya (Stage I)
i | Final bill to be settled | 73 | 52.67 | 2.28 | 2018-05-22 | 2019-12-05 | 100% | PT |  | - | - | - | Providing accommodation for misplaced children and not yet hand over
[8 empty] | PP | - | - | - | -
|  | 54.95 |  |  |  |  | 95.85% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 73 | 52.67 | 2.28
54.95
Sub Project - 44. Children's Orphanage at Aththidiya (Stage II)
i | Preliminaries, excavation and earth work | 6.6 | - | 3.96 | 2020-01-14 | 2020-08-18 | 80% | PT | - | 90% | 100% | - | Providing accommodation for misplaced children
[8 empty] | PP | - | - | - | -
|  | 6.96 |  |  |  |  | - | FT | - | 90% | 100% | -
[8 empty] | FP | - | - | - | -
ii | Concrete work of building | 6.7 | - | 3 | 2020-01-14 | 2020-08-13 | 10% | PT | - | 50% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 5.97 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
iii | Masonry work and water proofing | 3.82 | - | 2.5 | 2020-03-23 | 2020-08-13 | - | PT | - | 30% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 4.13 |  |  |  |  | - | FT | - | 30% | 100% | -
[8 empty] | FP | - | - | - | -
iv | Metal and wood work | 6.29 | - | 1.25 | 2020-05-29 | 2020-08-13 | - | PT | - | 70% | 100% | -
[8 empty] | PP | - |  | - | -
|  | 3.79 |  |  |  |  | - | FT | - | 70% | 100% | -
[8 empty] | FP | - |  | - | -
vi | Roof and ceiling | 3.04 | - | 1.25 | 2020-04-25 | 2020-08-05 | - | PT | - | 70% | 100% | -
[8 empty] | PP | - |  | - | -
|  | 2.15 |  |  |  |  | - | FT | - | 70% | 100% | -
[8 empty] | FP | - |  | - | -
vi | Electrical, plumbing and drainage work | 3.01 | - | 1 | 2020-03-07 | 2020-07-09 | - | PT | - | 60% | 100% | -
[8 empty] | PP | - |  | - | -
|  | 2.81 |  |  |  |  | - | FT | - | 60% | 100% | -
[8 empty] | FP | - |  | - | -
vii | Finishing (plastering and painting) and external work | 8.56 | - | 2 | 2020-03-31 | 2020-08-15 | - | PT | - | 60% | 100% | -
[8 empty] | PP | - |  | - | -
|  | 6.77 |  |  |  |  | - | FT | - | 60% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 38.02 | - | 14.96
32.58

## 8
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Colombo District
Sub Project - 45. Construction of New Market at Katubedda
i | Excavation and earthwork | 4.4 | 4 | 0 | 2019-10-25 | 2020-05-17 | 65% | PT | - | 100% | - | - | Construction of market building and facilitating the vendors and public
[8 empty] | PP | - | - | - | -
|  | 4.4 |  |  |  |  | 90.91% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Concrete work | 73.59 | 3 | 2 | 2019-11-05 | 2020-07-28 | 7% | PT | - | 30% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 73.59 |  |  |  |  | 4.077% | FT | - | 30% | 50% | 100%
[8 empty] | FP | - | - | - | -
iii | Masonry work | 5.69 | 0.2303 | 2.4 | 2019-11-07 | 2020-07-29 | 5% | PT | - | 25% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 5.69 |  |  |  |  | 4.048% | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
iv | Water proofing | 3.49 | 0 | 1 | 2020-01-28 | 2020-07-15 | - | PT | - | 30% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 3.49 |  |  |  |  | - | FT | - | 30% | 100% | -
[8 empty] | FP | - | - | - | -
v | Structural metal work for steel | 3.76 | 0 | 1 | 2020-06-05 | 2020-08-27 | - | PT | - | - | 100% | -
[8 empty] | PP | - | - | - | -
|  | 3.76 |  |  |  |  | - | FT | - | - | 25% | 100%
[8 empty] | FP | - | - | - | -
vi | Metal work | 5.11 | 0 | 0.65965 | 2020-04-02 | 2020-08-27 | - | PT | - | - | 100%
[8 empty] | PP | - | - | - | -
|  | 5.11 |  |  |  |  | - | FT | - | - | 25% | 100%
[8 empty] | FP | - | - | - | -
vii | Claddings | 2.34 | 0 | 0.3013 | 2020-05-10 | 2020-07-15 | - | PT |  | 25% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 2.34 |  |  |  |  | - | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
viii | Partitions/suspended ceiling | 6.56 | 0 | 0.84649 | 2020-05-10 | 2020-09-15 | - | PT | - | 25% | 100% | - | Construction of market building and facilitating the vendors and public
[8 empty] | PP | - | - | - | -
|  | 6.56 |  |  |  |  | - | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
ix | Roof covering/ roof plumbing | 4.55 | 0 | 0.58772 | 2020-06-21 | 2020-09-30 | - | PT | - | 50% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 4.55 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
x | Plumbing/ sanitary installation | 1.32 | 0 | 0.17027 | 2020-03-18 | 2020-09-01 | - | PT | - | 50% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 1.32 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
xi | Electrical installation | 5.92 | 0 | 0.76425 | 2020-05-13 | 2020-09-15 | - | PT | - | 40% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 5.92 |  |  |  |  | - | FT | - | 40% | 100% | -
[8 empty] | FP | - | - | - | -
xii | Floor, wall and ceiling finishing | 13.54 | 0 | 1.7471 | 2020-02-10 | 2020-09-15 | - | PT | - | 60% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 13.54 |  |  |  |  | - | FT | - | 60% | 100% | -
[8 empty] | FP | - | - | - | -
xiii | Painting | 3.01 | 0 | 0.38805 | 2020-05-07 | 2020-07-15 | - | PT | - | 30% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 3.01 |  |  |  |  | - | FT | - | 30% | 100% | -
[8 empty] | FP | - | - | - | -
xiii | Drainage system | 1.16 | 0 | - | 2020-05-12 | 2020-10-06 | - | PT | - | 30% | 75% | 100%
[8 empty] | PP | - | - | - | -
|  | 1.16 |  |  |  |  | - | FT | - | 30% | 75% | 100%
[8 empty] | FP | - | - | - | -
xiv | Landscaping | 0.85 | 0 | - | 2020-08-13 | 2020-08-26 | - | PT |  |  | 100% | -
[8 empty] | PP | - | - | - | -
|  | 0.85 |  |  |  |  | - | FT | - | - | 100% | -
[8 empty] | FP | - | - | - | -
xvi | Provisional sums for ground improvement, name boards, specific preliminary work, repairing road damages, sewer/ waste disposal | 21.6 | 0 | - | 2020-05-10 | 2020-07-26 | - | PT | - | 50% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 21.6 |  |  |  |  | - | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
xvi | Preliminaries | 9.38 | 5.1783 | - | 2019-07-15 | 2020-09-15 | 50% | PT | - | 70% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 9.38 |  |  |  |  | 55.21% | FT | - | 70% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 166.27 | 12.4086 | 11.8648
166.27
Sub Project - 46. Pola Development at Wellampitiya
i | Final bill to be settled | 115 | 62 | 10 | 2018-03-31 | 2020-01-30 | 100% | PT | - | - | - | - | Construction of pola building and facilitating the vendors and public and not yet handed over
[8 empty] | PP | - | - | - | -
|  | 115 |  |  |  |  | 53.91% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 115 | 62 | 10
115

## 9.
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Colombo District
Sub Project - 47. Construction of Real Time Flood Mitigation Center at Kirimandala Mawatha
i | Preliminaries | 52.42 | 35 | 2 | 2019-12-20 | 2020-06-30 | 54% | PT | - | 100% | - | - | * Developing an integrated flood control and water management information system * Providing Early Warning support on flood for the Metro Colombo * Developing optimal operational rules for the flood control facilities * Assessing current and evolving future water related risks and develop response strategies
[8 empty] | PP | - | - | - | -
|  | 52.42 |  |  |  |  | 66.77% | FT | - | 75% | 100% | -
[8 empty] | FP | - | - | - | -
ii | Building work | 362.82 | 154 | 2 | 2018-03-20 | 2020-06-30 | 47% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 362.82 |  |  |  |  | 42.45% | FT | - | 50% | 100% | -
[8 empty] | FP | - | - | - | -
iii | Electrical installation | 59.28 | 2.4 | 1 | 2018-03-20 | 2020-06-30 | 6% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 59.28 |  |  |  |  | 4.049% | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
iv | Water supply and drainage | 44.98 | 1.74 | 1 | 2019-01-12 | 2020-06-30 | 5% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 44.98 |  |  |  |  | 3.868% | FT | - | 25% | 50% | 100%
[8 empty] | FP | - | - | - | -
v | Mechanical installation | 208.29 | - | 1 | 2020-01-01 | 2020-12-31 | - | PT | - | 40% | 80% | 100%
[8 empty] | PP | - | - | - | -
|  | 208.29 |  |  |  |  | - | FT | - | 40% | 80% | 100%
[8 empty] | FP | - | - | - | -
vi | Landscaping and substation work | 8.58 | - | 0.5 | 2020-01-03 | 2020-12-31 | - | PT | - | 40% | 80% | 100%
[8 empty] | PP | - | - | - | -
|  | 8.58 |  |  |  |  | - | FT | - | 40% | 80% | 100%
[8 empty] | FP | - | - | - | -
vii | Roof work | 15.67 | 5.45 | 0.5 | 2019-01-09 | 2020-06-30 | 70% | PT | - | 100% | - | -
[8 empty] | PP | - | - | - | -
|  | 15.67 |  |  |  |  | 34.78% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 752.04 | 198.59 | 8
752.04

## 10.
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Colombo District
Sub Project - 48. Belek Kade Pola Development at Ratmalana
i | Construction of super structure | 70 | 30 | 15 | 2018-10-10 | 2020-07-31 | 50% | PT | - | 75% | 100% | - | Construction of pola building and facilitating the vendors and public
[8 empty] | PP | - | - | - | -
|  | 70 |  |  |  |  | 42.86% | FT | - | 75% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 70 | 30 | 15
70
Western Province - 19 Projects
Kalutara District
Sub Project - 49. Development of Bus Stand (Link Existing Railway Station) at Aluthgama
i | Preliminaries | 3.92 | 2.98 | 0.42 | 2018-10-14 | 2020-02-28 | 100% | PT | - | - | - | - | Providing parking facilities for busses and easy access between bus stand and railway station for public
[8 empty] | PP | - | - | - | -
|  | 3.4 |  |  |  |  | 87.65% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
ii | Building work | 27.47 | 10.61 | 5 | 2018-10-14 | 2020-12-31 | 55% | PT | - | 65% | 85% | 100%
[8 empty] | PP | - | - | - | -
|  | 30.42 |  |  |  |  | 34.88% | FT | - | 60% | 75% | 100%
[8 empty] | FP | - | - | - | -
iii | External work (additional bus parking spaces and drainage system) | 12.05 | - | 3 | 2020-01-31 | 2020-12-31 | - | PT | - | 15% | 60% | 100%
[8 empty] | PP | - | - | - | -
|  | 10.96 |  |  |  |  | - | FT | - | 15% | 60% | 100%
[8 empty] | FP | - | - | - | -
iv | Renovation work | 1.96 | - | 1 | 2020-01-02 | 2020-12-31 | - | PT | - | 15% | 60% | 100%
[8 empty] | PP | - | - | - | -
|  | 1.65 |  |  |  |  | - | FT | - | 15% | 60% | 100%
[8 empty] | FP | - | - | - | -
v | Provisional sum for ground improvement, name boards, repairing road damages, sewer/ waste disposal | 4.15 | 0.062 | 1.65 | 2019-11-12 | 2020-12-31 | 1% | PT | - | 20% | 60% | 100%
[8 empty] | PP | - | - | - | -
|  | 4.15 |  |  |  |  | 1.494% | FT | - | 20% | 60% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 49.55 | 13.652 | 11.07
50.58

## 11
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Kalutara District
Sub Project - 50. Development of Pola Area at Horana (Phase II)
i | Final bills to settled | 105 | 88.8 | 16.2 | 2018-09-04 | 2020-03-01 | 100% | PT | - | - | - | - | Development of pola and facilitating the vendors and public and not yet hand over
[8 empty] | PP | - | - | - | -
|  | 105 |  |  |  |  | 84.57% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 105 | 88.8 | 16.2
105

## 12
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Gampaha District
Sub Project - 51. Construction of Kithudana Pubuduwa National Center at Walpola, Ragama (Stage II)
i | Final bill to be settled | 21.91 | 10.04 | 10.01 | 2018-08-09 | 2020-05-31 | 85% | PT | - | 100% | - | - | Development of social infrastructure
[8 empty] | PP | - | - | - | -
|  | 20.05 |  |  |  |  | 50.07% | FT | - | 100% | - | -
[8 empty] | FP | - | - | - | -
Total |  | 21.91 | 10.04 | 10.01
20.05

## 13
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Gampaha District
Sub Project - 52. Public Market at Minuwangoda
i | Construction of super structure | 96 | 49 | 19 | 2018-09-25 | 2020-07-31 | 58% | PT | - | 70% | 100% | - | Construction of market building and facilitating vendors and public
[8 empty] | PP | - | - | - | -
|  | 96 |  |  |  |  | 51.04% | FT | - | 70% | 100% | -
[8 empty] | FP | - | - | - | -
ii | Consultancy work for the proposed building | 67 | 40 | 16 | 2018-05-01 | 2020-07-31 | 75% | PT | - | 80% | 100% | -
[8 empty] | PP | - | - | - | -
|  | 67 |  |  |  |  | 59.7% | FT | - | 75% | 100% | -
[8 empty] | FP | - | - | - | -
Total |  | 163 | 89 | 35
163

## 14
Activity Plan - 2020
Ministry of Urban Development, Water Supply and Housing Facilities
Name of the Project: Town Development Projects in Nine Provinces
# | Sub Activities | Total Estimated Cost (Rs.Mn) | Cumulative Expenditure up to 05.03.2020 (Rs.Mn) | Allocation for 2020 (Rs.Mn) As per the 2nd Vote on Account | Commencement Date | Expected End Date | Cumulative Physical and Financial Progress up to 05.03.2020 (%) | PT/ FT | Milestone - Cumulated (2020) |  |  |  | Expected Benefits/ Results
|  | Contract Sum (Rs.Mn) | [6 empty] | 1st Q | 2nd Q | 3rd Q | 4th Q
Western Province - 19 Projects
Gampaha District
Sub Project - 53. Drainage Design and Improvements at Wetland Park, Gampaha (Stage II)
i | Construction hold as per the request of the Gampaha Municipal Council | 150 | 51.68 | 9.33 | 2018-08-30 | 2020-06-30 | 70% | PT | - | 100% | - | - | Providing recreational facilities for public
[8 empty] | PP | - | - | - | -
|  | 150 |  |  |  |  | 34.45% | FT | - | 55% | 75% | 100%
[8 empty] | FP | - | - | - | -
Total |  | 150 | 51.68 | 9.33
150
Grant Total |  | 4665.69 | 1809.35 | 600
4384.79