## UDA - Siyak Nagara
Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programmes as at 30th June, 2022
Province | SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets | DPMM Comments
[10 empty] | Allocation 2022 Rs.Mn | Financial targets and progress- 2022 ( as at 30.06.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [6 empty] | Cumulative physical target as at 30.06.2022 (%) | Cumulative Physical Progress (as at 30.06.2022)
[11 empty] | Expenditure Target | Imprest Requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  |  | Original | Current (if revised during implementation) | Date of Commencement | Date of Completion | Revised (if extended) | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%) ( Revised) ( B) |  |  |  | Description | as % of (B) |  | Description | as % of overall Progress (% of A)
[20 empty] | Q-1 | Q-2 | Q-3 | Q-4
|  | -1 | -2 | -3 |  | -4 |  |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | (22) | -23 | -24 | -25
| 1 | Infrastructure facilities for Sri Dalada Maligawa | Kandy | 8259 | - | 2022-01-03 | 2022-12-01 |  | GoSL | 2670.95 | 1879.53 | 1869.82 | 1532.82 | 1532.82 | 337 | 1532.82 | Providing improved main access road including lighting | 0 | Improvement of main access road of the Sri Dalada Maligawa | 30 | 60 | 90 | 100 | fairface Rubble work is in progress. | 66.6667 | 60 | fairface Rubble work is in progress. | 40 | Due to unavailability of material and fuel at the market.
| 2 | Mahamaluwa development project at Dalada Maligawa (stage II) |  |  | - | 2021-12-29 | 2022-04-29 | [9 empty] | Improving appearance | 5 | Construction of face lifting | 70 | 95 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 3 | Hasalaka bus stand (stage II) | Hasalaka |  | - | 2021-05-11 | 2022-01-11 | [9 empty] | Improving appearance | 99 | Construction of face lifting | 1 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 4 | Kadugannawa face lifting | Kadugannawa |  | - | 2021-05-13 | 2022-08-02 | [9 empty] | Improving appearance | 52 | Construction of face lifting | 18 | 33 | 48 | - | Stage I - Completed. Stage II - Brick work completed and plastering are in progress. Stage III - Concreting work is in progress. | 87.8788 | 85 | Stage I - Completed. Stage II - Brick work completed and plastering are in progress. Stage III - Concreting work is in progress. | 81 | Due to unavailability of material and fuel at the market.
| 5 | Construction of office building for the Department of Railways at Gampola (relocation CGR building at Gampola) | Gampola |  | - | 2021-05-11 | 2022-02-11 | [9 empty] | Completion of town development | 68 | Relocation of CGR building | 32 | 32 | - | - | Finishing work in progress. | 84.375 | 100 | Finishing work in progress. | 95 | Due to unavailability of material and fuel at the market.
| 6 | Construction of by-pass road parallel to railway line at Gampola (connecting by-pass road at Gampola) |  |  | - | 2021-05-11 | 2022-08-11 | [9 empty] | Reducing traffic congestion | 23 | Construction of by-pass road | 27 | 57 | 77 | - | Construction has been suspended due to increase in prices of Building materials in the Market. It was decided to construct a drainage and cover slab in addition to the existing work. After the above completion work it was decided to suspended the construction. | 38.5965 | 80 | Construction has been suspended due to increase in prices of Building materials in the Market. It was decided to construct a drainage and cover slab in addition to the existing work. After the above completion work it was decided to suspended the construction. | 45 | Due to unavailability of material and fuel at the market.
| 7 | Development of walkway track at Gurudeniya | Gurudeniya |  | - | 2021-08-02 | 2022-01-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 95 | Construction of jogging trac | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 8 | Street sideway development project at Kings Street, Kandy | Kandy |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 75 | Landscape development | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 9 | Street sideway development project at Digana | Digana |  | - | 2021-08-16 | 2021-12-31 | [9 empty] | City beatification | 100 | Landscape development | - | - | - | - | Completed | 100 | - | Completed | 100 | -
| 10 | Street sideway development at Wattegama | Wattegama |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 70 | Landscape development | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 11 | Street sideway development at Pupuressa | Pupuressa |  | - | 2021-10-07 | 2022-04-08 | [9 empty] | City beatification | 40 | Landscape development | 40 | 60 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 12 | Street Sideway Development at Muruthalawa | Muruthalawa |  | - | 2021-10-07 | 2022-04-08 | [9 empty] | City beatification | 32 | Landscape development | 48 | 68 | - | - | Fance work and drain work are in progress. Interlock paving work is in progress. | 89.7059 | 100 | Fance work and drain work are in progress. Interlock paving work is in progress. | 93 | Due to unavailability of material and fuel at the market.
| 13 | Street sideway development at Theldeniya | Theldeniya |  | - | 2021-10-07 | 2022-04-08 |  | -13: City beatification; -14: 60; -15: Landscape development; Q-1 -16: 30; Q-2 -17: 40; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Work nearly completion.; Q-4 -21: 97.5; Q-4 (22): 100; Q-4 -23: Work almost completed; Q-4 -24: 99
| 14 | Street sideway development at Nawalapitiya | Nawalapitiya |  | - | 2021-09-21 | 2022-03-09 | [9 empty] | City beatification | 80 | Landscape development | 20 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 15 | Design and construction of infrastructure facilities at railway station at Hatton (stage V) | Hatton |  |  | 2020-12-17 | 2022-02-27 |  | -13: Providing better transport system for Sri Pada pilgrims and others; -14: 45; -15: Completion of railway station; Q-1 -16: 55; Q-2 -17: -; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: 100; Q-4 (22): 100; Q-4 -23: Completed; Q-4 -24: 100
| 16 | Nuwara Eliya central market (stage II) | Nuwara Eliya |  | - | 2021-04-07 | 2022-06-30 | [9 empty] | Relocation of vendors and traders | 45 | Construction of market building | 25 | 55 | - | - | Work in is progress. | 58.1818 | 100 | Work in is progress. | 77 | Material shortage and price fluctuation.
| 17 | Wetland development project at Kotagala (stage II) | Kotagala |  | - | 2021-04-19 | 2022-04-15 | [9 empty] | Town development | 55 | Improvement of public facilities | 25 | 45 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 18 | Town development at Walapane (stage I) | Walapane |  | - | 2021-09-01 | 2022-07-01 | [9 empty] | Town development | 23 | Improvement of public facilities | 27 | 74 | 77 | - | Preperation of outdoor parking area. (ABC compaction) | 37.8378 | 97 | Preperation of outdoor parking area. (ABC compaction) | 51 | Due to unavailability of material and fuel at the market.
| 19 | Nature corridor development along Nanu Oya stream at Nuwara Eliya | Nuwara Eliya |  | - | 2021-08-20 | 2022-08-30 | [9 empty] | Improvement of Nanu Oya stream | 18 | Landscaping | 22 | 52 | 82 | - | Work in is progress. | 71.1538 | 70 | Work in is progress. | 55 | Reduced the scope.
| 20 | Development of bus stand at Pudalu Oya (phase I) | Pudalu Oya |  | - | 2021-07-28 | 2022-07-01 | [9 empty] | Providing transport facilities | 60 | Construction of bus stand | 20 | 38 | 40 | - | Completed | 105.2632 | 98 | Completed | 100 | -
| 21 | Development of walkway track at Lake Gregory, Nuwara Eliya | Nuwara Eliya |  | - | 2021-08-26 | 2022-03-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 35 | Construction of jogging track | 65 | 65 | - | - | Gabion wall construction | 72.3077 | 100 | Gabion wall construction | 82 | Reduced the scope.
| 22 | City development project at Ginigathhena | Ginigathhena |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 62 | Construction of landscape development | 38 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 23 | Landscaping and city beautification project at Thalawakele | Thalawakele |  | - | 2021-10-25 | 2022-04-18 | [9 empty] | City beatification | 35 | Construction of landscape development | 55 | 65 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 24 | Town improvement project at Ragala | Ragala |  | - | 2021-09-17 | 2022-05-19 | [9 empty] | City beatification | 38 | Construction of landscape development | 37 | 62 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 25 | City development project at Rikillagaskada | Rikillagaskada |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 48 | Construction of landscape development | 62 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 26 | Jogging track at V.T. Nanayakkara Park at Matale (phase I) | Matale |  | - | 2021-02-11 | 2022-03-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 75 | Construction of jogging track | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 27 | City beautification project at Matale |  |  | - | 2021-10-07 | 2021-04-08 | [9 empty] | City beatification | 60 | Construction of landscape development | 30 | 40 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 28 | Town development project at Inamaluwa | Inamaluwa |  | - | 2021-10-25 | 2021-04-26 | [9 empty] | City beatification | 70 | Construction of landscape development | 25 | 30 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 29 | Pallepola town development | Pallepola |  | - | 2021-10-25 | 2021-04-26 | [9 empty] | City beatification | 65 | Construction of landscape development | 30 | 35 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 30 | Ukuwela town development | Ukuwela |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 31 | Naula town development | Naula |  | - | 2021-10-25 | 2021-04-26 | [9 empty] | City beatification | 50 | Construction of landscape development | 40 | 50 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 32 | Development of walkway track at Orr's Hill Road, Trincomalee (phase I) | Trincomalee |  | - | 2021-09-01 | 2022-02-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 75 | Construction of jogging track | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 33 | Kantale Wewa surrounding development projects | Kantale |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 30 | Construction of landscape development | 70 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 34 | Muthur junction beautification | Muthur |  | - | 2021-08-20 | 2022-02-17 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | 40 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 35 | Development of walkway track at Batticaloa (phase I) | Batticaloa |  | - | 2021-08-09 | 2022-05-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 40 | Construction of jogging track | 35 | 60 | - | - | To be handed over to the PS | 50 | 100 | To be handed over to the PS | 70 | Non availability of material and fuel.
| 36 | Construction of pedestrian pathway at Vantharumoolai | Vantharumoolai |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 37 | Construction of pedestrian pathway at Urani | Urani |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 75 | Construction of landscape development | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 38 | Construction of beach park at Nintavur (phase I) | Nintavur |  | - | 2021-07-15 | 2022-07-15 | [9 empty] | Sustained tourism development and small scale economic development | 60 | Completion of beach park | 15 | 35 | 40 | - | Temporary suspend work | 91.4286 | 95 | Temporary suspend work | 92 | Temporary suspend work
| 39 | Bicycle and walkway track development at Ampara (phase I) | Ampara |  | - | 2021-08-09 | 2022-02-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 75 | Construction of jogging track | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 40 | Mahaoya town area and hot well area beautification | Mahaoya |  | - | 2021-08-23 | 2022-02-17 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | 30 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 41 | Hingurana town center beautification | Hingurana |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 93 | Construction of landscape development | 7 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 42 | Dehiattakandiya town center beautification | Dehiattakandiya |  | - | 2021-08-20 | 2022-02-17 | [9 empty] | City beatification | 45 | Construction of landscape development | 55 | 55 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 43 | Kalmunai public bus stand area beautification | Kalmunai |  | - | 2021-08-20 | 2022-02-17 | [9 empty] | City beatification | 65 | Construction of landscape development | 35 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 44 | Balance work of Kilinochchi bus stand (stage II) | Kilinochchi |  | - | 2021-07-13 | 2022-03-10 | [9 empty] | Providing transport facilities | 60 | Completion of bus stand | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 45 | Kilinochchi town improvement project |  |  | - | 2021-09-21 | 2022-02-22 | [9 empty] | City beatification | 45 | Construction of landscape development | 55 | 55 | - | - | Cannel work completed. Retaining wall completed. Gravel laying work completed. Benches work 80% completed. Shoe drain completed | 9.0909 | 100 | Cannel work completed. Retaining wall completed. Gravel laying work completed. Benches work 80% completed. Shoe drain completed | 50 | Due to unavailability of material and fuel at the market.
| 46 | Pooneriyan town improvement project | Pooneriyan |  | - | 2021-11-11 | 2022-05-22 | [9 empty] | City beatification | 20 | Construction of landscape development | 55 | 80 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 47 | Mannar town improvement project | Mannar |  | - | 2021-10-07 | 2022-04-08 | [9 empty] | City beatification | 60 | Construction of landscape development | 30 | 40 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 48 | Vavuniya landscaping project | Vavuniya |  | - | 2021-08-13 | 2022-02-14 | [9 empty] | City beatification | 48 | Construction of landscape development | 52 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 49 | Parking development at Hospital Road at Jaffna (stage II) | Jaffna |  | - | 2021-07-13 | 2022-03-25 | [9 empty] | Providing parking facilities | 50 | Completion of car parking | 50 | 50 | - | - | Bridge completed. Filling completed. Security hut roof completed. Culvert area mass concrete work is in progress Gravel spreading in parking area ABC pilled in site premises | 60 | 100 | Bridge completed. Filling completed. Security hut roof completed. Culvert area mass concrete work is in progress Gravel spreading in parking area ABC pilled in site premises | 80 | Due to unavailability of material and fuel at the market.
| 50 | Green infrastructure development along “Vallaivelie” jogging track at Point Pedro | Point Pedro |  | - | 2021-09-01 | 2022-08-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 6 | Construction of jogging track | 36 | 66 | 94 | - | Project terminated. | 6.0606 | 72 | Project terminated. | 10 | Project terminated.
| 51 | Development of walkway track at Point Pedro (stage I) |  |  | - | 2021-09-02 | 2022-06-30 |  | -14: 7; -15: Construction of jogging track; Q-1 -16: 43; Q-2 -17: 93; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Project terminated.; Q-4 -21: 6.4516; Q-4 (22): 100; Q-4 -23: Project terminated.; Q-4 -24: 13; Q-4 -25: Project terminated.
| 52 | Maruthanarmadam town improvement project | Maruthanarmadam |  | - | 2021-08-13 | 2022-04-14 | [9 empty] | City beatification | 17 | Construction of landscape development | 58 | 83 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 53 | Velanai town improvement project | Velanai |  | - | 2021-08-13 | 2022-02-14 | [9 empty] | City beatification | 68 | Construction of landscape development | 32 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 54 | Kodikamam town improvement project | Kodikamam |  | - | 2021-08-19 | 2022-02-15 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 55 | Navatkuli town improvement project | Navatkuli |  | - | 2021-09-21 | 2022-03-16 | [9 empty] | City beatification | 42 | Construction of landscape development | 58 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 56 | Chavakachcheri town improvement project | Chavakachcheri |  | - | 2021-10-28 | 2022-04-17 | [9 empty] | City beatification | 8 | Construction of landscape development | 67 | 92 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 57 | Welioya town improvement project | Welioya |  | - | 2021-11-10 | 2022-05-17 | [9 empty] | City beatification | 52 | Construction of landscape development | 28 | 48 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 58 | Layout for Oddusuddan | Oddusuddan |  | - | 2021-11-12 | 2022-05-18 | [9 empty] | City beatification | 10 | Construction of landscape development | 50 | 90 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 59 | Landscape improvement at Thirappane | Thirappane |  | - | 2021-08-20 | 2022-03-20 | [9 empty] | Providing beautification for the area | 38 | Landscaping | 62 | 62 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 60 | Parking area and flower stalls development near Samadhi Statue (stage II) | Anuradhapura |  | - | 2021-09-01 | 2022-03-01 | [9 empty] | Providing facilities for public and venders | 87 | Construction of parking are and flower stalls | 13 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 61 | Landscaping and parking at Thirappane | Thirappane |  | - | 2021-08-13 | 2022-02-15 | [9 empty] | City beatification | 80 | Construction of landscape development | 20 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 62 | Malawawewa landscaping at Kekirawa | Kekirawa |  | - | 2021-08-13 | 2022-02-15 | [9 empty] | City beatification | 20 | Construction of landscape development | 80 | - | - | - | Terminated | - | 100 | Terminated | 61 | Contractor terminated
| 63 | Landscaping and parking at Eppawala | Eppawala |  | - | 2021-08-13 | 2022-02-15 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 64 | Landscape and road improvement at Kapugollewa | Kapugollewa |  | - | 2021-08-19 | 2022-02-15 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | 40 | - | - | Gravel compaction completed. Paving work in progress and 90% completed. Laying and compactoon of ABC completed. Laying of asphalt layer is remaining. EOT requested upto 15.05.2022 | 88 | 100 | Gravel compaction completed. Paving work in progress and 90% completed. Laying and compactoon of ABC completed. Laying of asphalt layer is remaining. EOT requested upto 15.05.2022 | 95 | Due to unavailability of material and fuel at the market.
| 65 | Landscaping along the Dharmapala Mawatha at Anuradhapura | Anuradhapura |  | - | 2021-09-17 | 2022-03-16 | [9 empty] | City beatification | 90 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 66 | Sanitary facilities development and landscaping at Habarana | Habarana |  | - | 2021-08-19 | 2022-02-15 | [9 empty] | City beatification | 20 | Construction of landscape development | 80 | - | - | - | Contractor terminated | - | 100 | Contractor terminated | 34 | Contractor terminated
| 67 | Road improvement and landscape project Medawachchiya | Medawachchiya |  | - | 2021-11-12 | 2022-04-16 | [9 empty] | City beatification | 6 | Construction of landscape development | 69 | 94 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 68 | Road improvement and landscape project at Galnewa | Galnewa |  | - | 2021-11-12 | 2022-04-17 | [9 empty] | City beatification | 25 | Construction of landscape development | 65 | 75 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 69 | Township development project at Nochchiyagama | Nochchiyagama |  | - | 2021-11-12 | 2022-04-18 | [9 empty] | City beatification | 11 | Construction of landscape development | 69 | 89 | - | - | Contractor mobilized the site on 14.11.2021. Drainage work is in progress. Raising the wall of the existing drain is in progress. 100% completed. Preperation of sub base for paving is in progress. Turffing 95% completed. contractor asks for a new rate for paving. | 60.6742 | 100 | Contractor mobilized the site on 14.11.2021. Drainage works is in progress. Raising the wall of the existing drain is in progress. 100% completed. Preperation of sub base for paving is in progress. Turffing 95% completed. contractor asks for a new rate for paving. | 65 | Due to unavailability of material and fuel at the market.
| 70 | Aralaganvila town beautification project | Aralaganvila |  | - | 2021-08-13 | 2022-02-15 | [9 empty] | City beatification | 75 | Construction of landscape development | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 71 | Madirigiriya town beautification project | Madirigiriya |  | - | 2021-08-13 | 2022-02-16 | [9 empty] | City beatification | 90 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 72 | Walikanda town beautification project | Walikanda |  | - | 2021-08-13 | 2022-02-17 | [9 empty] | City beatification | 90 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 73 | Jayanthipura town beautification project | Jayanthipura |  | - | 2021-08-13 | 2022-02-18 | [9 empty] | City beatification | 95 | Construction of landscape development | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
North Western Province | 74 | Public fair development at Alawwa town | Alawwa |  | - | 2021-06-01 | 2022-07-30 | [9 empty] | Providing facilities for public and venders | 65 | Construction of public fair | 15 | 30 | 35 | - | Construction work is in the first floor areis in progress. | 23.3333 | 95 | Construction work is in the first floor areis in progress. | 72 | Due to unavailability of material and fuel at the market.
| 75 | Lake round beautification at Kurunegala (stage III) | Kurunegala |  | - | 2021-06-16 | 2022-08-16 | [9 empty] | Providing beautification for the area | 54 | Landscaping | 21 | 36 | 46 | - | Construction of retaining wall and soil compaction work and turfing work are in progress. | 72.2222 | 90 | Construction of retaining wall and soil compaction work and turfing work are in progress. | 80 | Due to unavailability of material and fuel at the market.
| 76 | Redevelopment project of Rajapihilla Urban Park at Kurunegala (phase II) | Kurunegala |  | - | 2021-08-25 | 2022-08-30 | [9 empty] | Providing recreational facilities | 22 | Completion of recreational park | 28 | 58 | 78 | - | Sub structure finished | 39.6552 | 80 | Sub structure finished | 45 | Reduced the scope.
| 77 | Landscaping and city beautification project at Kobeigane | Kobeigane |  | - | 2021-08-19 | 2022-02-20 | [9 empty] | City beatification | 45 | Construction of landscape development | 55 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 78 | Landscaping and city beautification project at Ambanpola | Ambanpola |  | - | 2021-08-19 | 2021-12-31 | [9 empty] | City beatification | 100 | Construction of landscape development | - | - | - | - | Completed | - | - | Completed | 100 | -
| 79 | Landscaping and city beautification project at Hiripitiya | Hiripitiya |  | - | 2021-08-13 | 2021-12-31 | [9 empty] | City beatification | 100 | Construction of landscape development | - | - | - | - | Completed | - | - | Completed | 100 | -
| 80 | Landscaping and city beautification project at Bingiriya | Bingiriya |  | - | 2021-08-13 | 2022-02-20 | [9 empty] | City beatification | 75 | Construction of landscape development | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 81 | Landscaping and city beautification project at Alawwa | Alawwa |  | - | 2021-09-17 | 2022-03-20 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 82 | Landscaping and city beautification project at Hettipola | Hettipola |  | - | 2021-11-10 | 2022-04-21 | [9 empty] | City beatification | 25 | Construction of landscape development | 55 | 75 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 83 | Landscaping and city beautification project at Pannala | Pannala |  | - | 2021-08-13 | 2021-12-31 | [9 empty] | City beatification | 100 | Construction of landscape development | - | - | - | - | Completed | - | - | Completed | 100 | -
| 84 | Landscaping and city beautification project at Polgahawela | Polgahawela |  | - | 2021-11-10 | 2022-04-21 | [9 empty] | City beatification | 23 | Construction of landscape development | 62 | 77 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 85 | Landscaping and city beautification project at Bamunukotuwa | Bamunukotuwa |  | - | 2021-10-28 | 2022-03-22 | [9 empty] | City beatification | 28 | Construction of landscape development | 72 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 86 | Public convenience improvement project at Chilaw | Chilaw |  | - | 2021-08-19 | 2022-02-20 | [9 empty] | City beatification | 40 | Construction of landscape development | 60 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 87 | Transits oriented development project at Thoppuwa | Thoppuwa |  | - | 2021-08-19 | 2022-02-20 | [9 empty] | City beatification | 85 | Construction of landscape development | 15 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 88 | Landscape improvement project at Palaviya | Palaviya |  | - | 2021-10-25 | 2022-03-22 | [9 empty] | City beatification | 12 | Construction of landscape development | 88 | - | - | - | Construction work temporary stoped due to unavailability of funds. | - | 100 | Construction works temporary stoped due to unavailability of funds. | 97 | Construction works temporary stoped due to unavailability of funds.
| 89 | Bus stand development at Warakapola (phase I) | Warakapola |  | - | 2021-05-18 | 2022-05-18 | [9 empty] | Providing transport facilities | 62 | Completion of bus stand | 18 | 38 | - | - | Work is in progress | 78.9474 | 100 | Work is in progress | 92 | Due to unavailability of material and fuel at the market.
| 90 | Development of walkway track at Pinnwala, Rabukkana (approx.. 250m) | Rabukkana |  | - | 2021-08-02 | 2022-02-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 78 | Construction of jogging track | 22 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 91 | Township development at Hiriwadunna, Rambukkana | Rambukkana |  | - | 2021-08-19 | 2022-04-20 | [9 empty] | City beatification | 8 | Construction of landscape development | 62 | 92 | - | - | Slowly in progress | 56.5217 | 100 | Slowly in progress | 60 | Sheduled to be completed 31st July 2022.
| 92 | Town center amenities improvement project at Galigamuwa | Galigamuwa |  | - | 2021-08-13 | 2022-03-20 | [9 empty] | City beatification | 35 | Construction of landscape development | 65 | 65 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 93 | Landscaping and public amenities improvement project at Bulathkohupitiya | Bulathkohupitiya |  | - | 2022-01-31 | 2022-06-20 | [9 empty] | City beatification | 0 | Construction of landscape development | 60 | 100 | - | - | - | - | 100 | - | - | Project terminated
| 94 | Landscaping project at Moronthota | Moronthota |  | - | 2022-01-17 | 2022-06-21 | [9 empty] | City beatification | 0 | Construction of landscape development | 50 | 100 | - | - | Slowly in progress | 72 | 100 | Slowly in progress | 72 | Sheduled to be completed 31st July 2022.
| 95 | Public amenities improvement project at Hemmathagama | Hemmathagama |  | - | 2021-11-10 | 2022-04-11 | [9 empty] | City beatification | 20 | Construction of landscape development | 60 | 80 | - | - | Slowly in progress | 82.5 | 100 | Slowly in progress | 86 | Sheduled to be completed 31st July 2022.
| 96 | Public fair development at Rakwana | Rakwana |  | - | 2021-07-13 | 2022-01-15 | [9 empty] | Providing facilities for venders and public | 95 | Construction of public fair | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 97 | Public fair development at Kalawana | Kalawana |  | - | 2021-07-13 | 2022-03-15 | [9 empty] | Providing facilities for venders and public | 45 | Construction of public fair | 55 | 55 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 98 | Town center improvement at Kuruwita | Kuruwita |  | - | 2021-08-23 | 2022-02-20 | [9 empty] | City beatification | 65 | Construction of landscape development | 35 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 99 | Ayagama town center improvement project | Ayagama |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 100 | Nivithigala town center improvement project | Nivithigala |  | - | 2021-11-10 | 2022-03-10 | [9 empty] | City beatification | 25 | Construction of landscape development | 75 | 75 | - | - | Slowly in progress | 71 | 100 | Slowly in progress | 78 | Sheduled to be completed 31st July 2022.
| 101 | Jogging track along Dorawela Oya Balangoda (stage II) | Balangoda |  | - | 2021-10-25 | 2022-05-25 | [9 empty] | City beatification | 5 | Construction of landscape development | 60 | 95 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 102 | Development of playground at Baliwala, Benthota | Benthota |  | - | 2021-06-10 | 2022-03-15 | [9 empty] | Ensuring student's safety, controlling limited access on school grounds rely on physical barriers and creating a balance between aesthetics and security | 70 | Development of playground | 30 | 30 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 103 | Moragoda Ela walk path development at Galle | Galle |  | - | 2021-09-06 | 2022-02-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 68 | Construction of jogging track | 32 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 104 | Balapitiya Kirilla Ela walk path development | Balapitiya |  | - | 2021-08-02 | 2022-02-15 |  | -14: 80; -15: Construction of landscape development; Q-1 -16: 20; Q-2 -17: -; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: 100; Q-4 (22): 100; Q-4 -23: Completed; Q-4 -24: 100; Q-4 -25: -
| 105 | Holuwagoda Agro Ecological Park (phase I) | Holuwagoda |  | - | 2021-07-28 | 2022-02-15 |  | -14: 90; -15: Construction of landscape development; Q-1 -16: 10; Q-2 -17: 10; Q-3 -18: -; Q-4 -19: -; Q-4 -20: 1. Curb laying and solar power cabling along walk path is in progress. 2. construction work of 8m and 4m span steel bridges are in progress. 3. construction work of 5m span extended culvert is in progress 4. soil filling work at Island space and proposed service road are in progress. 5. turffing along the walk path is in progress.; Q-4 -21: 70; Q-4 (22): 100; Q-4 -23: 1. Curb laying and solar power cabling along walk path is in progress. 2. construction work of 8m and 4m span steel bridges are in progress. 3. construction work of 5m span extended culvert is in progress 4. soil filling work at Island space and proposed service road are in progress. 5. turffing along the walk path is in progress.; Q-4 -24: 97; Q-4 -25: Due to unavailability of material and fuel at the market.
| 106 | Kumarakanda junction improvement | Kumarakanda junction |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 93 | Construction of landscape development | 7 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 107 | Ambalangoda city entrance and beautification | Ambalangoda |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 97 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 108 | Construction of pedestrian pathways at Habaraduwa | Habaraduwa |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 90 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 109 | Southern entrance development and beautification at Bentota | Bentota |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 97 | Construction of landscape development | 3 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 110 | Landscape improvement and city beautification at Baddegama | Baddegama |  | - | 2021-08-20 | 2022-02-20 | [9 empty] | City beatification | 93 | Construction of landscape development | 7 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 111 | Landscape improvement and city beautification at Halwatura | Halwatura |  | - | 2021-08-20 | 2022-06-20 | [9 empty] | City beatification | 5 | Construction of landscape development | 55 | 95 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 112 | Bus stand development at Akuressa | Akuressa |  | - | 2022-01-22 | 2022-12-31 | [9 empty] | Providing transport facilities | 0 | Completion of bus stand | 20 | 50 | 80 | 100 | - | - | 50 | - | - | Project terminated
| 113 | Construction of bus stand at Deiyandara | Deiyandara |  | - | 2022-01-15 | 2022-12-31 | [9 empty] | Providing bus parking facilities | 0 | Completion of bus stand | 15 | 40 | 70 | 100 | - | - | 40 | - | - | Project terminated
| 114 | Development of walking track around Kamburugamuwa Lake (phase I) | Kamburugamuwa |  | - | 2021-09-01 | 2022-02-21 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 75 | Construction of jogging track | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 115 | Landscaping project at Deiyandara | Deiyandara |  | - | 2021-08-20 | 2022-02-21 | [9 empty] | City beatification | 69 | Construction of landscape development | 31 | 31 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 116 | Landscaping project at Morawaka | Morawaka |  | - | 2021-08-20 | 2022-02-21 | [9 empty] | City beatification | 84 | Construction of landscape development | 16 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 117 | Landscaping project at Pitabeddara | Pitabeddara |  | - | 2021-08-20 | 2022-02-21 | [9 empty] | City beatification | 63 | Construction of landscape development | 17 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 118 | Landscaping project at Deniyaya | Deniyaya |  | - | 2021-08-20 | 2022-01-21 | [9 empty] | City beatification | 99 | Construction of landscape development | 1 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 119 | Landscaping project at Weligama | Weligama |  | - | 2021-08-20 | 2022-02-21 | [9 empty] | City beatification | 95 | Construction of landscape development | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 120 | Landscaping project at Kamburupitiya | Kamburupitiya |  | - | 2021-08-19 | 2022-02-21 | [9 empty] | City beatification | 98 | Construction of landscape development | 2 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 121 | Mini bus terminal at Barawakumbura | Barawakumbura |  | - | 2021-06-11 | 2021-12-31 | [9 empty] | Providing bus parking facilities | 100 | Completion of bus terminal | - | - | - | - | Completed | - | - | Completed | 100 | -
| 122 | Construction of wholesale market and commercial building at Walasmulla | Walassmulla |  | - | 2021-06-11 | 2022-01-09 | [9 empty] | Providing market facilities for venders an public | 95 | Completion of wholesale market | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 123 | Development of walking track around Ampitiya Lake, Beliatta (phase I) | Beliatta |  | - | 2021-07-06 | 2022-04-15 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 35 | Construction of jogging track | 45 | 65 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 124 | Ranna town development | Ranna |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 75 | Construction of landscape development | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 125 | Weerawila junction development | Weerawila |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 85 | Construction of landscape development | 15 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 126 | Chithragala junction development | Chithragala |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 127 | Nonagama junction development | Nonagama |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | 30 | - | - | Finishing work is in progress. | 83.3333 | 100 | Finishing work is in progress. | 95 | Sheduled to be completed 31st July 2022.
| 128 | Aluthwewa junction development at Agunakolapalassa | Agunakolapalassa |  | - | 2021-08-16 | 2022-02-17 |  | -13: City beatification; -14: 75; -15: Construction of landscape development; Q-1 -16: 25; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: 100; Q-4 (22): 100; Q-4 -23: Completed; Q-4 -24: 100; Q-4 -25: -
| 129 | Mulgala junction development at Lunugamwehera | Lunugamwehera |  | - | 2021-08-16 | 2022-02-17 | [9 empty] | City beatification | 80 | Construction of landscape development | 20 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 130 | Weekly fair development project at Diyathalawa (stage I) | Diyathalawa |  | - | 2021-08-18 | 2022-02-28 | [9 empty] | Providing facilities for venders and public | 60 | Completion of pola | 40 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 131 | Pedestrian walking path and landscape project at Bandarawela | Bandarawela |  | - | 2021-08-16 | 2021-12-31 | [9 empty] | City beatification | 100 | Construction of landscape development | - | - | - | - | Completed | - | - | Completed | 100 | -
| 132 | Town improvement and landscaping project at Beragala | Beragala |  | - | 2021-11-09 | 2022-05-18 | [9 empty] | City beatification | 25 | Construction of landscape development | 30 | 75 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 133 | Town improvement project at Giradurukotte | Giradurukotte |  | - | 2021-11-09 | 2022-05-19 | [9 empty] | City beatification | 30 | Construction of landscape development | 40 | 70 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 134 | Spring Valley town center development at Badulla | Badulla |  | - | 2021-11-09 | 2022-05-20 | [9 empty] | City beatification | 18 | Construction of landscape development | 52 | 82 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 135 | Town improvement and landscaping at Kataragama | Kataragama |  | - | 2021-09-21 | 2022-03-22 | [9 empty] | City beatification | 53 | Construction of landscape development | 47 | 47 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 136 | Town improvement and landscaping at Wellawaya | Wellawaya |  | - | 2021-11-09 | 2022-05-10 | [9 empty] | City beatification | 25 | Construction of landscape development | 40 | 75 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 137 | Town improvement and landscaping at Thanamalwila | Thanamalwila |  | - | 2021-11-09 | 2022-05-10 | [9 empty] | City beatification | 30 | Construction of landscape development | 40 | 70 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 138 | Town improvement and landscaping at Sevanagala | Sevanagala |  | - | 2021-11-09 | 2022-05-10 | [9 empty] | City beatification | 22 | Construction of landscape development | 53 | 78 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 139 | Town improvement project at Okkampitiya | Okkampitiya |  | - | 2021-09-21 | 2022-04-10 | [9 empty] | City beatification | 26 | Construction of landscape development | 64 | 74 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 140 | Ethimala town center development | Ethimala |  | - | 2021-11-09 | 2022-05-10 | [9 empty] | City beatification | 15 | Construction of landscape development | 45 | 85 | - | - | Slowly Progress | 78.8235 | 100 | Slowly Progress | 82 | Sheduled to be completed 31st July 2022.
Western Province | 141 | Construction of new market at Katubedda | Katubedda |  | - | 2019-07-15 | 2021-12-31 | [9 empty] | Providing facilities for venders and public | 100 | Completion of market | - | - | - | - | Completed | - | - | Completed | 100 | -
| 142 | Boralesgamuwa multipurpose building (stage II) | Boralesgamuwa |  | - | 2021-06-09 | 2022-12-09 | [9 empty] | Providing facilities for vendors | 35 | Completion of building | 15 | 35 | 55 | 65 | Slowly in progress | 14.2857 | 70 | Slowly in progress | 40 | Funding issues
| 143 | Proposed Kotte Fortress Park Gateway and Facility Centre (stage I) | Kotte |  | - | 2021-09-29 | 2022-04-27 | [9 empty] | Conservation of heritage landscaping and improving socio cultural characteristic with heritage city concept | 65 | Completion of park and building | 25 | 35 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 144 | Proposed Kotte Fortress Park Gateway and Facility Centre (stage II) |  |  | - | 2021-09-15 | 2022-01-26 | [9 empty] | Conservation of historical place and providing recreational facilities | 70 | Conservation of historical place | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 145 | Hanwella bus stand development | Hanwella |  | - | 2021-04-19 | 2022-02-15 |  | -13: Providing transport facilities; -14: 85; -15: Completion of bus stand; Q-1 -16: 15; Q-2 -17: -; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: 100; Q-4 (22): 100; Q-4 -23: Completed; Q-4 -24: 100
| 146 | Development of public market at Avissawella | Avissawella |  | - | 2021-07-15 | 2022-06-15 | [9 empty] | Providing market facilities for venders | 17 | Completion of market | 43 | 83 | - | - | finishes work in progress | 61.4458 | 100 | finishes work in progress | 68 | Due to unavailability of funds and materials
| 147 | Development of playground and walkway at Moratuwa | Moratuwa |  | - | 2021-12-20 | 2022-03-15 | [9 empty] | City beatification | 0 | Construction of jogging track | 100 | - | - | - | - | - | - | - | 0 | Project terminated
| 148 | Pedestrian walkway at development project at Lunawa | Lunawa |  | - | 2021-08-02 | 2022-02-10 | [9 empty] | City beatification | 78 | Construction of jogging track | 22 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 149 | Pedestrian walkway around the floating market area (Fort Station up to Maradana junction) | Maradana |  | - | 2021-05-19 | 2022-04-15 | [9 empty] | City beatification | 35 | Construction of jogging track | 45 | 65 | - | - | Terminated | - | 100 | Terminated | 35 | Project terminated
| 150 | Construction of walking track around Kesbewa Wewa | Kesbewa |  | - | 2020-06-18 | 2022-02-15 | [9 empty] | City beatification | 80 | Construction of jogging track | 20 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 151 | Development of Angoda bus stand surrounding at Kotikawatta | Kotikawatta |  | - | 2021-08-19 | 2022-02-28 | [9 empty] | City beatification | 50 | Construction of landscape development | 50 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 152 | Construction of town center development at Hanwella | Hanwella |  | - | 2021-11-10 | 2022-03-15 | [9 empty] | City beatification | 15 | Construction of landscape development | 85 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 153 | Mini urban park development project at Padukka | Padukka |  | - | 2021-12-20 | 2022-04-20 | [9 empty] | City beatification | 15 | Construction of landscape development | 60 | 85 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 154 | Construction of open air theatre at Kaduwela | Kaduwela |  | - | 2021-12-03 | 2022-04-30 | [9 empty] | City beatification | 40 | Construction of landscape development | 45 | 55 | - | - | Completed | 109.0909 | 95 | Completed | 100 | -
| 155 | Construction of pedestrian pathway at Kottawa | Kottawa |  | - | 2021-11-10 | 2022-05-24 | [9 empty] | City beatification | 10 | Construction of landscape development | 60 | 90 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 156 | Public market Minuwangoda (stage II) | Minuwangoda |  | - | 2021-04-19 | 2021-12-31 | [9 empty] | Providing market facilities for vendors | 100 | Completion of market | - | - | - | - | Completed | - | - | Completed | 100 | -
| 157 | Peralanda Wewa recreational park (stage II) | Peralanda |  | - | 2021-04-19 | 2022-01-20 | [9 empty] | Providing recreational facilities | 75 | Completion of park | 25 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 158 | Development of public market at Gampaha (stage II) | Gampaha |  | - | 2021-09-25 | 2023-03-25 | [9 empty] | Providing market facilities for venders | 11 | Completion of market | 19 | 34 | 49 | 64 | Sub structure work is in progress | 35.2941 | 45 | Sub structure work is in progress | 23 | Due of unavailability of funds
| 159 | Development of jogging track at Makevita (stage I) | Makevita |  | - | 2021-03-26 | 2021-12-31 | [9 empty] | Providing recreational facilities | 100 | Completion of jogging track | - | - | - | - | Completed | - | - | Completed | 100 | -
| 160 | Development of jogging track at Makevita (Stage II) |  |  | - | 2021-06-09 | 2022-04-09 | [9 empty] | Providing recreational facilities | 42 | Completion of jogging track | 48 | 58 | - | - | Temporary suspended | 17.2414 | 100 | Hold the project | 52 | Temporary suspended
| 161 | Development of walkway track at Yakkala Ayurveda University (phase I) | Yakkala |  | - | 2021-06-14 | 2022-02-15 | [9 empty] | Providing recreational facilities | 78 | Completion of jogging track | 22 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 162 | Development of Henarathgoda walkway track at Gampaha (phase I) | Gampaha |  | - | 2021-06-11 | 2022-02-22 | [9 empty] | Providing recreational facilities | 80 | Completion of jogging track | 20 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 163 | Volleyball court and urban park at Gampaha (phase I) |  |  | - | 2021-12-20 | 2022-12-30 | [9 empty] | Promoting physical fitness and good health and increasing recreational facility among the people | 0 | Completion of jogging track | 20 | 55 | 75 | 100 | Taken time to change the scope | 14.5455 | 55 | Taken time to change the scope | 8 | Taken time to change the scope
| 164 | Development of walking track along Bauddaloka Mawatha at Gampaha (phase I) |  |  | - | 2021-09-07 | 2021-12-31 |  | -14: 100; -15: Completion of jogging track; Q-1 -16: -; Q-2 -17: -; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: -; Q-4 (22): -; Q-4 -23: Completed; Q-4 -24: 100; Q-4 -25: -
| 165 | Development of walking track along Bauddaloka Mawatha at Gampaha (phase II) |  |  | - | 2021-12-10 | 2022-02-10 |  | -14: 5; -15: Completion of jogging track; Q-1 -16: 95; Q-2 -17: 95; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Completed; Q-4 -21: 100; Q-4 (22): 100; Q-4 -23: Completed; Q-4 -24: 100; Q-4 -25: -
| 166 | Redevelopment of Oruthota walking path at Gampaha (phase I) |  |  | - | 2021-06-26 | 2022-02-20 |  | -14: 38; -15: Completion of jogging track; Q-1 -16: 62; Q-2 -17: 62; Q-3 -18: -; Q-4 -19: -; Q-4 -20: Work is in progress; Q-4 -21: 43.5484; Q-4 (22): 100; Q-4 -23: Work is in progress; Q-4 -24: 65; Q-4 -25: Contractor and enginers were failed to overcome the issue of high water level of the adjoining canal.
| 167 | Small town development project at Peliyagoda | Peliyagoda |  | - | 2021-10-13 | 2022-02-13 | [9 empty] | City beatification | 70 | Construction of landscape development | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 168 | Small town development project at Ekala | Ekala |  | - | 2021-11-28 | 2022-03-28 | [9 empty] | City beatification | 55 | Construction of landscape development | 45 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 169 | Small town development project at Awariyawatta | Awariyawatta |  | - | 2021-10-13 | 2022-02-13 | [9 empty] | City beatification | 50 | Construction of landscape development | 50 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 170 | Small town development projectat Minuwangoda | Minuwangoda |  | - | 2021-09-30 | 2022-01-30 | [9 empty] | City beatification | 60 | Construction of landscape development | 40 | 40 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 171 | Small town improvement project at Mellawagedara | Mellawagedara |  | - | 2021-10-14 | 2022-02-14 | [9 empty] | City beatification | 55 | Construction of landscape development | 45 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 172 | Small town improvement project at Ganemulla | Ganemulla |  | - | 2021-10-13 | 2022-01-31 | [9 empty] | City beatification | 50 | Construction of landscape development | 50 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 173 | Small town improvement project at Pugoda | Pugoda |  | - | 2021-10-14 | 2022-02-14 | [9 empty] | City beatification | 55 | Construction of landscape development | 45 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 174 | Makevita town development | Makevita |  | - | 2021-10-14 | 2022-02-14 | [9 empty] | City beatification | 48 | Construction of landscape development | 52 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 175 | Small town development project at Wathupitiwala | Wathupitiwala |  | - | 2021-11-15 | 2022-02-14 | [9 empty] | City beatification | 90 | Construction of landscape development | 10 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 176 | Small town development project at Radawana | Radawana |  | - | 2021-12-14 | 2022-04-14 | [9 empty] | City beatification | 3 | Construction of landscape development | 72 | 97 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 177 | Nittambuwa town development project | Nittambuwa |  | - | 2021-12-01 | 2022-04-01 | [9 empty] | City beatification | 15 | Construction of landscape development | 65 | 85 | - | - | Completed | 100 | 100 | Completed | 100 | -
| 178 | Development of Panadura public market and multipurpose building | Panadura |  | - | 2021-12-04 | 2022-12-04 | [9 empty] | Providing market facilities for venders | 2 | Completion of market | 18 | 38 | 68 | 98 | Foundation work completed | 26.3158 | 40 | Foundation work completed | 12 | Delay of temporary relocation of vendors and scarcity of materials
| 179 | Development of walkway track at Ingiriya, Horana | Ingiriya |  | - | 2021-09-01 | 2022-02-15 | [9 empty] | Providing recreational facilities | 70 | Completion of jogging track | 30 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 180 | Construction of pedestrian pathway at Moragahahena | Moragahahena |  | - | 2021-09-11 | 2022-01-11 | [9 empty] | City beatification | 98 | Construction of landscape development | 2 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 181 | Construction of pedestrian pathway at Nagoda | Nagoda |  | - | 2021-12-09 | 2022-01-12 | [9 empty] | City beatification | 95 | Construction of landscape development | 5 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 182 | Construction of pedestrian pathway at Dodangoda | Dodangoda |  | - | 2021-09-12 | 2022-01-12 | [9 empty] | City beatification | 65 | Construction of landscape development | 35 | - | - | - | Completed | 100 | 100 | Completed | 100 | -
| 183 | Town improvement project at Meegahathenna | Meegahathenna |  | - | 2021-11-05 | 2022-03-05 | [9 empty] | City beatification | 45 | Construction of landscape development | 55 | - | - | - | Completed | 100 | 100 | Completed | 100 | -

## UDA - Tech City
State Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programmes as at 30th June 2022
SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets
[8 empty] | Allocation 2022 (Rs. Mn) | Financial targets and progress- 2022 ( as at 30.06.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [6 empty] | Cumulativ Physical Target as at 30.06.2022 (%) | Cumulative Physical Progress (as at 30.06.2022)
[9 empty] | Expenditure target | Imprest requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  | Original | Current (if revised during implementation) | Original | Revised (if extended) | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%) ( B ) |  |  |  | Description | as % of (B) |  | Description | as % of overall target (% of A)
[18 empty] | Q-1 | Q-2 | Q-3 | Q-4
| -1 | -2 | -3 |  | -4 |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22 | -23 | -24 | -25
19 | Improvement of Road Infrastructure in the Homagama Region (Tech City Development)
19.1 | Construction of new access road from Kottawa to Mahenwatta | Kottawa - Mahenwaththa | 712 |  | Aug 2019- July 2020 | Aug 2019 - Feb 2022 | GOSL | 100 | - | - | - | - | 19.88 | 947.11 | Construction of New Access road from Kottawa to Mahenwatta | 88 | Acquisition of Lands, Implementation of work,Construction | 12 | 12 | - | - | Completed Identified balance work | 25 | 100 | Completed Identified balance work | 91 | It was decided to stop the project at the PP is 91%.
19.2 | Improvements to Roads - Pitipana/Thalagala road - Section A (from pitipana junction through school junction up to SLT data center in dampe road) - 4km | Pitipana - Thalagala (Consultant-PRDA) | 563 |  | Aug 2018- July 2020 | Aug 2018-Nov 2021 | GOSL | - | - | - | - | - |  |  | Improvements to Roads - Pitipana/ Thalagala road - Section A, Homagama Kottawa High Level Road traffc management | 5 | Acquisition of land, Implementation of work.Construction | - | 15 | 45 | 95 | Project Termineted | 0 | 100 | Project Termineted | 5 | Project Termineted

## UDA - Beira Lake
State Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programmes as at 30th June 2022
SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets | DPMM Comment | DPMM Obsrevations
[8 empty] | Allocation 2022 Rs. Mn | Financial targets and progress- 2022 ( as at 30.06.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [6 empty] | Cumulativ Physical Target as at 30.06.2022 (%) | Cumulative Physical Progress (as at 30.06.2022)
[9 empty] | Expenditure target | Imprest Requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  | Original | Current (if revised during implementation) | Original | Revised (if extended) | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%) ( B ) |  |  |  | Description | as % of (B) |  | Description | as % of overall target (% of A)
[18 empty] | Q-1 | Q-2 | Q-3 | Q-4
| -1 | -2 | -3 |  | -4 |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | (22) | -23 | -24 | -25 | -26
1 | Beira Lake Rehabilitation and Redevelopment Project | Beira Lake Colombo | 2920 | - | Jan 2018 - Dec 2021 | Jan 2018 - 15.Apr.2022 | GOSL | 20 | 20 | 12.85 | 12.85 | 12.85 | - | 1880.21 | Construction of Linear Park recreational facilities for all kind of people and age groups and protection of bank 1.4km of Bank Protection. Dreging works of East and West Beira Lake. 1.8km of Liner Park development | 78 | Construction of Linear ParkWestern Bank East Lake (800m) | 22 | 22 | - | - | Paving/Landscape/Visual/ barrier in progress | 10 | 100 | Paving/Landscape/Visual/ barrier in progress | 80.28 | Lack of allocation
[17 empty] | Construction of Bank protection of Western Bank of East Lake (800m) | [7 empty] | Completed
[17 empty] | Construction of Bank protection of Western Bank of East Lake (600m) | [7 empty] | Completed
[17 empty] | Construction of Liner Park of Western Bank of East Lake (600m) | [7 empty] | Not awarded yet
[17 empty] | Construction of Liner Park along beira lake (400m) (Adjacent to Finance Ministry) | [7 empty] | Not awarded yet

## UDA - Public
Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programmes as at 30th June, 2022
Province | SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets | DPMM Comments
[10 empty] | Allocation 2022 Rs.Mn | Financial targets and progress- 2021 ( as at 30.06.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [6 empty] | Cumulative physical target as at 30.06.2022 (%) | Cumulative Physical Progress (as at 30.06.2022)
[11 empty] | Expenditure target | Imprest requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  |  | Original | Current (if revised during implementation) | Original |  | Revised (if extended) | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%)( Revised) ( B) |  |  |  | Description | as % of (B) |  | Description | as % of overall Progress (% of A)
[20 empty] | Q-1 | Q-2 | Q-3 | Q-4
|  | -1 | -2 | -3 |  | -4 |  |  | -5 | -6 | (7) | (8) | (9) | (10) | (11) | (12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | (21) | (22) | -23 | -24 | -25
UDA Public Institutions
Western | 1 | Public market at Piliyandala | Piliyandala | 498 |  | 2022-01-12 | 2023-04-15 |  | GOSL | 300 | 250 | 184 | 50 | 50 | 134 | 50 | Improving market infrastructure facilities | 0 | Construction of public market | 30 | 40 | 50 | 60 | only priliminary work done | 0 | 40 | Only priliminary work done | 0 | Mutually agreed to terminate the project
Western | 2 | Boralesgamuwa Wewa surrounding area development (stage IV) | Boralesgamuwa | 91.5 |  | 2022-08-03 | 2022-02-03 | [9 empty] | Controlling unauthorized construction towards the lake, dumping of garbage to the lake through peripheral canals, drains and ditches, improving mental and physical health of public | 45 | Improving walkability to city dwellers while providing gathering spaces along the linear park | 55 | 55 | - | - | Once the fuel issue in the country compaction of soil could be done and achieve completion of the project.all the other items completed as discussed before, present progress is 85% | 73 | 100 | Once the fuel issue in the country compaction of soil could be done and achieve completion of the project.all the other items completed as discussed before, present progress is 85% | 85 | Shortage of fuel.
Western | 3 | Construction of relocation houses for Millewa new prison project | Millewa | 130 |  | 2021-10-30 | 2022-07-30 | [9 empty] | Relocation of families | 5 | Development of housing scheme | 55 | 90 | 95 | - | Work in Progress | 41.1111 | 95 | Work in Progress | 42 | Unavailability of material and fuel at the market.
Western | 4 | Ankumbura pola development | Ankumbura | 30 |  | 2022-01-25 | 2022-07-31 | [9 empty] | Upgrading public and infrastructure facilities of the town | 0 | Completion of weekly fair | 50 | 95 | 100 | - | Not yet awarded | 0 | 95 | Not yet awarded | 0 | Not yet awarded.
Western | 5 | Thalathuoya car park development | Thalathuoya | 9.5 |  | 2021-12-07 | 2022-03-30 | [9 empty] | Upgrading parking facilities of the town | 0 | Completion of car park | 100 | 100 | - | - | Decision has been taken to suspend construction temperary and complete reataining wall and column. | 37 | 100 | Decision has been taken to suspend construction temperary and complete reataining wall and column. | 37 | Decision has been taken to suspend construction temperary and complete reataining wall and column.
Western | 6 | Dawlagala public fair development | Dawlagala | 10 |  | 2021-11-27 | 2022-04-17 | [9 empty] | Upgrading public and infrastructure facilities of the town | 0 | Completion of weekly fair | 75 | 100 | - | - | Decision has been taken to suspend construction temperary and complete work upto only concrete column and tie beam. | 39 | 100 | Decision has been taken to suspend construction temperary and complete work upto only concrete column and tie beam. | 39 | Decision has been taken to suspend construction temperary and complete work upto only concrete column and tie beam.
Western | 7 | Pallemunei playground development (stage II) | Pallemunei | 46.31 |  | 2022-02-08 | 2022-11-10 | [9 empty] | Providing better facilities for players and sports fans | 0 | Completion of playground | 50 | 70 | 85 | 100 | - | 0 | 70 | - | 0 | Steps taken to temporarily suspend the project at the procurement stage.
Western | 8 | Completion of bus stand at Mullativu | Mullativu | 116.08 |  | 2021-11-05 | 2022-07-15 | [9 empty] | Providing safe, accessible, efficient and sustainable transport system | 4 | Completion of bus stand | 60 | 90 | 96 | - | Foundation work completed. Column conctreting work is in progress. | 37.7778 | 94 | Foundation work completed. Column conctreting work is in progress. | 38 | Funds shortage and Delay of Materaial supply
Western | 9 | Weekly pola development at Ampara | Ampara | 173 |  | 2021-09-01 | 2022-12-15 | [9 empty] | Upgrading public and infrastructure facilities of the town | 18 | Completion of pola | 27 | 47 | 62 | 82 | Work in Progress | 68.0851 | 65 | Work in Progress | 50 | Funds shortage and Delay of Materaial supply
Western | 10 | Construction of waterfront park for public at Abayawewa | Abayawewa | 34.73 |  | 2022-01-04 | 2022-03-15 | [9 empty] | Development of social infrastructure Improving public parking and recreational facilities of the area | 0 | Development of sacred area | 100 | 100 | - | - | - | 26 | 100 | - | 26 | Funds shortage and Delay of Materaial supply
Western | 11 | Landscape development project at Bandaranayake Mawatha | Anuradhapura | 13.19 |  | 2021-11-28 | 2022-06-30 |  | -14: 0; Q-1 -16: 30; Q-2 -17: 100; Q-3 -18: -; Q-4 -19: -; Q-4 -20: -; Q-4 (21): 19; Q-4 (22): 100; Q-4 -23: -; Q-4 -24: 19; Q-4 -25: Mutually agreed to terminate the project
Western | 12 | Landscape development project for Maithreepala Senanayake Mawatha |  | 20.89 |  | 2021-12-20 | 2022-07-20 |  | -14: 0; Q-1 -16: 30; Q-2 -17: 70; Q-3 -18: 100; Q-4 -19: -; Q-4 -20: -; Q-4 (21): 22.8571; Q-4 (22): 70; Q-4 -23: -; Q-4 -24: 16; Q-4 -25: Mutually agreed to terminate the project
Western | 13 | Landscape development project for Harishchandra Mawatha |  | 30.79 |  | 2021-11-25 | 2022-08-25 |  | -14: 0; Q-1 -16: 30; Q-2 -17: 70; Q-3 -18: 100; Q-4 -19: -; Q-4 -20: -; Q-4 (21): 0; Q-4 (22): 70; Q-4 -23: -; Q-4 -24: 0; Q-4 -25: Steps taken to temporarily suspend the project at the procurement stage.
Western | 14 | Relocation of low income housing settlement at Beruwana Watta, Eheliyagoda (by-pass road) | Eheliyagoda | 95 |  | 2021-07-07 | 2022-06-07 | [9 empty] | Providing housing facilities | 40 | Construction of housing units | 30 | 60 | - | - | Work in Progress | 66.6667 | 100 | Work in Progress | 80 | Funds shortage and delay of materaial supply
Western | 15 | Kegalle bus depot relocation - ancillary facility and external work | Kegalle | 321 |  | 2021-12-07 | 2023-06-07 | [9 empty] | Improving transport facility | 6 | Construction of bus stand | 27 | 37 | 46 | 56 | Work in Progress | 21.6216 | 43 | Work in Progress | 14 | Funds shortage and delay of materaial supply
Western | 16 | Malimboda estate housing project | Malimboda | 80 |  | 2021-10-06 | 2022-10-05 | [9 empty] | Housing scheme | 0 | Housing scheme development | 40 | 60 | 90 | 100 | Work in Progress | 51.6667 | 60 | Work in Progress | 31 | Funds shortage and delay of materaial supply
Western | 17 | Development of Ruwanwella pola | Ruwanwella | 67 |  | 2022-01-10 | 2022-09-10 | [9 empty] | Upgrading public and infrastructure facilities of the town | 0 | Completion of pola | 30 | 60 | 100 | - | Work in Progress | 140 | 60 | Work in Progress | 84 | -
Western | 18 | Kataragama entrance square development (phase III and stage III) | Kataragama | 63 |  | 2021-08-15 | 2022-06-15 | [9 empty] | Improving social and economical infrastructure | 30 | Construction of 66 shops | 45 | 70 | - | - | Completed | 100 | 100 | Completed | 100 | -
Western | 19 | Entrance square development at Kataragama (phase III and stage IV) |  | 79 |  | 2021-08-15 | 2022-06-15 | [9 empty] | Improving social and economical infrastructure | 17 | Construction of 55 shops | 53 | 83 | - | - | Finishing Work | 75.9036 | 100 | Finishing Work | 80 | Delay due to shortage of fuel.
Western | 20 | Construction of balance work of bus stand at Baddegama (stage III) | Baddegama | 10 |  | 2021-12-24 | 2022-05-31 | [9 empty] | Providing bus parking facilities | 0 | Construction of bus stand | 50 | 100 | - | - | Completed | 100 | 100 | Completed | 100 | -
Western | 21 | Deiyandara landscape development (phase II) | Deiyandara | 10 |  | 2021-12-21 | 2022-06-01 | [9 empty] | Improving social and economical infrastructure | 0 | Construction of bus stand | 60 | 100 | - | - | Finishing Work | 98 | 100 | Finishing Work | 98 | Delay do to fuel issue.
Western | 22 | Deiyandara bus stand surrounding area development (phase III) |  | 10 |  | 2021-12-20 | 2022-05-31 | [9 empty] | Providing bus parking facilities | 0 | Construction of bus stand | 60 | 100 | - | - | Completed | 100 | 100 | Completed | 100 | -

## Solid Waste
State Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programmes as at 30th June 2022
SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets | DPMM Comments
[8 empty] | Allocation 2022 Rs. Mn | Financial targets and progress- 2022 ( as at 30.03.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [6 empty] | Cumulativ Physical Target as at 30.06.2022 (%) | Cumulative Physical Progress (as at 30.06.2022)
[9 empty] | Expenditure target | Imprest requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  | Original | Current (if revised during implementation) | Original | Revised (if extended) | [10 empty] | Descriptive target for 2021 | Cumulative quarterly targets (%) ( B ) |  |  |  | Description | as % of (B) |  | Description | as % of overall target (% of A)
[18 empty] | Q-1 | Q-2 | Q-3 | Q-4
| -1 | -2 | -3 |  | -4 |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22 | -23 | -24 | -25
1 | Metro Colombo Solid Waste Management Project | Kelaniya and Aruwakkalu | 14017 | 24092.79 | 2017-2020 | 2017- 2022.06.30 | GoSL | 800 | 592.39 | 592.39 | 228.27 | 228.27 | 364.12 | 18464.99 | a) Package - A (Transfer Stations at Meethotamulla and Aruwakkalu) b) Package - B (Sanitary Landfill at Aruwakkalu) c) Package - C (Rail Track Extension and Connectivity Line) d) Package -D (Rail equipment, machinary and other improvements) | 87 | Complete the construction of Package A,B,C . | 2 | 4 | 8 | 13 | 1) The construction of Aruwakkalu Sanitary Landfill is Completed, 2) The construction of railway connectivity is completed and comissioning is completed. The installation of railway signaling system, Installattion of Grantry cranes, construction of Access road , strom water drainage system and planting of live fence at Aruwakkalu are need to be completed. All the other construction works are already completed. 3) The commissioning of leachate treatment plant at Aruwakkalu is completed. 2)Installation of Deodarization system and leachate treatment facility of Kelaniya Transfer station facility are in progress. (5) All the Civil Construction works of Kelaniya Transfer Station facility completed . (6) The installation of stationary compactors and the Grantry cranes are ned to be completed | 75 | 91 | 1)The construction of Aruwakkalu Sanitary Landfill is Completed, 2) The 82% of construction of Aruwakkalu Transfer station facility including Transfer station, railway line connectivity is completed. . 3) The commissioning of leachate treatment plant at Aruwakkalu is completed. 4) 81% of Construction of Kelaniya Transfer Station facility including leachate treatment plant, deodarization system, railway connectivity, culverts, bridges management building etc is completed . | 90 | 1)Inundation of the Leachate Treatment plant at Aruwakkalu the night of 8th November 2021. 2) ii. Restriction imposed by RDA for the movement of the heavy vehicles over the damaged bridge 9/2 in Puttalam Mannar road being damaged due to the heavy rain experienced on 08th November 2022. 3)iii. The Pandemic situation due to the Covid-19 caused massive impact on the construction owing to stoppages of work and slowdown in work due to restrictions imposed by the health authorities. 4)iv. Delayed the supply and installation of 11Kv Feeding Arrangement for Kelaniya Transfer Station by the LECO Projects (Pvt) Ltd. 4)v. Contractor’s Payment delays due to the lack of financial provisions has also compelled the Contractor to slow down the work and reduce the number of workers in the site which directly affected the construction progress.
[17 empty] | Complete the Purchasing of , 94 Container boxes and 34 Container carrier wagons |  |  |  |  | 1.) The 04 Nos. Locomotives received from Dongfang Electric International Corporation were unloaded at the Railway premises. 96 Container boxes- All boxex recived and unloaded at Kelaniya site. 34 Nos Container Carrier Wagons- ., Since long time taken to finalized the design specifications of the container carrier wagons by the contractor, said contract is terminated. Accordingly, now planning to use existing railway wagons which belongs to SLR after making few developments. This is a Temporary solution. However, in response to letter sent by this ministry to the Secretary of the Transport Ministry to the requesting cost proposal for the manufacturing of New Railway wagons by the SLR, SLR sent thir cost proposal to manufature 17 Nos Container Carrier Wagons. Currently Cabinet memorandum is prepared and under reveiw. |  |  | 1.) The tenders was awarded to purchasing of 34 Nos Container Carrier Wagons and 94 Nos Container Boxes to M/S BESCO Limited and M/s Dongfang Electric International Corporation respectively.. 2.) The 04 Nos. Locomotives received from Dongfang Electric International Corporation were unloaded at the Railway premises.. 3)96 Container boxes- All are received to country and unloaded at Kelaniya site. 4) 34 Nos Container Carrier Wagons- ., Since long time taken to finalized the design specifications of the container carrier wagons by the contractor, said contract is terminated. Accordingly, now planning to use existing railway wagons which belongs to SLR after making few developments. However, in response to letter sent by this ministry to the Secretary of the Transport Ministry to the requesting cost proposal for the manufacturing of New Railway wagons by the SLR, SLR sent their cost proposal to manufacture 17 Nos Container Carrier Wagons. According cabinet memorandum is prepared and currently it is under review.. |  | Submission of cabinet memorandum to funds transfer to SLR is in progress.
Bills in hand contain in contractor pyment for the period of October 2020 to May 2021 amount Rs Mn 919.91

## UDA - Off Budget
State Ministry of Urban Development, Waste Disposal and Community Cleanliness
Pysical & Financial Progress Development Pojects & Progress as at 30th June 2022
SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Reasons for not achieving financial and physical targets | DPMM Comments
[8 empty] | Allocation 2022 Rs.Mn | Financial targets and progress- 2022 ( as at 30.06.2022) |  |  |  |  | Cumulative expenditure (as at 30.06.2021) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [7 empty] | Cumulative Physical Progress (as at 30.06.2021)
[9 empty] | Expenditure target | Imprest requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  | Original | Current (if revised during implementation) | Original | Revised (if extended) | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%) ( B) |  |  |  | Description | as % of (B) | Cumilative physical target (%) as at 30.06.2022 | Description | as % of overall taeget (% of A)
[18 empty] | Q-1 | Q-2 | Q-3 | Q-4
| -1 | -2 | -3 |  | -4 |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 |  | -23 | -24 | -25
1 | Piling Work - Car Park Narahenpita | Narahenpita | 147 |  | 2020.11.19 | 17.04.2021 | UDA | 96 | 96 |  |  | 95.8 |  | 95.8 | Completion of sub structure | 10 |  | 90 | 90 | - | - | Completion of sub structure | 100 | 90 | Completion of sub structure | 100 | -
| Design & Construction of Super structure of Multi Storied Car Park & Mixed Development project at Narahenpita | Narahenpita | 989 |  | 2021.06.29 | 2022.06.28 | UDA | 324 | 324 |  |  | 213 | _ | 213 | Priliminary works | 29 | Pile up concreteing | 26 | 56 | 71 | - | Slab concreting | 44.6429 | 56 | Ground floor slab 97% first floor sleb 92% second floor sleb 80% theired floor sleb 50% forth floor 05% | 54 | Delaying due to Financial and Material supply issues
2 | Piling Work - Car Park Fort | Fort | 139 |  | 2020.10.06 | 2021.03.04 | UDA | 50 | 50 |  |  | 67.6 |  | 67.6 | Completion of sub structure | 20 |  | 80 | 80 | - | - | Completion of sub structure | 100 | 80 | Completion of sub structure | 100 | -
| Design & Construction of Super structure of Multi Storied Car Park & Mixed Development project at Colombo Fort | Fort | 1565 |  | 2021.07.25 | 2023.01.26 | UDA | 629 | 629 |  |  | 360.13 | _ | 360.13 | Preliminary works | 20 | Additional pilling | 11 | 29 | 43 | 79 | Fist and second floor selb | 17.2414 | 29 | Fist and second floor selb 90% and Third and Forth floor 65% fisrt to second floor ramp casted | 25 | Delaying due to Financial and Material supply issues
3 | REFURBISHMENT OF 80 CLUB OF COLOMBO. | Indipendence | 412 |  | 2020.11.18 | 2021.11.30 | UDA | 439 | 439 | _ | _ | 401 | _ | 401 | Completion of Building | 40 | Structural work | 50 | 60 | - | - | Completed | 100 | 60 | Completed | 100 | -
4 | REFURBISHMENT OF GAFFOOR BUILDING AT COLOMBO FORT | Colombo Fort | 3000 |  | 2020.09.08 | 2022.06.31 | UDA | 620 | 620 |  |  | 740 | _ | 740 | Structural works | 45 | Completion | 20 | 55 | - | - | Structural works | 42 | 55 | Civil work and interior work | 68 | Delaying due to payment & Materially scarcity
5 | PROPOSED HIGH - RISED OFFICE COMPLEX AT SETHSIRIPAYA STAGE III | Baththaramulla | 16700 |  | 2021.02.10 | 2024.07.24 | UDA | 8000 | 8000 |  |  | 5363 | 640 | 6003 | Completion of High Rise Office Complex | 6 | Structural works of Twelveth Floor | 5.8 | 7 | 11.5 | 19.5 | Structural works of Upper Ground Floor Slab | 100 | 7 | Substructure 100% Lower Ground Floor Slab 100% Upper Ground Floor Slab 100% First Floor Slab 100% | 13

## MIHP - Off Budget
State Ministry of Urban Development, Waste Disposal and Community Cleanliness
Physical and Financial Progress of Development Projects and Programs as at 30th June 2022
SN | Project | Location | Total Cost (Rs.Mn.) |  | Project period From To (Month/ Year) |  | Funding Source | Financial Targets and Progress (Rs.Mn.) | [6 empty] | Physical Targets and Progress | [11 empty] | Remarks
[8 empty] | Allocation 2022 (Rs.Mn) | Financial targets and progress- 2022 ( as at 30.06.2022 |  |  |  |  | Cumulative expenditure (as at 30.06.2022) | Overall physical target (expected outputs) of the project (A) | Cumulative physical progress as at December 2021 as % of (A) | Physical targets and progress -2022 | [7 empty] | Cumulative Physical Progress (as at 30.06.2022)
[9 empty] | Expenditure target | Imprest requested | Imprest Received | Actual Expenditure | Bills in hand |  |  |  | Targets |  |  |  |  | Progress (as at 30.06.2022)
|  |  | Original | Current (if revised during implementation) | from | to | [10 empty] | Descriptive target for 2022 | Cumulative quarterly targets (%) ( B) |  |  |  | Description | as % of (B) | Cumulative Physical Target (%) (as at 30.06.2022 | Description | as % of overall target (% of A)
[18 empty] | Q-1 | Q-2 | Q-3 | Q-4
| -1 | -2 | -3 |  | -4 |  | -5 | -6 | -7 | -8 | -9 | -10 | -11 | -12 | -13 | -14 | -15 | -16 | -17 | -18 | -19 | -20 | -21 | -22 | -23 | -24 | 25
4 | "Oval View" Borella | Borella | 4499.2 | 4949.12 | 10/5/2016 to 9/5/2019 | 14/8/2020 | Pre Sell | 487.48 | 487.48 |  |  | 460 |  | 5772 | 100 | 100 | Completion of the Project | - | - | - | - | Completed | 100 | Completed | Completed | 100
1 | Viyathpura" Weera Mawatha | Pannipitiya | 5327.5 | 5860.25 | 2017-06-15 | 13/7/2022 | Pre Sell | 1705.8 | 1039.6 |  |  | 688 |  | 3854 | 72 | 70 | Completion of the Project | 15 | 20 | 25 | 30 | Construction in process. | 20 | 40 | Construction in process. | 78 | Delayed due to delay of approving the Reviced Payment Scheame
2 | Green Arcade | Kottawa | 3699.13 | 4069.043 | 2017-10-16 | 13/ 7/ 2022 | Pre Sell | 2814.2 | 1105 |  |  | 217 |  | 918 | 64 | 61 | Completion of the Project | 19 | 25 | 32 | 39 | Construction in process. | 25 | 36 | Construction in process. | 70 | Delayed due to delay of approving the Reviced Payment Scheame
3 | Eliot Place | Borella | 9368 | 10304.8 | 2020-10-19 | 18/12/2023 | Pre Sell | 2844.3 | 953.5 |  |  | 1129 |  | 1171 |  | 12 | Completing 40% of the overall project | 6 | 15 | 20 | 28 | Construction in process. | 15 | 53 | Construction in process. | 20 | Elliot Recidencies also not achieved the Expenditure Targets due to Covid Pandemic
| Note: | Viyathpura and Green Arcade projects not achieved the Expenditure Targets due to delay of approving the Reviced Payment Scheame
Elliot Recidencies also not achieved the Expenditure Targets due to Covid Pandemic