## Summery
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition (Rs. 1200Mn.)
1 | Implementation of Megapolis Development project and Land Acquisition (Rs. 1200Mn.)
1.1 | Aero City Development Project | 170.75
1.2 | Western Region Administrative Cities Development Project | 74.15
1.3 | Tech City Development Project | 17.5
1.4 | Western Region Transport city Development Project | 317.6
1.5 | Sukitha Purawara | 400
1.6 | Maritime City Development Project | 220
Total |  | 1200

## Aero City 170.75
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Project: Expenditure Proposal 143 - Development and Creating Modern Sustainable Urban Hub (170.75Mn) - Aero City Development Project
# | Proposed Activity | Allocation (Rs. Mn) | Date of Commencement | Date of Completion | 2018 Financial Targets (Rs.Mn) |  |  |  | 2018 Physical Targets (%) |  |  |  | Output or Indicator | Implementing Agency | Responsible By | Contact No. | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
BIA Gate Way Project at Katunayake
1 | Land clearance | - | 2017-10-19 | 2018-06-30 | - | - | - | - | 15% | 25% | 35% | 25% | Deed document | Urban Development Authority (UDA) | Aero city Development Project (ADP) | 0715885050, 0770485114, 0714409968, 0775361475 | Market value of land is Rs. 640Mn. Fund request for Q2 Rs. 110Mn. and Q3 Rs. 50Mn .(25% of the land value) (Lands acquisition is in progress)
2 | Technical Studies/assessments/relevant documents | 10 | 2018-01-25 | 2018-06-30 | 5 | 5 | - | - | 50% | 50% | - | - | Surveying Plan, Relevant Tec, Report | UDA/ADP | ADP |  | Subject to land clearance
3 | Design development and project consultancy | 57 | 2018-07-01 | 2018-12-01 | - | - | 22 | 35 | 20% | 30% | 30% | 20% | Contract Documents and Drawings
Sub Total |  | 67 |  |  | 2018 Financial Targets (Rs.Mn) Q1: 5; 2018 Financial Targets (Rs.Mn) Q2: 5; 2018 Financial Targets (Rs.Mn) Q3: 22; 2018 Financial Targets (Rs.Mn) Q4: 35
Logistics and Business Park Project - Ekala
1 | Land Acquisitions and compensation | - | 2017 March | 2018 December | - | - | - | - | 25% | 25% | 25% | 25% | Deed document, consent letter | UDA/ADP | UDA/ADP | 0779387974, 0714409968, 0775361475 | Land value is Rs. 2600Mn. and it is subjected to co-occurrence of Ministry of Finance & Mass Media ( Sri Lanka Broadcasting Corporation). Funds requirements for Q2 is Rs. 650Mn.(25% of land value). Q4; Rs. 1300Mn (50% of land value). Balance payment carried to 2019
2 | Technical studies/assessments/relevant documents | 10 | 2018 March | 2018 Sep. | - | 5 | 5 | - | 25% | 50% | 25% | - | Traffic Impact Assessment, drainage plan reports, survey plan, EIA Report and relevant documents |  |  |  | Subjected to land clearance, consent and compensation
3 | Detailed project design and implementation (Construction and management) | 40 | 2018 Sep | 2019 Sep | - | - | 25 | 15 | 15% | 20% | 30% | 35% | Value addition cluster, SME cluster, museum and public park, city hotel, convention center, mega mall, innovation center, parking facilities etc.… |  |  |  | Target project activity period is subjected to land clearance. Rs. 320Mn is required in 2018. Balance payment of Rs. 963Mn. Will be expected in 2019
Sub Total |  | 50 |  |  | 2018 Financial Targets (Rs.Mn) Q1: -; 2018 Financial Targets (Rs.Mn) Q2: 5; 2018 Financial Targets (Rs.Mn) Q3: 30; 2018 Financial Targets (Rs.Mn) Q4: 15
Airport Business City Project At Katana
1 | Development of Preliminary Master Plan | - | 2017-01-11 | 2018-06-04 | - | - | - | - | 100% | - | - | - | Master Planning Report | UDA | ADP/UDA | 0778558034, 0714409968, 0775361475
2 | Detailing Infrastructure Plans / Socio-Economic Plan | 7.4 | 2018-01-01 | 2018-08-10 | 1 | 3.7 | 2.2 | 0.5 | 10% | 50% | 30% | 10% | Detail plans for gazette and implementation |  | ADP
3 | Stakeholder consultation | 0.6 | 2018-01-01 | 2018-08-10 | 0.2 | 0.2 | 0.2 | - | 10% | 50% | 40% | - | Detail plans with implementing agencies contribution
4 | Planning approvals and gazette as a main implementing arm | - | 2018-01-12 | 31/05/2019 | - | - | - | - | 15% | 25% | 25% | 35% | Need to follow UDA gazette shedule | UDA | ADP
5 | Marketing and Documentations | 7 | 2018-08-15 | 2018-12-31 | - | - | 3 | 4 | - | - | 50% | 50% | Marketing documents, 3D architectural visuals, graphic designs, media publications | ADP/UDA | ADP
6 | Start first phase planning and detail designs | 5 | 2018-01-01 | 2018-08-10 | _ | _ | 3 | 2 | 10% | 10% | 30% | 50% | Structural Engineer designs for road improvements, fiber optic installation consultation, capacity improvement of Local Authority | RDA, UDA, LA
Sub Total |  | 20 |  |  | 2018 Financial Targets (Rs.Mn) Q1: 1.2; 2018 Financial Targets (Rs.Mn) Q2: 3.9; 2018 Financial Targets (Rs.Mn) Q3: 8.4; 2018 Financial Targets (Rs.Mn) Q4: 6.5
Aero city Master Plan Preparation/Finalization
1 | Conducting stakeholder meetings, surveys and field visits, public hearings | 10 | 2018 January | 2018 December | 2 | 4 | 2 | 2 | 25% | 25% | 25% | 25% | Survey reports | ADP | ADP | 0778558034, 0714409968, 0775361475
2 | Consultancy services technical evaluation, detailed master plan preparation and analytical works | 23.75 | 2018 January | 2018 December | 6 | 6 | 7.75 | 4 | 10% | 40% | 30% | 20% | Relevant technical reports | ADP/UDA | ADP/UDA
Sub Total |  | 33.75 |  |  | 2018 Financial Targets (Rs.Mn) Q1: 8; 2018 Financial Targets (Rs.Mn) Q2: 10; 2018 Financial Targets (Rs.Mn) Q3: 9.75; 2018 Financial Targets (Rs.Mn) Q4: 6
Grand Total |  | 170.75 |  |  | 2018 Financial Targets (Rs.Mn) Q1: 14.2; 2018 Financial Targets (Rs.Mn) Q2: 23.9; 2018 Financial Targets (Rs.Mn) Q3: 70.15; 2018 Financial Targets (Rs.Mn) Q4: 62.5

## Admin City 74.15
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Project: Implementation of Megapolis Development Project and Land Acquisition (Rs.74.15Mn) - Western Region Administrative Cities Development Project (Expenditure Proposal 143)
# | Proposed Activity | Allocation (Rs. Mn) 2018 | Date of Commen.t | Date of Compl.n | Financial Targets 2018 (Rs.Mn) |  |  |  | Physical Targets 2018 (%) |  |  |  | Output or Indicator | Implementing Agency | Responsible By | Contact No. | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Proposed High Rise Mixed Development (Sethsiripaya - Stage IV) at Denzil Kobbekaduwa Mawatha, Battaramulla (PPP Project) | 5.4 | 2018 | 2021 | - | 1.8 | 1.8 | 1.8 | 15% | 30% | 30% | 25% | Construction of G+39 Storied building at proposed location with total floor area of 68,000m2. Out of it 28350m2 office area will be allocated for government office relocation program | Western Region Administrative Cities Development Project | Project Director | 773793818
2 | Proposed High Rise Mixed Development at Junction of Kaduwela Road, Battaramulla (Integrating to Proposed Multi Modal Transport Light Rail Transit (LRT) Station at Junction) (PPP Project) | 4 | 2018 | 2021 | - | - | 2 | 2 | 10% | 20% | 35% | 35% | Construction of 40+ storied building with minimum of 10,445 m2 floor are and integrating Multi Model Transport Center at Battaramulla Junction Provide minimum of 10445m2 floor area for government office relocation
3 | Proposed Multi Model Transport Hub (MMTH) at Pettah (PPP Project) - Fea | 8 | 2018 | 2019 | - | - | 4 | 4 | 20% | 25% | 25% | 30% | Feasibility study to centralize the Colombo MMTH hub of railways, buses, and other modes of transportation (including LRT) to a single place and integrating Commercial activities by creating the MMTH and identify potencial commercial, residencial and industiral activities in CDB of Pettah.
4 | Soft and hard landscaping improvements for existing routes and upcoming road networks in Administrative City Limit (Consolidated Fund) | 0 | 2018 | 2019 | - | 0 | 0 | 0 | - | - | 50% | 50% | • Identification of landscaping development in Administrative City of Sri Jayawardanapura • Complete landscape designs for existing routes and upcoming routes and entertainment activities • Transform pleasing environment for Administrative City |  |  |  | NPD approval has not given.Hence Budget was Transferred to road project
5 | Administrative City a Smart City in 2020 (PPP Project) | 2 | 2018 | 2020 | 0.5 | 0.5 | 0.5 | 0.5 | 25% | 25% | 25% | 25% | To bring systematic changes and development processes into the administrative city, which will ensure that the inhabitants of the City become a part of socio-economic development of the country while maintaining high levels in quality of life.
6 | A solar energy proposal for the Administrative City: generate 10MW solar electricity power using roof surfaces and premises of government building at administrative capital – Sri Jayewardenepura, Kotte (PPP Project) | 3.75 | 2018 | 2019 | - | 0.5 | 1.25 | 2 | 20% | 25% | 25% | 30% | Intended to generate and supply of sustainable (green) energy (Minimum of 5 MW) to national electricity grid utilizing existing building roof tops and open spaces of government premises in the Administrative City
7 | New road development connecting Battaramulla Junction and Polduwa Road, proposed bus terminals and facilitate LRT line in the center-median Construction of connecting road of Battaramulla junction and Polduwa Road (Consolidated Fund) | 21 | 2018 | 2019 | 4 | 5 | 4 | 8 | 15% | 25% | 30% | 30% | Connecting Battaramulla Junction and Polduwa Road &rearrange effective traffic arrangement.
8 | Offices for parliamentary related activities, constitutional commissions, foreign missions and related amenities at land originally allocated for the Prime Minister’s Office and residence (Consolidated Fund) | 25 | 2018 | 2020 | - | 8 | 12 | 5 | 10% | 30% | 30% | 30% | This will be by fulfilled the building requirement of Parliamentary affairs and office requirements of Administrative City
9 | Proposed CHINA – SRI LANKA MUSEUM at KOTTE RAMPART | 2 | 2018 | 2019 |  |  | 1 | 1 |  | 25% | 25% | 50% | To Create a network of governments, community, business and cultural organisations that will bring cultural understanding between countries and communities through cultural exchange
10 | Construction of proposed 108 Housing Units at Palanwatta - Pannipitiya for Veteran Artists in Sri Lanka | 3 | 2018 | 2019 |  |  | 1 | 2 |  | 25% | 25% | 50% | 108 houses for Veteran Artists in Sri Lanka of UDA Land at Palanwatta , Pannipitiya. The other purpose of this housing scheme is to reach the Colombo city as fast as possible.
Grand Total |  | 74.15 |  |  | Financial Targets 2018 (Rs.Mn) Q1: 4.5; Financial Targets 2018 (Rs.Mn) Q2: 15.8; Financial Targets 2018 (Rs.Mn) Q3: 27.55; Financial Targets 2018 (Rs.Mn) Q4: 26.3

## Tech City 17.50
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Project : Expenditure Proposal 143 - Development and Creating Modern Sustainable Urban Hub (Rs.17.50Mn) - Western Region Tech City Development Project
# | Proposed Activity | Allocation - 2018 (Rs.Mn) | Date of Commenc.t | Date of Completion | Financial Targets (Rs.) |  |  |  | Physical Targets (%) |  |  |  | Output - 2018 | Implementing Agency | Responsible by | Contact Tel. No. | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Market Positioning | 5 | Jan.2018 | Dec.2018 | 3 | 0.25 | 1.5 | 0.25 | 60% | 5% | 30% | 5% | 02 TV programmes/ providing 500no. Brochurs/ providing promotional materials | Tech City Development Project | Project Director (TCDP) | 011 2870566 | Budget allocation will be from capital cost
2 | Consultancy | 10 |  |  | 2.5 | 2.5 | 2.5 | 2.5 | 25% | 25% | 25% | 25% | 05 environmental studies for roads/ services of the feasibility study
3 | Preliminary activities | 2.5 |  |  | 0.625 | 0.625 | 0.625 | 0.625 | 25% | 25% | 25% | 25% | Soil investigation - 02 bridges/ publish consultancy - 05/ publish contracts - 02 survey roads - 16km
Total |  | 17.5 |  |  | Financial Targets (Rs.) Q1: 6.125; Financial Targets (Rs.) Q2: 3.375; Financial Targets (Rs.) Q3: 4.625; Financial Targets (Rs.) Q4: 3.375

## Transport 317.60
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Project :Expenditure Proposal 143 - Development and Creating Modern Sustainable Urban Hub - (Rs. 317.60Mn) - Western Region Transport city Development Project
No. | Proposed Activity | Allocation(Rs.) Mn. | Date of Commencement | Date of Completion | Financial Targets 2018 (Rs.) Mn. |  |  |  | Physical Targets 2018 (%) |  |  |  | Output or Indicator | Implementing Agency | Responsible by | Contact Tel. No. | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Introducing of Rapid Transist System | [13 empty] | Project Director, TDP,Ministry of Megapolis and Western Development | 0112870751 | Project has been commenced
1.2 | Pre Feasibility and Feasibility Study of LRT line1,line2,line3,line5,line6,line7 | 202.48 | 2018-01-01 | 2018-11-01 | 81 | 0 | 81 | 40.48 | 25% | 25% | 25% | 25% | Feasibility Study Report and RFP Document for implementation of the project mentioned in 1.1 on PPP basis. | Transport Development Project
Sub Total |  | 202.48 |  |  | Financial Targets 2018 (Rs.) Mn. Q1: 81; Financial Targets 2018 (Rs.) Mn. Q2: 0; Financial Targets 2018 (Rs.) Mn. Q3: 81; Financial Targets 2018 (Rs.) Mn. Q4: 40.48
2 | Inland Water Based Passenger Transport System (IW1 & IW 2) | [13 empty] | Project Director, TDP,MMWD | 0777482069 | RFP will be submitted by the Shortlisted bilder . Estimated Cost is Rs. 125 mn
2.1 | IW 1- Battaramulla - Wallawatta Route (PPP) | [11 empty] | Opening up of a ferry based passenger transportation system from Wellawattha to Battaramulla on PPP basis. | TDP /Sri Lanka Land Reclamation and Devolopment corperationLRDC
2.1.1 | Construction of three Jetties at Open University near 176 route, Havelock City and Battaramulla behind Sethsiripaya | 112.94 | 2018-01-01 | 2018-11-01 | 10 | 40 | 62.94 | - | 25% | 25% | 25% | 25% | Completion of 3 jetties at Wellawattha, Open University, Battharamulla and 3 other locations to facilitate ferry service using GOSL funds. | TDP /SLRDC
2.2 | IW 2 - Fort to Union Place along Berei Lake | PPP | 2018-01-01 | 2018-11-01 | - | - | - | - | 10% | 20% | 40% | 30% | Opening up of a ferry based passenger transportation system in the Berea Lake aiming passenger transportation as well as recreational services. | TDP /SLRDC
Sub Total |  | 112.94 |  |  | Financial Targets 2018 (Rs.) Mn. Q1: 10; Financial Targets 2018 (Rs.) Mn. Q2: 40; Financial Targets 2018 (Rs.) Mn. Q3: 62.94; Financial Targets 2018 (Rs.) Mn. Q4: 0
4 | Facilitating Services
4.1 | Consultancy services for the flexi hours pilot project in Battaramulla administrative city | 2.18 | 2018-01-01 | 2018-03-01 | 2.18 | - | - | - | 100% | - | - | - | Introduce "Flexi-Hours" in Battharamulla area and later expand it to other suitable areas of the Country. | TDP | Project Diretor, TDP,MMWD | 112870751 | Project has been commence
Sub Total |  | 2.18 |  |  | Financial Targets 2018 (Rs.) Mn. Q1: 2.18; Financial Targets 2018 (Rs.) Mn. Q2: 0; Financial Targets 2018 (Rs.) Mn. Q3: 0; Financial Targets 2018 (Rs.) Mn. Q4: 0
| Total | 317.6 |  |  | Financial Targets 2018 (Rs.) Mn. Q1: 93.18; Financial Targets 2018 (Rs.) Mn. Q2: 40; Financial Targets 2018 (Rs.) Mn. Q3: 143.94; Financial Targets 2018 (Rs.) Mn. Q4: 40.48

## sukitha new 400
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Expenditure Proposal 143 - Development and Creating Modern Sustainable Urban Hub (Rs. 400Mn) - Sukitha Purawara and Sihilal Dahana
# | Proposed Activity | Allocation (Rs Mn) | Date of Commencement | Date of Completion | Financial Targets 2018 (Rs.Mn) |  |  |  | Physical Targets 2018 (%) |  |  |  | Output Indicator | Implementing Agency | Responsible By. | Contact | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Auxiliary Infrastructure Elements as Pre-requisite for Megapolis Development and Upgrading of Socio-Economic-Cultural Ecosystem in Western Region (Sukitha Purawara) | [11 empty] | No.of projects completed | District Secretaries (Colombo /Gampaha /Kalutara) | Additional Secretary (Megapolis) | 112864483 | With Sihilal Dahana projects
1.1 | Fund released for bills in hand | 119 | 2018-01-01 | 2018-12-31 | 100 | 19 | - | - | 60% | 40% | - | -
1.2 | Approval for continuation projects | - |  |  | - | - | - | - | 90% | 10% | - | -
1.3 | Funds releasing for continuation projects | 281 |  |  | 10 | 211 | 60 | - | 3% | 90% | 7% | -
Total |  | 400 |  |  | Financial Targets 2018 (Rs.Mn) Q1: 110; Financial Targets 2018 (Rs.Mn) Q2: 230; Financial Targets 2018 (Rs.Mn) Q3: 60; Financial Targets 2018 (Rs.Mn) Q4: -

## policy page
Ministry of Megapolis and Western Development
Policy :
Establishing large urban cities to facilitate the improvement of investment climate to attract business, industries, Foreign Direct Investment by Assuring sustainable city development
Strategies :
* Developing Colombo City and the Western Region as a Megapolis centering Colombo City as the main hub
* Potential urban cities to be developed as Mega Cities interlinking with emerging and the economic flow of the prime commercial hub (Western Region)
Key Performance Indicators (KPIs)
* Increasing the average speed of vehicles or reduction of travel time of passengers with in Western Region

## maritime City 220
Ministry of Megapolis and Western Development
ACTION PLAN - 2018
Implementation of Megapolis Development project and Land Acquisition
Expenditure Proposal 143 - Development and Creating Modern Sustainable Urban Hub (Rs.220 Mn) - Maritime City Development Project
# | Proposed Activity | Allocation for the Project (Rs. Mn) | Date of Commencement | Date of Completion | Financial Targets for 2018 (Rs. Mn) |  |  |  | Physical Targets for 2018 (%) |  |  |  | Output | Implementing Agency | Responsible by | Contact Tel. Nos | Remarks
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project-Development of recreational beach from Colpetty to Dehiwala canal outlet
1 | Project Initiation | - | 2017-02-13 | 2017-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project identification | Ministry of Megapolis and Western Development (Maritime City Development Project) | Project Director | 0716886564 | Completed
2 | Project Approval | - | 2017-02-13 | 2018-02-28 | 0 | 0 | 0 | - | 100% | - | - | - | Project identification |  |  |  | Completed- Cabinet memo for awarding feasibility study to NARA
3 | Feasibility Study(including EIA) and supplementry EIA | 135 | 2017-09-27 | 2018-12-31 | 0 | 35 | 50 | 50 | 12% | 13% | 35% | 40% | Approved report |  |  |  | In progress. The actual date of completion will be 28/02/2019. If required, supplementary EIA will be conducted and will be completed by 31/08/2019. 80% of total task is considered for 2018.
4 | Project Procurement (EoI and RfP) Process | - | 2018-01-02 | 2018-12-31 | 0 | 0 | 0 | 0 | 25% | 25% | 25% | 25% |  |  |  |  | In progress.
5 | Commencement of Construction | - | - | - | 0 |  |  |  | 0 | 0 | 0 | 0 | Project deliverables |  |  |  | Yet to be started.The actual date of commencement will be 01/03/2019 and completion will be 31/08/2021.
6 | Relocation of Housing, Restaurants & Government Institutions(including temporarary relocation) | 50 | 2018-09-03 | 2018-12-31 |  | 0 | 25 | 25 | 6% | 19% | 50% | 25% |  |  |  |  | Commencement of works of GOSL scope is to be started before the private partner (Investor) commence construction. 30% of total task is considered for 2018. The actual date of completion will be 20/03/2020
| Sub Total | 185 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 35; Financial Targets for 2018 (Rs. Mn) Q3: 75; Financial Targets for 2018 (Rs. Mn) Q4: 75
Design and Construction of recreational beach area from Colpetty to Dehiwala (By Investor)
| Design and constructions of perched beach inclusive of marine structures (breakwater and revetments) from Colpetty to Dehiwala – approx. 100 ha (including creation of a safe bathing area in the proximity of Bambalapitiya) | 16500 | 2019-09-01 | 2021-08-31 | 0 | 0 | 0 | 0 | - | - | - | - |  | MM & WD (MCDP) | Project Director | 716886564
| Landscaping the existing Land /beach stretch along with the perched beach.[inclusive root bowling of trees, street lighting ,water supply, drainage/sewage system | 300 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Connection & extension of 14 drainage outlets including Wellawatta canal outlet & Dehiwala canal outlet towards sea | 150
| Preparation and leveling of land area for development | 15
| Construction of car park, wash room complex each near Colpetty ,Bambalapitiya & Wellawatta railway stations | 150
| Building of a walking path | 30 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Construction of beach boutiques along the walking path [inclusive concrete chairs & garbage collection system / bins etc.] | 10 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Construction of separation wall to isolate third/fourth rail track & beach area | 150 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Building of a pier incorporating the ship model | 150 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Extended pier to be created near Colpetty towards sea (to facilitate safe small boat anchorage and launching of boat service for the intended wreck diving sites) | 150 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Small boat service between Wellawatta to Colpetty and Wellawatta to Nawala could be commenced with the participation of fishermen in area | 75 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Amusement park establishment | 750 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Aquarium establishment | 300 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| establishment of Turtle park | 15 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Procurement and consultancy services | 900 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Total Investor Commitment | 19645 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
| Contingencies 10% for Investor | 1964.5 |  |  | 0 | 0 | 0 | 0 | - | - | - | -
Project: Port related logistic development at Bloemendhal
1 | Project Initiation | - | 2017-02-13 | 2017-12-29 | - | - | - | - | 25% | 25% | 25% | 25% | Project identification | MMWD (WRMCDP) | Project Director | 0716886564 | Completed
2 | Project Development | 35 | 2018-01-02 | 2018-12-31 | - | 10 | 10 | 15 | 10% | 30% | 40% | 20% | By the SLPA/ WRMCDP |  |  |  | In progress
3 | Project Approval (by the Cabinet) | - | 2018-01-02 | 2018-02-28 | - | - | - | - | 100% | - | - | - | Approved project |  |  |  | In progress
3.1 | Preparation and submission of joint cabinet paper | [15 empty] | Completed | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
3.2 | Approval for joint cabinet paper | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
4 | Project Procurement Process-phase I | - | 2018-03-02 | 2018-12-31 | - | - | - | - | - | 30% | 40% | 30% | Selected Investor |  |  |  | In progress. 50% of total task is considered for 2018
4.1 | Preparation of RFP document and Notice for the project | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
Publish RFP Notice, receive proposals, proposal evaluation and recommend the successful bidder | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
Contract negotiation & Award of Contract to the successful investor | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
4.2 | Consultancies, surveys, engineering investigations, Feasibility & EIA studies etc., and preparation of related reports and other documentation | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
4.3 | Development and Implementation of Public Recreation Enhancement Strategy and implementation of Logistic promotions / related programs at Bloemendhal & the logistic community | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
4.4 | Public / Logistic Awareness Programs for various groups and production of materials (Audio/Video and printed media material and Media publication) | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
4.5 | Local & Foreign Training and Capacity Building on Logistic parks & Logistic related subjects | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
5 | Commencement of Construction | - | 2018-10-01 | 2018-12-31 | - | - | - | - | - | - | - | 100% | Project deliverables |  |  |  | Yet to be started.10% of total task is considered for 2018. The actual date of completion will be 31/12/2020.
Monitoring | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Financial Targets for 2018 (Rs. Mn) Q4
Progress meetings | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Financial Targets for 2018 (Rs. Mn) Q4
6 | Relocation of Housing, and Government Institutions | - | 2018-09-30 | 2018-12-31 | - | - | - | - | - | - | 25% | 75% | Construction commencement |  |  |  | 20% relocations are already done by UDA by now. SLPA shall settle the cost to UDA for the relocation.The actual date of completion will be 30/04/2020.
| Sub Total | 35 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 10; Financial Targets for 2018 (Rs. Mn) Q3: 10; Financial Targets for 2018 (Rs. Mn) Q4: 15
Project: ECT- East Container Terminal Development
1 | Project Initiation | 0 | 2018-01-02 | 2018-01-31 | 0 | 0 | 0 | 0 | 100% | - | - | - | Additional deep draft berthing facilities for Colombo Port | MM & WD (MCDP) | Project Director | 0716886564 | Completed
2 | Project Approval | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0 |  |  |  |  | On progress.
3 | Feasibility Studies | 0 | 2018-03-01 | 2018-06-01 | 0 | 0 | 0 | 0 | 5% | 95% | - | - |  |  |  |  | On progress.
4 | Procurement Process | 0 | 2018-06-02 | 2018-12-31 | 0 | 0 | 0 | 0 | - | 15% | 55% | 30% |  |  |  |  | On progress. 75% of total task is considered for 2018. The actual date of completion will be 01/03/2019.
| Sub Total | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0
Project: Logistic Corridor Development
1 | Project Initiation | 0 | 2018-01-02 | 2018-06-15 | - | - | - | - | 25% | 75% | - | - | Infrastructure for Logistic | MM & WD (MCDP) | Project Director | 0716886564 | In progress
2 | Project Approval | 0 | [14 empty] | Yet to be started. | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Financial Targets for 2018 (Rs. Mn) Q4
3 | Detail Design and Master Plan | 0 | 2018-05-01 | 2018-12-31 | - | 0 | 0 | 0 | - | 30% | 30% | 40% |  |  |  |  | Yet to be started.80% of total task considered for 2018. The actual date of completion will be 31/01/2019.
| Sub Total | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0
Project: Passenger Ship Terminal Development at Bandaranayke Quay (BQ)
1 | Project Initiation | 0 | 2018-01-02 | 2018-03-31 | - | - | - | - | 100% | - | - | - | Berthing facilities for Passenger Ships | MM & WD (MCDP) | Project Director | 0716886564 | Completed
2 | Project Approval | 0 | [14 empty] | Yet to be started. | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Physical Targets for 2018 (%) Q4
3 | Feasibility Studies | 0 | 2018-05-02 | 2018-10-01 | - | - | - | - | - | 25% | 35% | 40% |  |  |  |  | Yet to be started.
4 | Procurement Process | 0 | 2018-10-02 | 2018-12-31 | - | - | - | - | - | - | - | 100% |  |  |  |  | Yet to be started. 10% of total task is considered for 2018. The actual date of completion will be 01/07/2019.
| Sub Total | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0
Project: Logistic Park Welisara
1 | Project Initiation | 0 | 2018-01-02 | 2018-06-30 | - | - | - | - | 30% | 70% | - | - | Logistic infrastructure development | MM & WD (MCDP) | Project Director | 0716886564 | Completed
2 | Project Approval | 0 | [14 empty] | Yet to be started. | bar: Financial Targets for 2018 (Rs. Mn) Q1 to Financial Targets for 2018 (Rs. Mn) Q4
3 | Feasibility Studies | 0 | 2018-07-01 | 2018-12-31 | - | - | - | - | - | - | 50% | 50% |  |  |  |  | Yet to be started.
4 | Relocation |  | - | - | [12 empty] | Yet to be started. Actual date of commencement will be 01/01/2019 and completion will be 31/12/2019 | bar: Physical Targets for 2018 (%) Q1 to Physical Targets for 2018 (%) Q4
| Sub Total | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0
Project: Yacht Marina Development in Dikowita
1 | Project Initiation | 0 | 2018-02-05 | 2018-07-31 | 0 | 0 | 0 | 0 | 25% | 50% | 25% | - | Berthing facilities for Yachts | MM & WD (MCDP) | Project Director | 0716886564 | In progress
2 | Project Approval | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0 |  |  |  |  | Yet to be started.
3 | Feasibility Studies | 0 | 2018-08-01 | 2018-12-31 | 0 | 0 | 0 | 0 | - | - | 50% | 50% |  |  |  |  | Yet to be started.
4 | Procurement (RfP) | 0 | - | - | 0 | 0 | 0 | 0 | - | - | - | - |  |  |  |  | Yet to be started. The actual date of completion will be 31/03/2019.
| Sub Total | 0 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 0; Financial Targets for 2018 (Rs. Mn) Q3: 0; Financial Targets for 2018 (Rs. Mn) Q4: 0
| Grand Total | 220 |  |  | Financial Targets for 2018 (Rs. Mn) Q1: 0; Financial Targets for 2018 (Rs. Mn) Q2: 45; Financial Targets for 2018 (Rs. Mn) Q3: 85; Financial Targets for 2018 (Rs. Mn) Q4: 90