## Sheet1
MONITORING AND EVALUATION PLAN -2021
OFFICE FOR REPARATIONS
KEY OBJECTIVES
(a) To have a transparent system and procedures in place through a well defined policy and guideline for reparation regime by August 2021
(b) To address the issues and problems of aggrieved persons by implementing the policy and guideline
(c) To have an integrated and coordinated mechanism to ensure the compatibility of the activities undertaken by other organizations by December 2021
(d) To establish an efficient and updated information management system for evidence-based decision making by December 2021
(e) To ensure efficient service delivery to aggrieved persons through a monitoring mechanism
Problem | Solution | Outcome indicators | KPIs | Information to be collected | Data sources
Non availability of a Policy on granting reparations | Development of a Policy and guideline to operationalize the Reparation process | I. Cabinet approval obtained for the policy and guideline and being implemented ii. Approved policy and guideline are adhered in implementing the reparation process | All documents provided and facilitated in obtaining approval for Policy and guideline from the cabinet and Parliament and gazette by 2021 August. | Approval for the Policy and Guideline | i.Cabinet decisions ii. Gazette notification
Inadequate awareness on reparation regime | Create awareness among all stakeholders on Reparation Regime through a well-defined Awareness Strategy | i. Aggrieved persons know their rights ii. Complaints against reparation process reduced iii Reparation claims are processed through a transparent mechanism | No of stakeholders made aware on the reparation regime/ Increase in the receipt of completed reparation claim | Success statistics on awareness creation programmed | No. of reparation claims Attendance sheets of workshops No of leaflets distribution Feedback survey reports
Inadequate system and procedures in granting reparations | Establish transparent systems and procedures inline with the Policy and guideline through- Development of a Reparation Manual | i. Aggrieved persons are satisfied with reparation process | Grant Reparation Manual finalized and is used in entire reparation claim process by end of December. | Reach and success of the intervention Communities engaged in using the system | Feed back surveys Amount of grant reparation
Inadequate system and procedures in granting reparations | Establish transparent systems and procedures inline with the Policy and guideline through-Reparation Manual | i Reparation grants are awarded without a delay ii. Needs of aggrieved persons are addressed iii. Living standard of aggrieved persons improved | Increase in the number of reparation grants within the scheduled time without a delay | Qualitative data on success rate | Delivery schedule No of claims received
Social survey Focus group discussion Income generation reports
Problem | Solution | Outcome indicators | KPIs | Information to be collected | Data sources
Inadequate access to finance for aggrieved persons to improve living standards | Find alternative financing mechanisms for aggrieved persons | Access to finance for aggrieved persons ensured | Increase in number of aggrieved persons supported with special loan scheme at lending institutes | Amount of loan disbursed and repayment rates | Loan data from lending institutes
Psycho social problems leading to unhealthy and unhappy families | Design and conduct psycho social progarmmes for aggrieved persons based on a needs assessment | i. Living standards of the aggrieved persons improved ii. Psychosocial related problems in the community reduced | No. of aggrieved persons provided psycho social support | Reach and success of the intervention at the community level | Social survey Case studies Individual interviews
Duplication in reconciliation and reparation process | Create a coordination mechanism for better and integrated outcome | i. Duplication in reconciliation process minimized ii. Resource deficiency in reconciliation process minimized | i. An Inter Agency coordination mechanism is in operation to avoid duplication by September. | Joint initiatives | Meeting attendance and minutes Evaluation report on joint programmes
|  |  | ii. Public-private partnership mechanism on reparations in place avoiding duplications/maximizing resource use by end of September. |  | Feedback surveys on joint programmes Focus group discussions
Inadequate data and information for evidence-based decision making on reparation | A proper mechanism to collate data and information and make it available for decision making | i. Reparation and reconciliation efforts are taken based on evidences. ii. Updated data and information is available for decision making iii. Stakeholder satisfaction in reparation regime (can be conducted through regular feedback system) . | A website with updated information is launched and operated with real time data for OR | Service statistics such as ability to create reports, quick access to information, statistics usage in national reporting etc. | Live website observation Website hits
Inadequate data and information for evidence-based decision making on reparation | A proper mechanism to collate data and information and make it available for decision making | i. Reparation and reconciliation efforts are taken based on evidences. | i. Data fields and data needs identified and collected to feed into the database | Service statistics such as ability to create reports, quick access to information, statistics usage in national reporting etc. | Data collection sheets SRS and Old database
|  |  | ii. An Information Management System is available and in operation for decision making by end of December |  | Live IMS observation Reports created through the system Stakeholder feedback Central Bank Report Site sourcing by International agencies
Problem | Solution | Outcome indicators | KPIs | Information to be collected | Data sources
Inadequate data and information for evidence-based decision making on reparation | A proper mechanism to collate data and information and make it available for decision making | ii. Updated data and information is available for decision making | iii. User friendly access to information system is available at OR by December. | Service statistics such as ability to create reports, quick access to information, statistics usage in national reporting etc. | User feedback survey Statistical analysis No of hits to site
|  | iii. Responding time to reparation claims reduced | iv. Online reparation claim system is introduced to stakeholders to create awareness among aggrieved persons |  | Report on number of online claims Feedback surveys
Non availability of a M & E system within OR to monitor performance | Develop and assign KPIs to staff and monitor through the M & E Plan | i. Efficient service delivery is ensured for aggrieved persons | Targets assigned to staff were completed as planned (individual KPIS will be assigned int he Activity Plan) | Performance improvement records | Regular progress review reports Number of claims handled and processed
|  | ii.Staff performance are ensured in reaching OR objectives | Timely remedial actions taken in addressing reparation grievances |  | No of issues received and addressed with proper solution
|  | iii.OR staff understands the OR regime and equipped with required knowledge to serve aggrieved persons i. Results based service delivery is established | Reparation activities were coordinated without duplication. |  | No. of training provided Feedback survey from stakeholders and aggrieved persons
The COVID pandemic affected the overall performance of OR to a larger extent