## MPP-2018
Master Procurement Plan for Year 2019 (Updated)
Ministry of Highways & Road Development and Petroleum Resources Development (Highways & Road Development Sector)
No | Department/ Line/ Agency/ Ministry | Procurement Category (W/G/ S) | Title of the Procurement | Estimated Cost (Rs. Mn.) | Total Estimated Cost for 2019 (Rs. Mn.) | Source of Funding / Name of the Donor | Procurement Method (ICB.LIB.LNB.NCB & National Shopping etc) | level of Authority | Priority Status U = urgent P = Priority N = Normal | Current status of Procurement Preparedness acticities | Scheduled date of commencement | Scheduled date of completion | Referance to Action Plan. | Remarks
01. Badulla Chenkaladi Road Improvement Project (BCRIP)
1 | BCRIP | W | OFID 01-Rehabilitation/ Improvements to Peradeniya Badulla Chenkaladi Road (A005) from Badulla (130+800km) to Passara (150+800km) | 7800 | 2200 | The OPEC Fund for International Development. | ICB | SCAPC | U | Awarded | 2016.12.15 | 2019-Dec | 51 | *1
2 |  | W | OFID 02-Rehabilitation/ Improvements to Peradeniya Badulla Chenkaladi Road (A005) from Passara (150+800km) to Lunugala (171+800km) |  |  |  |  | SCAPC
3 |  | W | OFID 03-Rehabilitation/ Improvements from Lunugala (171+800km) to Bibila (190+800km) |  |  |  |  | SCAPC
4 |  | S | Consultancy from Badulla to Bibile |  |  |  | LCB | SCACPC | U | Awarded. | 2016.12.15 | 2019-Dec |  |  | `
5 |  | W | SFD 01-Bibile (190+800km) to Padiyathalawa (219+800) | 7800 | 1550 | The Saudi Fund for International Development. | ICB | SCAPC | U | Awarded. | 2018.06.05 | 2019-Dec | 39
6 |  | W | SFD 02-Padiyathalawa (219+800km) to Thampitiya (249+800km) |  |  |  |  | SCAPC
7 |  | W | SFD 03-Thampitiya (249+800km) to Chenkaladi (277+550km) |  |  |  |  | SCAPC
8 |  | S | Consultancy From 190+800km (Bibile) to 277+550km (Chenkaladi) |  |  |  | LIB & LCB | SCACPC | U | Awarded. | 2017.08.10 | 2019-Dec
Sub Total |  |  |  | 15600 | 3750
02. Central Expressway Project-1 (CEP-1)
9 | CEP-1 | W | Civil Work for Kadawatha to Meerigama | 158386 | 3076.49 | EXIM Bank-China & GOSL | LIB | SCAPC | P | Awarded | 2016.06.12 | 2020-June | 11 & 15 | *2
10 |  | S | Cleaning Service, Lease Vehicles & Building Rent |  | 13.23 | GOSL | Shopping | PPC | N | To be commenced | 2019-Jan | 2022-Dec
11 |  | G | Purchases of Resettlements Sites (Furniture, Computer Accessories & other equipments) |  | 210.28 | GOSL | Shopping | PPC | N | To be commenced | 2019-Jan | 2019-Dec
12 |  | S | Consultancy for Kadawatha to Meerigama | 2549 | 700 | BOC | NCB | CACPC | P | Awarded. | 2017.06.01 | 2022-June |  | *3
Sub Total |  |  |  | 160935 | 4000
03. Central Expressway Project-2 (CEP-2)
13 | CEP-2 | W | Meerigama to Kurunegala and Ambepussa link road | 150000 | 77000 | Local Banks | NCB | CANC | P | Awarded. | 2016.11.01 | 2019.12.31 | 12 & 15 | *4
14 |  | S | Consultancy for Meerigama to Kurunegala and Ambepussa link road | 4000 |  | Local Banks | SS | CACPC | P | Awarded.
15 | CEP - 2 | G | Land & Land Improvements Infranstructure Development | 50 | 50 | Local Banks | SS | PPC | P |  |  |  | 12 & 15
Sub Total |  |  |  | 154050 | 77050
04. Central Expressway Project-3 (CEP-3)
15 | CEP-3 | W | Construction of Pothuhera to Galagedara | 134905.2 | 4964.5 | MUFG Bank of Japan | LIB | CANC | P | To be Awarded. | 2019 Feb | 2022-Jan | 13 & 15 | *5
16 |  | S | Construction Supervision of Pothuhera to Galagedara | 2860 | 970.8 |  | LIB | CAPC | P | To be Awarded. | 2019 Feb | 2022-May |  | *6
17 |  | W | Construction of tube wells | 10 | 10 | GOSL | LNB | PPC | P | To be Procured in several stages | 2019-Jan | 2019-Dec
18 |  | G | Stationery | 22.33 | 1.3 | GOSL | Shopping | PPC | P |  | 2013-Jan | 2022-Dec
19 |  | S | Hiring of vehicles | 105.82 | 24 | GOSL |  | PPC | P |  | 2013-Jan | 2022-Dec
20 |  | G | Office furniture & Equipment | 15.27 | 1 | GOSL |  | PPC | P |  | 2013-Jan | 2022-Dec
21 |  | W | Development of the re settelement site | 100 | 100 | GOSL | NCB | PPC | P | Awarded | 2018-Oct | 2019-Sep |  | *7
22 |  | S | Baseline Surveys | 5.5 | 5.5 | GOSL | LNB | CPCM | P | To be Procured in several stages | 2018-Aug | 2019-Mar
23 | CEP - 3 | S | Ecological Surveys | 2.9 | 2.9 | GOSL | LNB | CPCM | P |  | 2018-Aug | 2019-Mar
Sub Total |  |  |  | 138027.02 | 6080
05. Central Expressway Project-4 (CEP-4)
24 | CEP-4 | W | Civil Work for Kurunegala to Dambulla | 162000 | 30 | EXIM Bank-China & GOSL | LIB | SCAPC | N | Received Cabinet Approval to Award the Contract & Contract Agreement yet to be signed. | 2019 June | 2020.05.31 | 14 & 15
25 |  | S | Consultancy Service for Kurunegala to Dambulla | 2383 | 20 | EXIM Bank-China & GOSL | LIB | SCAPC | N |  | 2019 May | 2020.05.31
Sub Total |  |  |  | 164383 | 50
06. Construction Division-RDA
26 | Cons. Div. | W | Aaphalt Concrete overlay (Wearing Course ) on Osu Uyana Road from Ch 0+000 -2+200)Km | 77.5 | 25 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 73
27 |  | W | Supply & Installation of Street lighting system with LED light on Cotta Road (CH-0+000 to 0+760 km).(with centerlized system) | 14.15 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 74
28 | Construction Division | W | Supply & Installation of street light system with LED light on link Road connecting Parliment Road and Buthgamuwa Road near HSBC Premises. (0+000- 0+400) Km (with centerlized system) | 7.24 | 5 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 74
29 |  | W | Reconstruction of Bridge No. 1/3 at Panagoda - Henpita Road | 85 | 40 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 75
30 |  | W | Reconstruction of Bridge No. 2/3 at Panagoda - Henpita Road | 30 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
31 |  | W | Improvement of Asphalt Overlaying on Wattala - Hekitta road (0+000 - 1+560)km | 88.4 | 61 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 77
32 |  | W | Improvements to Ja-Ela Intersection | 46 | 31.9 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
33 |  | W | Improvements to Udupila Junction | 50 | 23 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
34 |  | W | Improvements to Meevitigammana Junction | 50 | 24 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
35 |  | W | Improvements to New Nuge Road(1.3km) | 50 | 30.15 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
36 |  | W | Improvements to Minioluwa-Elapiliyawa rd | 74.75 | 25 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
37 |  | W | Structural Improvements to Weliweriya Kirindiwela Road 0+000 13+250 km | 99.2 | 13.5 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.01 | 2019.12.31 | 80
38 | CONSTRUCTION DIVISION | W | Re-Construction of 10/4 bridge on Miriswatta Wathurugama Road | 20 | 14 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.01 | 2019.12.31 | 80
39 |  | W | Strucral Improvements to Udugampola Divlapitiya Road 0+000 - 15+000 km | 98.3 | 13 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.01 | 2019.12.31
40 |  | W | Widening and Improvements to Makandura Badalgama Road 2+400 - 4+500 km | 99.5 | 14 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.01 | 2019.12.31 | 81
41 |  | W | Structural Improvements to Negambo Meerigama Road 22+000 - 30+500 km | 89.5 | 10.25 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.04.01 | 2019.12.31
42 |  | W | Construction of bridge no 17/1 on Meepe Ingiriya Road | 40 | 30 | 30 | NCB | DPC | N | Preparing Estimates. | 2019.04.01 | 2019.12.31 | 83
43 |  | W | Reconstruction of Bridge No 4/1 Horawela-Pelawatta-Pitigala Road | 60 | 24.14 | 24.14 | NCB | MPC | N | Preparing Estimates. | 2019.04.01 | 2019.12.31
44 |  | W | Construction of Bridge across Kukule Ganga on Illupitiya - Kitulgalwila Road (Super Structure) | 49.5 | 20 | GOSL | NCB | DPC | N | Tendering | 2019.01.15 | 2019.12.31 | 84
45 |  | W | Widening & Improvements to Ingiriya-Halwathura-Egala Oya Road 4+000 to 6+000 Km) | 83 | 53 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
46 |  | W | Widening & Improvements to Wales park Junction on Sangaraja Mawatha in Kandy Town | 86.14 | 38.6 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 87
47 |  | W | Widening of Link Road 02 - William Gopallawa Mawatha Junction in front of Kandy railway station | 30 | 15 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
48 | CONSTRUCTION DIVISION | W | Construction of R/W on Nanuoya Hendeniya Road ( 2nd Km ) | 10 | 8 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 89
49 |  | W | A/C overling on Gampola Grehead road 0+000 - 2+000 km | 32 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
50 |  | W | Widinig & Improvements on Matale Illukkubura Laggala Road (9+225-9+525-0+000 km / Raththota Town) | 95 | 30 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.15 | 2019.12.31 | 91
51 |  | W | Fixing hand rails on Kandy Jaffna Road [ A - 9] - 26/1 - 27/5 (25.00km-27.00km) | 40 | 17.2 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.15 | 2019.12.31
52 |  | W | Construction of Footwalk Using Intarlock Block on Ambepussa Kurunegala Trincomalee road ( 90+000-91+700km) | 60 | 7 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.15 | 2019.12.31
53 |  | W | Widening & Improvements of Matale Udupihilla Road (0+230-0+530km) | 95.25 | 30 | GOSL | NCB | DPC | N | Tendering | 2019.06.15 | 2019.12.31
54 |  | W | Widening & Improvements of Matale Udupihilla road (0+000-0+230km) | 60.6 | 29 | GOSL | NCB | DPC | N | Tendering | 2019.06.15 | 2019.12.31
55 |  | W | Palapathwela-Galewela road (0.000-0+100km) | 60 | 28.5 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.06.15 | 2019.12.31
56 |  | W | Improvement of Bengamuwa-Mologgamuwa-Galdola Road(0+000-4+000Km) | 96.4 | 75 | GOSL | NCB | MPC | N | Tendering | 2019.03.31 | 2019.12.31 | 94
57 | CONSTRUCTION DIVISION | W | Improvements to Yakkalamulla - Katanwila Road (10+000-12+370Km) | 99.5 | 75 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31 | 94
58 |  | W | Reconstruction of Bridge No. 14/1 on Thihagoda-Kamburupitiya-Mawarala-Kotapola Road | 152 | 85 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
59 |  | W | Katuwana-Rukmalpitiya Road (4.8km-9.00km) | 100 | 74.5 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
60 |  | W | Reconstruction Of culvert No 19/1on GDM road & Construction of drains & foot walk on kottawa - Batemulla road ( RHS) (12+940- 13+40 km) - & Ahangama - Imaduwa road (RHS LHS) (9+920-10+080 km) | 40 | 30 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 96
61 |  | W | Improvemrnt to Kosgoda - Uragaha Road (0+000 -6+000 km) | 80 | 31 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
62 |  | W | Construction of Culvert No 196/1 on Colombo -Galle -Hambantota -Wellawaya Road | 27 | 20 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31 | 98
63 |  | W | Construction of Bridge No 10/2 on Weeraketiya Middeniya road | 38 | 25 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
64 |  | W | Construction of Bridge No 12/2 on Weeraketiya Middeniya Road | 35 | 25 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
65 |  | W | Kataragama Sellakataragama | 100 | 50 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
66 | CONSTRUCTION DIVISION | W | Improvement of Thalawa Dambaralla Hingura Road (0+000 - 1+500)km | 50 | 30 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 98
67 |  | W | Weligatta Lunugamwehera Road(6+300-10+400)km | 100 | 55 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
68 |  | W | Widening Improvement to Kadduvan- Myliddy Road 0.000 - 1.000 km | 83 | 46.7 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 99
69 |  | W | Widening Improvement to Vallai Thellipalai Araly Road 7.9 -9.1 kmm | 95.3 | 40 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
70 |  | W | Reconstruction of Bridge No12/1 on Paranthan Karachchi Mullaitivu Road | 80 | 8.7 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 101
71 |  | W | ABC Overlaying and Asphalt Concreting work with Retaining wall at Erukakalmpiddy road - B119. | 100 | 70 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31 | 102
72 |  | W | ABC Overlaying and Asphalt Concrete work on Pallimunai Road 0.8 - 2.3 km (B352) | 39.5 | 39.5 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
73 |  | W | ABC Overlaying and Asphalt Concreting work on Approach Road to Public Building (Station Road) 0.00 - 2.4 km (B030) | 100 | 66.9 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
74 |  | W | Constuction of Bridge No; 185/2 on Kandy-Jaffna Road | 115 | 61.3 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 104
75 | Construction Division | W | Constuction of Build up drain with cover slabs on Bazar Street | 87 | 87 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 104
76 |  | W | Reconstruction of Bridge No 28/2 on Paranthan Karachchi Mullaitivu Road | 50 | 24.4 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 105
77 |  | W | Reconstruction of Bridge No 31/2 on Paranthan Karachchi Mullaitivu Road | 50 | 33 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
78 |  | W | Reconstruction of Bridge No 14/2 and Retaining wall at Mankulam Velleankulam road | 20 | 14 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
79 |  | W | Widening Improvement Old Road Kattankudy (5+500km-6+500km)(Asphalt overlaying with construction of drain) | 80 | 80 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31 | 106
80 |  | W | Supply & Installation of Street Light at Old Road Kattankudy (3+500-5+500)km | 35 | 35 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
81 |  | W | Construction of Retaining Wall at BTT Road (5+000-6+000)km | 31.7 | 31.7 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
82 |  | W | Widening & Imp.to Chadayanthalawa-Uhana road chain.from 6+100 to 9+100km | 75.66 | 7 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
83 |  | W | Widening & Imp.to Chadayanthalawa-Uhana road chain.from 9+100 to 12+100km | 75.66 | 8.13 | GOSL | NCB | MPC | N | Tendering | 2019.03.31 | 2019.12.31
84 | CONSTRUCTION DIVISION | W | Correction of base and Asphalt Overlaying on TP Road(0.0 km to 0.35 km) | 15 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
85 |  | W | Improvement to Palathoopur seruwela Road and Construction of side drain(1st Km 300m & 2nd Km 266m ) | 60 | 30 | GOSL | NCB | DPC | N | Checking Estimate | 2019.03.31 | 2019.12.31
86 |  | W | Construction of foot walk at TP Road (0.225km-0.9km) LHS | 15 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
87 |  | W | Correction of base and Asphalt Overlaying on TP Road(0.35 km to 0.7 km) | 10 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
88 |  | W | Construction of foot walk at TP Road (0.225km-0.9km) RHS | 10 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
89 |  | W | Base correction and Asphalt overlaying on Trincomalee-pulmuddai road(50-55km) | 10 | 23.97 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
89 |  | W | Construction of Build up drain at 107th Km to 109th Km in BTT road | 10 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 112
90 |  | W | Improvements to Mawathagama Barandana Road (2+300 -4+600 km) | 80 | 16 | GOSL | NCB | MPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 115
91 |  | W | Balance work of Construction ofStructures on Mahakeliya - Katupotha Road(0+000 - 12+020km) | 62.66 | 13 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
92 | CONSTRUCTION DIVISION | W | Widening and Asphalt overlaying on Hiripitiya - Galtenwewa Road (12+695-14+600 km) - balance work | 100 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 116
93 |  | W | Improvements to Karuwalagaswawe - Meeyallawa Road (3+000 - 5+500 km ) | 85 | 16 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 118
94 |  | W | Asphalt Overlaying to Kahatagasdigiliya - Rathmalgahaweewa - Kivulekade Road | 60 | 19 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31 | 125
95 |  | W | Sripura to Singhepura 3rd mile post (5+650 - 8+524 km) & Singhepura Temple Junction to Padaviya School End (0+000 - 2+000 km) | 30 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 126
96 |  | W | Asphalt Overlaying to Kapugollewa - Ambagaswewa - Dutuwewa - Wagollagoda Road (0.0-5.0)km | 20 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
97 |  | W | Reconstruction of culvert No 52/3 at Maradankadawala- Habarana- Thirukkondiyamadu Road | 12 | 12 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 127
98 |  | W | Widening & Improvement of Moragaswewa - Ilukwewa B294 road section 1(0+000km to 0+0.750km) | 75 | 55 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
99 | Construction Division | W | Widening & Improvement of Moragaswewa - Ilukwewa B294 road section 2(0+750km-1+500km) | 75 | 58.05 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
100 |  | W | Improvement of Bandarawela Intersection of Beragala - Haliela and Bandarawela Welimada roads | 30 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 130
101 |  | W | Improvement of Bandarawela - Liyangahawela - Poonagala Road (1.3 - 2.5 km) | 64 | 30 | GOSL | NCB | DPC | N | Tendering | 2019.03.31 | 2019.12.31
102 |  | W | Improvement of Bandarawela - Liyangahawela - Poonagala Road (5+000 - 7+000)km | 95 | 48 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
103 |  | W | Improvement of Embilipitiya - Moraketiya - Kiri Ibban Ara - Uda Mauara road (14.2 - 16.8 km) | 80 | 50 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 131
104 |  | W | Improvement of Hulandawa Junction at Intersection of Colombo - Rathnapura - Wellawaya - Baticaloa and Passara Monaragala Road | 30 | 20 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
105 |  | W | Widening of Passara - Hingurukaduwa - Palwatta Road (10+000 - 15+500)km | 80 | 76.4 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
106 |  | W | Balance work of Thibiripola Suspension Bridge | 15 | 15 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 134
107 | CONSTRUCTION DIVISION | W | Raised Foot Walk inbetween 39 th km- 40 th km on Kegalle -Bulathkohupitiya-Karawanella Road at Ruwanwella Town. | 21 | 18 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 134
108 |  | W | Asphalt overlaying in bad section's (specialy bends) on Awissawella -Hatton-Nuwaraelliya Road (0.8 km-42.2km) | 50 | 50 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
109 |  | W | Construction of Retaining wall in between 4/4 -4/5 LHS & Widening of Culvert No 4/5 on Rambukkana -Mawanella | 22 | 15 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
110 |  | W | Construction of Culvert No 6/3 Magammana - Kurupaththa - Daigala Road | 20 | 15 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
111 |  | W | Back Filling of existing Retaing wall in Dehiowita Draniyagala Nooriya Road (3Km Post - 4/1 LHS,9/7 -9/8 RHS & 12/3 - 12/4 RHS ) | 4 | 4 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
112 |  | W | Rehabilitation and Asphalt concrete on Pallebedda Madaganoya Weligepola Road (2+000-4+000)km | 50 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
113 |  | W | Rehabilitation and Asphalt concrete on Kalawana - Deepdeen - Rakwana road ( 45 - 47 km ) | 60 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 138
114 | CONSTRUCTION DIV. | W | Retaining wall Construction of Kuruwita Town (86km post - 87/1) | 25 | 4 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 138
115 |  | W | Rehabilitation and Asphalt concrete overlaying Embilipitiya Panamura Bulitota Road (25+000-27+000)km | 50 | 10 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
116 |  | W | Construction of Bridge at 0+480 on Eheliyagoda old rail track road(Only foundation work) | 130.8 | 22 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31 | 138
117 |  | W | Improvement to Malwala-Carney road(From 2+000km to 4+000km) | 240 | 6 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
118 |  | W | Widening of Bridge No. 99/6 on Colombo-Ratnapura-Wellawaya-Batticaloa road(Downstream) | 145 | 18.85 | GOSL | NCB | DPC | N | Preparing Estimates. | 2019.03.31 | 2019.12.31
119 |  | W | Works Order and Bill hands | 4811.66 | 4811.66 | GOSL | NCB | DPC | N |  | 2019.03.31 | 2019.12.31
Sub Total |  |  |  | 10569.87 | 7546
07. Elevated Highway Project (EHP) From NKB to Athurugiriya
120 | EHP-NKB | W | Civil Works for New Kelani Bridge to Rajagiriya | 36650 | 75 | BOT | ICB | CANC | P | Procurement Commence | 2017.07.13 | 2022-Jan | 24 | *8
121 |  | W | Civil Works for Rajagiriya to Athurugiriya | 54350 |  | BOT | NS | CANC | P | Feacibility Study is in progress | 2018.01.01 | 2019.03.31 |  | *9
122 |  | S | Consultancy Services for New Kelani Bridge to Athurugiriya | 1500 | 100 | GOSL | ICB | CACPC | P | Awarded. | 2017.07.13 | 2022-Jan |  | *8
123 | EHP - NKB | G | New Kelani Bridge to Athurugiriya | 400 | 50 | GOSL | Shopping | MPC | N | Awarded. | 2019-Jan | 2022-Jan | 24 | *8
Sub Total |  |  |  | 92900 | 225
08. Extention of Sourthern Expressway Project-1 (ESEP-1)
124 | ESEP-1 | W | Extention of Sourthern Expressway from Matara to Beliatta | 113589.98 | 9838 | EXIM Bank-China | Unsolisited/ Stand-along | SCAPC | P | Awarded. | 2016.01.19 | 2019.07.18 | 16 & 21 | *10
125 |  | S | Consultancy Services for Extention of Sourthern Expressway from Matara to Beliatta | 3806.6 | 1986 | EXIM Bank-China | Unsolisited/ Stand-along | CACPC | P | Awarded. | 2016.01.20 | 2019.07.18 |  | *11
126 |  | G | Extention of Sourthern Expressway from Matara to Beliatta | 610 | 96 | GOSL | Shopping | MPC
Sub Total |  |  |  | 118006.58 | 11920
09. Extention of Sourthern Expressway Project-2 (ESEP-2)
127 | ESEP-2 | W | Civil Works for Extention of Sourthern Expressway from Beliatta to Wetiya | 55200 | 7484.47 | EXIM Bank-China & HNB Sri Lanka | LIB | SCAPC | P | Awarded. | 2016.10.28 | 2019.10.27 | 17 & 21 | *12
128 | ESEP-2 | S | Consultancy Service for Extention of Sourthern Expressway from Beliatta to Wetiya | 2783.53 | 1665.53 | EXIM Bank-China | LIB | CACPC | P | Awarded. | 2016.01.25 | 2020.04.27 |  | *13
Sub Total |  |  |  | 57983.53 | 9150
10. Extention of Sourthern Expressway Project-3 (ESEP-3)
129 | ESEP-3 | W | Civil Works for Extention of Sourthern Expressway from Wetiya to Andarawewa | 31574.1 | 3962 | EXIM Bank-China | LIB | SCAPC | P | Awarded. | 2016.01.25 | 2018.11.24 | 18 & 21 | *14
130 |  | S | Consultancy Service forExtention of Sourthern Expressway from Wetiya to Andarawewa | 1982 | 1268 | EXIM Bank-China | LIB | CACPC | P | Awarded. | 2015.09.01 | 2019.05.19 |  | *15
Sub Total |  |  |  | 33556.1 | 5230
11. Extention of Sourthern Expressway Project-4 (ESEP-4)
131 | ESEP-4 | W | Extention of Sourthern Expressway from Hambanthota to Mattala via Andarawewa | 52156 | 4250 | CDB | Unsolisited/ Stand-along | SCAPC | P | Awarded. | 2016.01.19 | 2019.01.18 | 19 & 21 | *16
132 |  | S | Construction Supervision of Extention of Sourthern Expressway Matara to Hambanthota | 1620 | 1300 | CDB | Unsolisited | CACPC | P | Awarded. | 2016.01.20 | 2019.01.19 |  | *17
Sub Total |  |  |  | 53776 | 5550
12. Integrated Road Investment Programme (i-Road)
133 | i- Road | W | i-Road - 1 National Roads. | 25000 | 12404.91 | ADB | ICB | SCAPC | P | Documents are been prepaired | 2019-June | 2024-June | 55 & 56 | *18
134 |  | W | Rehabilitation & Improvements of Rural Roads including Performance based Maintenance of 03 years in Western Province (i-Road -2) | 22225 | 1000 | ADB | NCB/ ICB | SCAPC | P | Documents are been prepaired | 2019-Sep | 2024-Sep
135 |  | W | Rehabilitation & Improvements of Rural Roads including Performance based Maintenance of 03 years in Eastern Province (i-Road -2) | 26590 | 1000 | ADB | NCB/ ICB | SCAPC | P | Bids are been evaluated | 2019-Mar | 2026-Mar
136 |  | W | Rehabilitation & Improvements of Rural Roads including Performance based Maintanance of 03 years in Nothern Province (i-Road -2) | 38970 | 800.09 | ADB | NCB/ ICB | SCAPC | P | Bids are been evaluated | 2019-Mar | 2026-May
137 |  | S | Project Implementation Consultant (PIC) Uva, Northern, Eastern, Western Province & Individual Consultants | 6000 | 100 | ADB | NCB | CACPC | P | Awarded. | 2019-Jan | 2027-Jan
138 |  | G | i-Road -2 | 900 | 95 | ADB | Shopping | MPC | P | To be Commenced | 2019-Jan | 2027-Jan
Sub Total |  |  |  | 119685 | 15400
13. Landslide Disaster Protection Project (LDPP)
139 | LDPP | W | Civil Works Package 1 | 2829 | 880 | JICA | ICB | SCAPC | P | Awarded. | 2012.10.09 | 2020.03.31 | 186 | *19
140 |  | W | Civil Works Package 2 | 3438 | 1551 | JICA | ICB | SCAPC | P | Awarded. | 2012.10.09 | 2020.03.31
141 |  | W | Stablishment of EWS | 31 | 1 | JICA | LCB | PPC | P | Awarded. | 2012.10.09 | 2020.03.31
Sub Total |  |  |  | 6298 | 2432
14. Local Bank Funded Project (LBFP)
142 | LBFP | W | Constriction of 20 National Highways. | 23150 | 5500 | NSB | NCB | CAPC | P | Engineer's Estimate Finalized. | 2019 May | 2021.01.01 | 143 & 144 | This will be implemented only if Treasury gurantee given
Sub Total |  |  |  | 23150 | 5500
15. Maintenance & Management Division (MM)-RDA
143 | MM | W | Surfacing Programm under periodic maintenance -RMTF | 1000 | 4700 | GOSL | NCB | DPC | P | Document Preparation. | 2018-Dec | 2019-Dec | 30 - 31
144 | MM | W | Rehabilitation & Reconstruction of Week Bridges | 300 | 300 | GOSL | NCB | DPC | P | Document Preparation. | 2018-Oct | 2019-Dec | 31 - 32
Sub Total |  |  |  | 1300 | 5000
16. Miscellaneous Foreign Aided Projects Division (MFAP)
145 | MFAP | W | Rehabilitation & Improvements to Piliyandala -Maharagama Road (B367) (RDA/MFAP/ICB/OFID-2/05) | 717 | 280 | OFID-02 | ICB | SCAPC | N | Land Acquisition is in progress. | 2019.06.01 | 2020.09.30 | 46
146 |  | W | Rehabilitation & Improvements to Orugodawatta-Ambatale Road (B435) (RDA/MFAP/ICB/OFID-2/09B) Stage II | 1500 | 529 | OFID-02 | ICB | SCAPC | N | Awarded. | 2018.09.03 | 2020.09.02 |  | *20
147 |  | W | Rehabilitation & Improvements to Walgama - Diyagama Road (B452) (RDA/MFAP/ICB/OFID-2/04) | 823.6 | 450 | OFID-02 | ICB | SCAPC | N | Awarded. | 2019.03.01 | 2020.09.30 | 46 | *21
148 |  | W | Widening & Improvements to Galle - Deniyaya - Madampe Road Section from Sooriyakanda (Ch.113+000Km) to Rakwana (Ch.130-600Km) Stage 1 | 5851 | 510 | OFID-04 | ICB | SCAPC | P | Awarded. | 2019-Aug | 2022-Aug | 45 | *22
149 |  | W | Widening & Improvements to Galle - Deniyaya - Madampe Road Section from Deniyaya (Ch.78+000Km) to Sooriyakanda (Ch.113-000Km) Stage 2 | 11295 | 150 | OFID-04 | ICB | SCAPC | P | Land Acquisition is in Progress. | 2020-May | 2023-May
150 | MFAP | W | Rehabilitation & Improvements of Kandy-Jaffna Road Naula Town Section from 53+740km-54+990km -58+000km | 546.83 | 300 | SFD-02 | ICB | MPC | U | Awarded. | 2018.09.20 | 2021.02.20 | 40 | *23
151 |  | W | Widening of Bridge No.6/2 on Orugodawatta-Ambathale Road | 230 | 190 | SFD-02 | ICB | DPC | U | Awarded. | 2018-Dec | 2020-Mar | 46 | *24
152 |  | W | Widening of Bridge No.6/1 on Orugodawatta-Ambathale Road | 245 | 195 | SFD-02 | ICB | DPC | U | Awarded. | 2018-Dec | 2020-Mar
153 |  | W | Widening of Bridge No.4/3 on Orugodawatta-Ambathale Road | 255 | 205 | SFD-02 | ICB | DPC | U | Awarded. | 2018-Dec | 2020-Mar
154 |  | S | Construction of Kandy Tunnel | 1495 | 300 | EDCF | LCB | CACPC | U | Preparation of EOI & RFP | 2019-Feb | 2022-Mar
Sub Total |  |  |  | 22958.43 | 3109
17. New Bridge Construction Project Over Kelani River (NKBCP)
155 | NKBCP | S | Consultant's Services - Design Tender Assistance and Construction Supervision for New Bridge Construction Project Over Kelani River | 4165.89 | 732.2 | JICA | ICB | CACPC | N | Awarded. | 2015.01.05 | 2020.12.31 | 181 | *25
156 |  | W | Reconstruction and Relocation of Main Building and Laboratories in a new location at Orugodawatta for Sri Lanka Atomic Energy Board (SLAEB) | 597.2 | 15 | JICA | NCB | MPC | U | Awarded. | 2017-April | 2019-Jan |  | *26
157 | NKBCP | W | Shifting of CEB overhead High Tension Transmission Lines (220kV & 132kV) | 1209 | 150 | JICA | NCB | SCAPC | U | Awarded. | 2017.04.17 | 2019-Jan | 181
158 |  | S | Consultancy - External Montoring Agency (EMA) | 8.67 | 5.2 | JICA | NCB | PPC | U | Awarded. | 2015.08.01 | 2019.02.28 |  | *27
159 |  | W | Package 1 (Steel Bridge Section) | 31539.03 | 5627.26 | JICA | ICB | SCAPC | U | Awarded. | 2017.10.18 | 2020.12.31 |  | *28
160 |  | W | Package 2 (Extradosed Bridge Section) | 9896.03 | 2630.34 | JICA | ICB | SCAPC | U | Awarded. | 2017.11.16 | 2020.12.31
Sub Total |  |  |  | 47415.82 | 9160
18. Northern Road Connectivity Project (NRCP)
161 | NRCP | W | Rehabilitation / Improvement of A09 Kandy – Jaffna (141+100km to 150+400km)- | 799.54 | 405 | ADB-Loan 2890 (SF)/ 2891-SRI | NCB | SCAPC | U | Awarded. | 2017-Mar | 2019-Mar | 43 & 44 | NRCP-AF *29
162 | NRCP | W | Civil Works (NRCP-Additional Financing)/ B-282 Medawachchiya-Horowpathana Road CP 23 (section 10.0-37.8km) | 1280 |  | ADB-Loan 2890 (SF)/ 2891-SRI | NCB | SCAPC | U | Preparing Engineer Estimate. | 2019-Jan | 2020-Jan | 43 & 44 | NRCP-AF
163 |  | W | Construction of Port Access Elevated Highway | 38000 | 3550 | ADB | OCB | SCAPC | U | Evaluation is in progress | 2018-Dec | 2021-Dec | 25 | PAEHP
164 |  | W | Construction of Maritime Facilitation Center (Building) | 4200 |  | ADB | OCB | SCAPC | U | Evaluation is in progress | 2019-Oct | 2021-Nov |  | PAEHP
165 |  | W | Piling works for Maritime Facilitation Center (Piling) | 600 |  | GOSL | OCB | MPC | U | Evaluation is in progress | 2018-Dec | 2021-Jun |  | PAEHP
166 |  | S | Procurement of Contractor for Electronic toll Collection System | 4480 |  | ADB | OCB | CACPC | U | Preparedness activities in progress. | 2019-Jun | 2021-Dec |  | PAEHP
167 |  | S | Construction Supervision of PAEH | 1290 |  | ADB | QCBS | CACPC | U | RFP Document Issued. | 2018-Jun | 2021-Dec |  | PAEHP
168 |  | S | Procurement of Consultant for Electronic toll Collection System Management | 550 |  | ADB | QCBS | MPC | U | Preparedness activities in progress. | 2019-Dec | 2021-Dec |  | PAEHP
169 |  | S | Individual Consultant- Structural Advisor | 65 |  | ADB | ICB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2021-Dec |  | PAEHP
170 |  | S | Individual Consultant- Contract Management Advisor | 30 |  | ADB | ICB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2021-Dec |  | PAEHP
171 | NRCP | S | Individual Consultant- Contract Engineer | 20 |  | ADB | NCB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2021-Dec | 25 | PAEHP
172 |  | S | Individual Consultant- IT Specialist | 15 |  | ADB | NCB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2021-Dec |  | PAEHP
173 |  | S | Individual Consultant-Implementation Support for Maritime Facilitation Center | 6 |  | ADB | NCB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2020-Dec |  | PAEHP
174 |  | S | Individual Consultant-Implementation Support for Maritime Facilitation Center | 6 |  | ADB | NCB | MPC | U | Preparedness activities in progress. | 2018-Dec | 2020-Dec |  | PAEHP
175 |  | S | Expressway Connectivity Improvement Plan | 6.8 | 100 | ADB Loan 3028 SRI (SF) | QCBS | CACPC | U | EOI document in being prepared. | 2019-Jan | 2020-Jan | 61 | ECIP
176 |  | S | Consultancy (Individual)- Financial Advisor for Peliyagoda Rajagiriya Elevated Highway(ICS-01) | 32.57 | 200 | ADB Loan 3028 SRI (SF) | ISC | DPC | N | Awarded. | 2017-Oct | 2019-July |  | TPPF *30
177 |  | S | Consultancy (Individual)- Legal Advisor for Peliyagoda Rajagiriya Elevated Highway(ICS-02) | 9.61 |  | ADB Loan 3028 SRI (SF) | ISC | DPC | N | Awarded. | 2018-May | 2019-Sep |  | TPPF *31
178 |  | S | Consultancy (Individual)- Transaction Advisor for Peliyagoda Rajagiriya Elevated Highway(ICS-03) | 37.67 |  | ADB Loan 3028 SRI (SF) | ISC | DPC | N | Awarded. | 2017-Oct | 2019-July |  | TPPF *30
179 | NRCP | S | International PPP Procurement Advisor (ICS-04) | 24 |  | ADB Loan 3028 SRI (SF) | ISC | DPC | N | Awarded. | 2018-Nov | 2019-Dec | 61 | TPPF *32
Sub Total |  |  |  | 51452.19 | 4255
19. Outer Circular Highway Project III (OCHP-III)
180 | OCHP-3 | W | Construction of OCH-NS II from Kerawalapitiya to Kadawatha. | 66690 | 13950 | EXIM Bank-China & GOSL | Unsolisited | SCAPC | U | Awarded. | 2016.01.01 | 2019.06.30 | 22 | *33
181 |  | S | Consultancy Service for Construction Supervision of OCH-NS II. | 1592 | 350 | BOC | LIB | CACPC | U | Awarded. | 2014.10.20 | 2019.06.30
182 |  | W | Land Acqisition & Resettlement activities. | 8700 | 1000 | GOSL | NS | MPC | P | Awarded. | 2007.09.01 | 2019.01.31 |  | *34
183 |  | S | PMU cost, rent out office building, security & cleaning service. | 1718 | 145 | GOSL | NS | MPC | N | Awarded. | 2011.01.01 | 2019.12.31 |  | *1
Sub Total |  |  |  | 78700 | 15445
20. Priority Road Project 3 - Phase I (PRP3-I)
184 | PRP3-1 | W | Improvement and Rehabilitation of Priority Road Project 3 - Phase I (PRP3-I) | 49955.2 | 3000 | CDB & GOSL | Unsolisited | SCAPC/CANC | P | Awarded. | 2014.09.09 | 2019.09.30 | 48 - 49 | *35
Sub Total |  |  |  | 49955.2 | 3000
21. Priority Road Project 3 - Phase II (PRP3-II)
185 | PRP3-2 | W | Improvement and Rehabilitation of Priority Road Project 3 - Phase II (PRP3-II) | 16000 | 2020 | EXIM Bank-China & GOSL | Unsolisited | CAPC/CANC | P | Awarded. | 2016.12.03 | 2019.04.22 | 58 - 60 | *36
Sub Total |  |  |  | 16000 | 2020
22. Ruwanpura Expressway Project (REP)
186 | REP | G | Furniture, Equipments etc. | 80 | 25 | GOSL | NCB | PPC | P | To be commenced. | 2019 Jan | 2019 Dec | 23
187 |  | S | Security, Cleaning Utilities etc. | 90 | 75 | GOSL | NCB | PPC | P | To be commenced | 2019 Jan | 2019 Dec
188 |  | W | Section 1 of REP (Chinage 0-26.30km) | 107021 |  | EXIM Bank- China | NSB | CANC | P | Proposal under Evaluation. | 2019 Jan | 2019 Dec
189 |  | W | Section 2 of REP (Chinage 26.30km-47.30km) | 137680 |  | EXIM Bank- China | NSB | CANC | P | Preliminary Design is in Progress. | 2019 Jan | 2019 Dec
190 |  | W | Section 3 of REP (Chinage 47.30km-60.00km) | 77500 |  | EXIM Bank- China | NSB | CANC | P | Corridor Survey started. | 2019 Jan | 2019 Dec
191 |  | W | Section 4 of REP (Chinage 60.00km-73.90km) |  |  | EXIM Bank- China | NSB | CANC | P | Corridor Survey started. | 2019 Jan | 2019 Dec
192 |  | S | Consultancy, Hydrologic study etc. | 3500 |  | GOSL | ICB | CACPC | P | To be commenced. | 2019 Jan | 2019 Dec
Sub Total |  |  |  | 325871 | 100
23. Special Projects Management Unit (SPMU)
193 | SPMU | W | Reconstruction of 25 Bridges Project-Package 3 Civil works | 2000 | 1600 | KFAED | ICB | SCAPC | U | Design of Bridges in progress & Estimation of cost not completed yet. | 2019-Aug | 2021-July | 175 | Estimation of cost not completed yet.
194 |  | W | Major Bridges Construction Project of the Naional Road Network:Package 3 civil works (3bridges) | 2500 | 2280 | JICA | ICB | SCAPC | U | In Progress | 2019-Mar | 2021-Feb | 178
195 |  | S | Consultancy Service for Reconstruction of 25 Bridges Project-Package 3 | 300 | 730 | KFAED | ICB | CACPC | U | Bids are been evaluated | 2019-Jun | 2021-Sep | 175
Sub Total |  |  |  | 4800 | 4610
24. Southern Road Connectivity Project (SRCP)
196 | SRCP | W | Civil Works | 2800 | 1720 | ADB | ICB | SCAPC | P | Preparing Documents for ADB & CAPC Approval. | 2018-Oct | 2019-Mar | 53
Sub Total |  |  |  | 2800 | 1720
25. Transport Connectivity & Asset Management project (TCAMP)
197 | TCAMP | G | Procurement of Tow vehicle ( for FWD machine) and Network Servey Vehicle (NSV) for Asset Management Unit. | 80 | 6.7 | World Bank | NCB | PPC | P | Preperation in Bidding Document in Progress | 2018-Oct | 2019-Mar | 62
198 |  | G | Procurement of Skylift & Road Marking Machine for RDA. | 25 | 20 | World Bank | NCB | PPC | P | Preperation in Bidding Document in Progress | 2018-Oct | 2019-Mar
199 |  | G | Procurement of Sport Utility Vehicle (SUV) | 20 | 16 | World Bank | NCB | PPC | P | Preperation in Bidding Document in Progress | 2018-Oct | 2019-Mar
200 |  | G | Procurement of Hardware Requrement for Asset Management Unit. | 7.5 | 6 | World Bank | NCB | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
201 | TCAMP | G | Procurement of Software Requrement for Asset Management Unit. | 23 | 18 | World Bank | NCB | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
202 |  | S | Consultancy for establishing protocols for data collection | 1.5 | 1.5 | World Bank | IC | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar | 62
203 |  | S | Consultancy for institutional Assessment | 3 | 3 | World Bank | QBC | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
204 |  | S | Consultant for road sector stratergy and policy | 3 | 3 | World Bank | IC | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
205 |  | S | Establishing Monitoring and Evaluation System | 4.3 | 4.3 | World Bank | QBC | PPC | P | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
206 | TCAMP | W | Project for Turnkey Construction of Bridge and Approaches across Kokilai Lagoon on Mulathiv- Kokilai-Pulmudai Road | 9050 | 200 | Ceskoslovenska Obchodni bank of Czech Republic | SSS | SCAPC | U | Contract Negotiation | 2018-Nov | 2021-Oct
207 |  | W | Widening & Improving of Katugastota - Kurunagala - Puttalam Road(A10) From Katugasthota to Galagethara , (Ch. 0+000 to Ch. 13+000 Km) | 7200 | 80 | EXIM Bank of India | ICB | SCAPC | U | Feasibility Study & Geometric Design In Progress | 2018-Oct | 2019-Mar | 62 | Improvements of Central Expressway Connectivity Road in Kandy & Its Suberbs under TCAMP
208 |  | W | Construction of By-pass Road at Katugastota town connecting A009 Road & A010 Road (Ch. 0+000 to Ch. 0+531 Km) | 700 | 15 | EXIM Bank of India | ICB | SCAPC | U | Feasibility Study & Geometric Design In Progress | 2018-Oct | 2019-Mar
209 |  | W | Widenning and Improving of Aladeniya - Eriyagama Road (B 005)(Ch. 0+000 to Ch. 10+000 Km) | 3850 | 20 | EXIM Bank of India | ICB | SCAPC | U | Feasibility Study & Geometric Design In Progress | 2018-Oct | 2019-Mar
210 | TCAMP | W | Widening & Improving of Barigama Haloluwa Road (B537)(Ch. 0+000 to Ch. 5+760 Km) | 1900 | 50 | EXIM Bank of India | ICB | SCAPC | U | Feasibility Study & Geometric Design In Progress | 2018-Nov | 2019-Mar |  | Improvements of Central Expressway Connectivity Road in Kandy & Its Suberbs under TCAMP
211 |  | W | Widening & Improving of Arambekade - Bokkawala-Ambatenna Road (B015),( From Arambekade to Girihagama) | 325 | 32.5 | EXIM Bank of India | ICB | SCAPC | U | Feasibility Study & Geometric Design In Progress | 2018-Nov | 2019-Mar | 62
212 |  | W | Widening & Improving of Alawathugoda -Pujapitiya Road (B377) (Ch. 0+000 to Ch. 8+050 Km) | 2365 | 25 | EXIM Bank of India | ICB | SCAPC | U | Preperation in Bidding Document in Progress | 2018-Nov | 2019-Mar
213 |  | S | Consultancy Services For Preparation of Detailed Project Report on Central Expressway Connectivity Roads | 165 | 13 | EXIM Bank of India | SSS | CACPC | U | Awarded. | 2018-Aug | 2019-July
Sub Total |  |  |  | 25722.3 | 514
26. UK Steel Bridge Project (UKSBP)
214 | UKSBP | W | Land Acqisition & Resettlement activities for Rajagiriya, Ganemulla & Polgahawela Flyovers | 530 | 42 | GOSL | Stand-along | DPC | N | Awarded. | 2016.05.04 | 2019 May | 184 | *37
215 |  | W | Extra Works -Rajagiriya Flyover | 15.84 | 6.77 | GOSL | VO | PPC | N | Awarded. | 2018.03.01 | 2019 May
216 | UKSBP | W | Extra Works -Polgahawela Flyover | 47.87 | 10 | GOSL | VO | PPC | N | Awarded. | 2018.03.01 | 2019 May | 184
217 |  | W | Extra Works -Ganemulla Flyover | 10 | 10 | GOSL | Shopping | PPC | N | Awarded. | 2018.11.01 | 2019.04.30 |  | *38
218 |  | W | Reconstruction of Bridge no.28/9 on Katugastota Madawala Bambarella Road | 47.7381 | 12.29 | FARDF | NCB | PPC | N | Awarded. | 2016.04.04 | 2019.03.31 | 174 | *39
219 |  | W | Reconstruction of Bridge no. 8/4 on Kottawa Batemulla Road | 53.0985 | 8.43 | FARDF | NCB | PPC | N | Awarded. | 2016.03.31 | 2019.03.31
220 |  | W | Reconstruction of Bridge no.2/1 Mawanella Aranayake Horawela Road | 32.0183 | 6.51 | FARDF | NCB | PPC | N | Awarded. | 2016.09.12 | 2019.03.31
221 |  | W | Reconstruction of Bridge no.284/1 on Colombo Ratnapura Wellawaya Road | 180.1117 | 22 | FARDF | NCB | PPC | N | Awarded. | 2016.09.21 | 2019.01.31 |  | *40
222 |  | W | Reconstruction of Bridge no.14/6 & 16/8 on Lindula End of Agras | 153.6774 | 17 | FARDF | NCB | PPC | N | Awarded. | 2016.10.10 | 2019.02.28 |  | *41
223 |  | W | Reconstruction of Bridge no.13/10 on Malwala Carney Road | 99.0162 | 12 | FARDF | NCB | PPC | N | Awarded. | 2016.12.05 | 2019.02.28 |  | *42
224 |  | S | PMU Management Overhead & Contingencies |  | 8 | FARDF |  |  |  |  | 2013.09.16 | 2019.12.31
Sub Total |  |  |  | 1169.3703 | 155
27 RDA Divisional Procurements
225 | RDA Procurements | G | Engineering Division |  | 8.57 | GOSL | Normal Shopping | DPC | N |  |  |  | 187 - 188
226 | RDA Procurements | G | Enviornmental & Social Development Division |  | 124.7 | GOSL | Normal Shopping | DPC | N |  |  |  | 187 - 188
227 |  | G | Finance Division |  | 5.5 | GOSL | Normal Shopping | DPC | N
228 |  | G | Highway Design Division |  | 150 | GOSL | Normal Shopping | DPC | N
229 |  | G | Internal Audit Division |  | 3.26 | GOSL | Normal Shopping | DPC | N
230 |  | G | Land Division |  | 0.96 | GOSL | Normal Shopping | DPC | N
231 |  | G | Leagle Division |  | 0.68 | GOSL | Normal Shopping | DPC | N
232 |  | G | Mechanical Division |  | 4000 | GOSL | Normal Shopping | DPC | N
233 |  | G | Planning Division |  | 1500 | GOSL | Normal Shopping | DPC | N
234 |  | G | Procurement Division - Office |  | 0.81 | GOSL | Normal Shopping | DPC | N
235 |  | G | Property Management & Revenue Division |  | 1.37 | GOSL | Normal Shopping | DPC | N
236 |  | G | Quality Assurance Progress Monitoring Division |  | 2.27 | GOSL | Normal Shopping | DPC | N |  |  |  | 187 - 188
237 |  | G | Research & Development Division |  | 200 | GOSL | Normal Shopping | DPC | N
238 |  | G | Rural Bridge Construction |  | 500 | GOSL | Normal Shopping | DPC | N
239 |  | G | Training Division |  | 1.88 | GOSL | Normal Shopping | DPC | N
240 |  | G | Expressway Operation Management & maintenance |  | 17,869.19* | GOSL | Normal Shopping | DPC | N
Sub Total |  |  |  |  | 6500
Ministry Procurements
| Min. Proc. | G | Building & Structures |  | 0.95 | GOSL | NS | DPC | P |  |  |  | 5
|  | G | Furniture & Office Equipment |  | 4.55 | GOSL | NS | DPC | P
|  | G | Plant, machinery & Equipment |  | 2.5 | GOSL | NS | DPC | P
Sub Total |  |  |  |  | 8
209479
|  |  | Land Division (for Land Acquisition ) |  | 7321 | [8 empty] | *43
|  |  | Maganeguma |  | 10000 | [8 empty] | *44
|  |  | Gap Financing |  | 43700 | [8 empty] | *45
Total Estimated Amount for 2019 |  |  |  |  | 270500
|  |  | Total Estimated Amount for 2019, as per the Procurement Plan (Rs. Mn.) | [6 empty] | 270500
According to the procurement Plan for Year 2019, Central Expressway Project -2 (CEP-2) and Local Bank Funded Project (LBFP) have allocated Rs. 77,000Mn and Rs. 5,500.00Mn for year 2019. These amounts are obtaining from Local Banks and not including in the Budgetry Estimation for Year 2019. Also, Rs. 3,000.00 Mn which has been financed by Local Bank which has been incorporated in the figer mentioned under Construction Division (Rs.7546.00) Hence, this amount should not be mentioned in the Budget.
|  |  | Total Estimated Amount for 2019, without Local Banks Funds (Rs. Mn.) | [6 empty] | 185000
Checked by:
Recommended by:
|  | J.K.Nilupul S.Perera | [6 empty] | sgd./ Sunil Hettiarachchi
|  | Chief Financial Officer, | [7 empty] | Secretary
|  | Ministry of Highways, Road Development & Petroleum Resources Development | [7 empty] | MOHRD&PRD
Notes
|  | *1 | Procurement Process is completed. Civil Construction and Construction Supervision are shedule to be complete on December - 2019.
|  | *2 | Procurement Process is completed. Civil Construction is shedule to be complete on June - 2020.
|  | *3 | Procurement Process is completed. Construction Supervision is shedule to be complete on June - 2022.
|  | *4 | Procurement Process is completed. Civil Construction and Construction Supervision are shedule to be complete on December-2019.
|  | *5 | Procurement Process is completed. Civil Construction is shedule to be complete on January - 2022.
|  | *6 | Procurement Process is completed. Construction Supervision is shedule to be complete on May - 2022.
|  | *7 | Procurement Process is completed. Civil Construction is shedule to be complete on September - 2019.
|  | *8 | Procurement Process is completed. Civil Construction is shedule to be complete on January - 2022.
|  | *9 | Procurement Process is completed. Civil Construction is shedule to be complete on March - 2019.
|  | *10 | Procurement Process is completed. Civil Construction is shedule to be complete on September - 2019.
|  | *11 | Procurement Process is completed. Construction Supervision is shedule to be complete on September - 2019.
|  | *12 | Procurement Process is completed. Civil Construction is shedule to be complete on February - 2020.
|  | *13 | Procurement Process is completed. Civil Construction is shedule to be complete on April-2019.
|  | *14 | Procurement Process is completed. Civil Construction is shedule to be complete on November-2018.
|  | *15 | Procurement Process is completed. Construction Supervision is shedule to be complete on May - 2019.
|  | *16 | Procurement Process is completed. Civil Construction is shedule to be complete on January - 2019.
|  | *17 | Procurement Process is completed. Construction Supervision is shedule to be complete on January - 2019.
|  | *18 | Procurement Process is completed. Construction Supervision is shedule to be complete on January - 2027
|  | *19 | Procurement Process is completed. Construction Supervision is shedule to be complete on March - 2020.
|  | *20 | Procurement Process is completed. Civil Construction is shedule to be complete on September - 2020
|  | *21 | Procurement Process is completed. Civil Construction is shedule to be complete onSeptember- 2020.
|  | *22 | Procurement Process is completed. Civil Construction is shedule to be complete on August - 2022
|  | *23 | Procurement Process is completed. Civil Construction is shedule to be complete on February - 2021.
|  | *24 | Procurement Process is completed. Civil Construction is shedule to be complete on March - 2020.
|  | *25 | Procurement Process is completed. Construction Supervision is shedule to be complete on December - 2020.
|  | *26 | Procurement Process is completed. Civil Construction is shedule to be complete on January - 2019.
|  | *27 | Procurement Process is completed. Construction Supervision is shedule to be complete on February - 2019.
|  | *28 | Procurement Process is completed. Civil Construction is shedule to be complete on December -2020.
|  | *29 | Procurement Process is completed. Civil Construction is shedule to be complete on March -2019
|  | *30 | Procurement Process is completed. Construction Supervision is shedule to be complete on July - 2019
|  | *31 | Procurement Process is completed. Construction Supervision is shedule to be complete on September - 2019.
|  | *32 | Procurement Process is completed. Construction Supervision is shedule to be complete on December - 2019.
|  | *33 | Procurement Process is completed. Civil Construction and Construction Supervision are shedule to be complete on June-2019.
|  | *34 | Procurement Process is completed. Civil Construction is shedule to be complete on January -2019
|  | *35 | Procurement Process is completed. Civil Construction is shedule to be complete on September - 2019.
|  | *36 | Procurement Process is completed. Civil Construction is shedule to be complete on April - 2019.
|  | *37 | Procurement Process is completed. Civil Construction is shedule to be complete on May - 2019.
|  | *38 | Procurement Process is completed. Civil Construction is shedule to be complete on April - 2019.
|  | *39 | Procurement Process is completed. Civil Construction is shedule to be complete on March-2019.
|  | *40 | Procurement Process is completed. Civil Construction is shedule to be complete on January - 2019..
|  | *41 | Procurement Process is completed. Civil Construction is shedule to be complete on February - 2019
|  | *42 | Procurement Process is completed. Civil Construction is shedule to be complete on February-2019.
|  | *43 | Land Acquisition Cost
|  | *44 | Budget Proposals for Ran Mawath
|  | *45 | Pe Payment for Lacal Bank Loans