## Sheet1
NO | PRO | Component | Sub Components | Overall Target | Overall Achivement | Target Quarter 01 | Achievement (%)
16 | Puraneguma | Water Supply Projects - Completed | Ibbagamuwa WS |  |  | 1 | 1

## dashebord
Project Progress of Foreign Funded Projects - 2021
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## DATABASE
NO | PRO | Component | Sub Components | Overall Target | Overall Achivement | Target Quarter | Achievement (%)
1 | GCWMPI | Rehabilitation of Pumping Stations | Wannthamulla PS | 82% | 76% | 100% | 96.51%
2 | GCWMPI | Rehabilitation of Pumping Stations | Maligawatta PS |  |  | 100% | 74.38%
3 | GCWMPI | Rehabilitation of Pumping Stations | Vystwyke PS |  |  | 100% | 70.81%
4 | GCWMPI | Rehabilitation of Pumping Stations | Bambalapitiya PS |  |  | 100% | 99.7%
5 | GCWMPI | Rehabilitation of Pumping Stations | Thibirigasyaya PS |  |  | 100% | 72.59%
6 | GCWMPI | Rehabilitation of Pumping Stations | Slave Island |  |  | 100% | 95.98%
7 | GCWMPI | Rehabilitation of Pumping Stations | Borella |  |  | 100% | 60.93%
8 | GCWMPI | Rehabilitation of Pumping Stations | CS3 |  |  | 100% | 99.79%
9 | GCWMPI | Rehabilitation of Pumping Stations | Central Monitoring System |  |  | 100% | 78.16%
10 | GCWMPI | Rehabilitation of Pumping Stations | Drainage Division Workshop |  |  | 100% | 100%
11 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Thambalawewa extentions in Bandiwewa Water Supply Scheme in Polonnaruwa District. | 73% | 67% | 100% | 100%
12 | Puraneguma | 3. Treatment Plant - Completed | Minneriya Water treatment Plant Improvement Project (Construction of Rapid Sand Filter) |  |  | 100% | 100%
13 | Puraneguma | 2. Water Supply - Ongoing | Extension of Water Supply Scheme of Thambala in Polonnaruwa District |  |  | 100% | 98%
14 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Uththupitiya (From Kekirawa Water Supply Scheme) in Anuradhapura District |  |  | 100% | 100%
15 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Mahailuppallama and Thirappane in Anuradhapura District |  |  | 100% | 100%
16 | Puraneguma | 1. Water Supply Projects - Completed | Extentions to Elagamuwa Main and Distribution System in Anuradhapura District |  |  | 100% | 100%
17 | Puraneguma | 1. Water Supply Projects - Completed | Improvements to Kebithigollewa Water Supply Scheme, NCP |  |  | 100% | 100%
18 | Puraneguma | 1. Water Supply Projects - Completed | Rajanganaya, Namalgamuwa and Kandegama in Anuradhapura District |  |  | 100% | 100%
19 | Puraneguma | 1. Water Supply Projects - Completed | Extention to Ibbagamuwa, (Pipe Network) North Western Province |  |  | 100% | 100%
20 | Puraneguma | 1. Water Supply Projects - Completed | Ibbagamuwa Water Supply Scheme |  |  | 100% | 100%
21 | Puraneguma | 1. Water Supply Projects - Completed | Rideemaliyadda (at Kuralawela, Ekiriyankumbura) |  |  | 100% | 100%
22 | Puraneguma | 2. Water Supply - Ongoing | Rahathangama, Kumaragama and Kukurampola (From Buttala Water Supply Scheme) |  |  | 29% | 18%
23 | Puraneguma | 1. Water Supply Projects - Completed | Renovation and Augmentation of existing Water Treatment Plant at Dambulla |  |  | 100% | 100%
| Puraneguma | 2. Water Supply - Ongoing | Sewagama Water Tower | 73% | 67% | 100% | 91.27%
| Puraneguma | 2. Water Supply - Ongoing | Nikaweratiya-Ambanpola |  |  | 100% | 90%
| Puraneguma | 2. Water Supply - Ongoing | Karuwalagaswewa Pradeshiya Sabha |  |  | 78% | 43%
| Puraneguma | 2. Water Supply - Ongoing | Bathalayaya and Belaganwewa Areas |  |  | 63% | 54%
| Puraneguma | 2. Water Supply - Ongoing | Passara Water Supply Scheme |  |  | 42% | 34%
| Puraneguma | 2. Water Supply - Ongoing | Dambulla Rural Areas and Kandalama |  |  | 67% | 57%
| Puraneguma | 2. Water Supply - Ongoing | Inamaluwa and Kithulhitiyawa |  |  | 98% | 84%
| Puraneguma | 2. Water Supply - Ongoing | Sigiriya and Habarana |  |  | 98% | 83%
| Puraneguma | 2. Water Supply - Ongoing | Galewela and Tiththawelgolla |  |  | 87% | 74%
| Puraneguma | 2. Water Supply - Ongoing | Pahaladiggala |  |  | 39% | 33%
| Puraneguma | 2. Water Supply - Ongoing | Udapalatha, Udadumbara and Wilgamuwa PS Areas |  |  | 82% | 61%
| Puraneguma | 2. Water Supply - Ongoing | Nattandiya Pradeshiya Sabha |  |  | 100% | 90%
| Puraneguma | 2. Water Supply - Ongoing | Water Bowsers NWP |  |  | 30% | 90%
24 | Puraneguma | 3. Treatment Plant - Completed | Minneriya Treatment Plant in NCP | 73% | 67% | 100% | 100%
26 | Puraneguma | 3. Treatment Plant - Ongoing | Nuwarawewa Water Treatment Plant, North Central Province |  |  | 100% | 94.8%
27 | Puraneguma | 3. Treatment Plant - Ongoing | Kalawewa Treatment Plant, NCP |  |  | 100% | 80%
31 | Puraneguma | 3. Treatment Plant - Ongoing | Augmentation of Girandurukotte Treatment Plant |  |  | 35% | 41%
32 | Puraneguma | 3. Treatment Plant - Ongoing | Augmentation of Girandurukotte Treatment Plant |  |  | 5% | 22%
42 | Puraneguma | 3. Treatment Plant - Ongoing | Tissawewa Treatment Plant, NCP
43 | Puraneguma | 4. PS Buildings - Completed | Nanu Oya - Nuwara Eliya Pradeshiya Sabha | 100% | 99% | 100% | 100%
44 | Puraneguma | 4. PS Buildings - Completed | Pallepola Pradeshiya Sabha |  |  | 100% | 100%
46 | Puraneguma | 4. PS Buildings - Completed | For Kurunegala Pradeshiya Sabha |  |  | 100% | 100%
47 | Puraneguma | 4. PS Buildings - Completed | Netolpitiya for Tangalle Pradeshiya Sabha |  |  | 100% | 100%
48 | Puraneguma | 4. PS Buildings - Completed | Habaraduwa Pradeshiya Sabha |  |  | 100% | 100%
49 | Puraneguma | 4. PS Buildings - Completed | Nayagoda for Rathgama Pradeshiya Sabha |  |  | 100% | 100%
50 | Puraneguma | 4. PS Buildings - Completed | Baddegama |  |  | 100% | 100%
51 | Puraneguma | 4. PS Buildings - Completed | Bentota Pradeshiya Sabha |  |  | 100% | 100%
52 | Puraneguma | 4. PS Buildings - Completed | Pahala Karagahamuna for Mahara PS - Stage 1 |  |  | 100% | 100%
53 | Puraneguma | 4. PS Buildings - Completed | Waskaduwa Town for Kalutara PS-Stage 1 |  |  | 100% | 100%
54 | Puraneguma | 4. PS Buildings - Completed | Kandana for Ja-Ela PS - Stage 1 |  |  | 100% | 100%
55 | Puraneguma | 4. PS Buildings - Completed | Mahabage for Wattala PS |  |  | 100% | 100%
56 | Puraneguma | 4. PS Buildings - Completed | Beruwala Pradeshiya Sabha - stage 1 |  |  | 100% | 100%
| Puraneguma | 5. PS Buildings - Ongoing | For Narammala Pradeshiya Sabha |  |  | 100% | 98%
57 | Puraneguma | 4. PS Buildings - Completed | Southern Province (Ambalangoda, Baddegama, Habaraduwa, Ratgama, Tangalla and Matara PSs | 100% | 99% | 100% | 100%
58 | Puraneguma | Health Centres | Matale Pradeshiya Sabha | 100% | 90% | 100% | 100%
59 | Puraneguma | Health Centres | Mahawatta for Kundasale Pradeshiya Sabha |  |  | 100% | 100%
60 | Puraneguma | 4. PS Buildings - Completed | Polgolla for Kundasale PS |  |  | 100% | 100%
61 | Puraneguma | Health Centres | Udunuwara for Pradeshiya Sabha |  |  | 100% | 100%
62 | Puraneguma | Health Centres | Nahena for Kelaniya Pradeshiya Sabha |  |  | 58% | 53%
63 | Puraneguma | Public Market | Gelioya for Udunuwara Pradeshiya Sabha | 100% | 95% | 100% | 100%
64 | Puraneguma | Public Market | Polgahawela for Polgahawela Pradeshiya Sabha |  |  | 100% | 98%
65 | Puraneguma | Public Market | Madurankuliya for Puttalam Pradeshiya Sabha |  |  | 100% | 100%
66 | Puraneguma | Public Market | Balapitiya Pradeshiya Sabha |  |  | 100% | 100%
67 | Puraneguma | Public Market | Kekandura for Matara Pradeshiya Sabha - SP |  |  | 100% | 100%
68 | Puraneguma | Public Market | Homagama Pradeshiya Sabha - Stage 1 |  |  | 100% | 100%
69 | Puraneguma | Public Market | Wadduwa for Panadura Pradeshiya Sabha |  |  | 75% | 68%
70 | Puraneguma | Library | Dunkannawa for Naththandiya Pradeshiya Sabha | 100% | 100% | 100% | 100%
71 | Puraneguma | Library | Madurankuliya for Puttalam Pradeshiya Sabha |  |  | 100% | 100%
72 | Puraneguma | Weekly Fair | Gonagala for Bentota Pradeshiya Sabha | 100% | 100% | 100% | 100%
73 | Puraneguma | Auditorium | Batapola for Ambalangoda Pradeshiya Sabha | 100% | 99% | 100% | 100%
74 | Puraneguma | Auditorium | Kadirana for Katana PS |  |  | 100% | 100%
75 | Puraneguma | Crematorium | Warakapitiya for Weligama Pradeshiya Sabha | 100% | 90% | 95% | 90%
76 | TCAMP-PRDP | 1. Phase I Stage I | WP/01 | 45% | 30.67% | 100% | 67.5%
77 | TCAMP-PRDP | 1. Phase I Stage I | WP/02 | - | - | 100% | 82%
78 | TCAMP-PRDP | 1. Phase I Stage I | SP/01 | - | - | 80% | 95.5%
79 | TCAMP-PRDP | 1. Phase I Stage I | SP/02 | - | - | 60% | 40%
80 | TCAMP-PRDP | 1. Phase I Stage I | EP/01 | - | - | 50% | 30.99%
81 | TCAMP-PRDP | 1. Phase I Stage I | EP/02 | - | - | 50% | 37.25%
82 | TCAMP-PRDP | 1. Phase I Stage I | NWP/01 | - | - | 80% | 84.84%
83 | TCAMP-PRDP | 1. Phase I Stage I | NWP/02 | - | - | 15% | 3.18%
84 | TCAMP-PRDP | 2. Phase I Stage II | NCP/01 | 45% | 30.67% | 35% | 47.68%
85 | TCAMP-PRDP | 2. Phase I Stage II | NCP/02 | - | - | 20% | 10.21%
86 | TCAMP-PRDP | 2. Phase I Stage II | UV/01 | - | - | 12% | 10.2%
87 | TCAMP-PRDP | 2. Phase I Stage II | CP/01 | - | - | 12% | 10.2%
88 | TCAMP-PRDP | 2. Phase I Stage II | CP/02 | - | - | 12% | 9.6%
89 | TCAMP-PRDP | 2. Phase I Stage II | NP/01 | - | - | 10% | 2.5%
90 | TCAMP-PRDP | 2. Phase I Stage II | NP/02 | - | - | 30% | 10.1%
91 | TCAMP-PRDP | 3. Phase II Stage I | WP/03 | 45% | 30.67% | 15% | -
92 | TCAMP-PRDP | 3. Phase II Stage I | NWP/03 | - | - | 15% | 6.82%
93 | TCAMP-PRDP | 3. Phase II Stage I | NCP/03 | - | - | 15% | 1.32%
94 | TCAMP-PRDP | 3. Phase II Stage I | UV/03 | - | - | 15% | 2.3%
95 | TCAMP-PRDP | 3. Phase II Stage I | EP/04 | - | - | 15% | -
96 | TCAMP-PRDP | 3. Phase II Stage I | CP/03 | - | - | 15% | -
97 | TCAMP-PRDP | 3. Phase II Stage I | NP/03R | - | - | 5% | -
98 | TCAMP-PRDP | 3. Phase II Stage I | SP/03R | - | - | 5% | -
99 | TCAMP-PRDP | 3. Phase II Stage I | EP/03R | - | - | 5% | -
100 | TCAMP-PRDP | 3. Phase II Stage I | UV/05R | - | - | 5% | -
101 | TCAMP-PRDP | 3. Phase II Stage I | SG/04R | - | - | 5% | -
102 | TCAMP-PRDP | 3. Phase II Stage I | SG/05R | - | - | 5% | -

## TEC
Row Labels
TCAMP-PRDP
Grand Total

## Allocation
Row Labels
TCAMP-PRDP
Grand Total

## Financil_Progress
Row Labels | Sum of Overall Target | Sum of Overall Achivement
TCAMP-PRDP | 0.45 | 0.3067
Grand Total | 0.45 | 0.3067

## Physical
Row Labels | Sum of target Quarter | Achievement
SP/01 | 0.8 | 0.955
SP/02 | 0.6 | 0.4
WP/01 | 1 | 0.675
WP/02 | 1 | 0.82
EP/01 | 0.5 | 0.3099
EP/02 | 0.5 | 0.3725
NWP/01 | 0.8 | 0.8484
NWP/02 | 0.15 | 0.0318
Grand Total | 5.35 | 4.4126

## Sheet4
NO | PRO | Component | Total Estimate Cost | Allocation | Financial_TQ2 | ExpenditureQ2 | Cumulative Expenditure | Target_Quarter | Achievement (%)
39 | GCWMPI | Interest and Commitment Chargers |  | 80 | 40 | 52.88 |  | 0 | 0
38 | GCWMPI | Project Administration |  | 24 | 12 | 22.06 |  | 0 | 0
37 | GCWMPI | Training and Capacity development |  | 42.4 | 22.2 | 0.26 |  | 0 | 0
36 | GCWMPI | Individual Consultants |  | 61.6 | 30.8 | 16.57 |  | 0 | 0
35 | GCWMPI | Rehabilitation of CS19 sewer / wannathamulla sewer |  | 150 | 60 | 0 |  | 0.16 | 0
34 | GCWMPI | Rehabilitation of Pumping Stations |  | 2580 | 1290 | 351.37 |  | 0.65 | 0.416
33 | GCWMPI | Condition Assessment of sewer |  | 895 | 586 | 216.36 |  | 0.997 | 0.9619